## Summary Performance (hidden)
Status as of: |  |  | 2014-01-30
Raised by | TYPE OF ACTION
| Incidents | [5 empty] | Audit AOR / CAR | [5 empty] | Meetings | [5 empty] | Inspections
| Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue
Facility
Marine
Area / Others
Total: |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0
Monthly Performance: Facility | TYPE OF ACTION
| Incidents | [5 empty] | Audit AOR / CAR | [5 empty] | Meetings | [5 empty] | Inspections
| Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue
January
February
March
April
May
June
July
August
September
October
November
December
Monthly Performance: Marine | TYPE OF ACTION
| Incidents | [5 empty] | Audit AOR / CAR | [5 empty] | Meetings | [5 empty] | Inspections
| Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue
January
February
March
April
May
June
July
August
September
October
November
December
Monthly Performance: Others / Area | TYPE OF ACTION
| Incidents | [5 empty] | Audit AOR / CAR | [5 empty] | Meetings | [5 empty] | Inspections
| Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue | Raised | Active | Closed, Not Overdue | Open, Not Overdue | Closed, Overdue | Open, Overdue
January
February
March
April
May
June
July
August
September
October
November
December

## MDR Incidents (hidden)
CENTRAL ACTION REGISTRY - INCIDENTS
Control / Reference Number | Class | Action Title / Description | Type of Incident | Project / Department | Client | Entity Name | Priority / Criticality | Description of Action | Originator / Responsible Person | Date Assigned | Date Target | Person Assigned | Status | Date Completed | Closed Out Justification | Comments
MEP-15002-D6376-PD-NWR | Incident | NWR - Fire on Decoder Unit | NWR | D6376 | ARAMCO | MEP | C1 | Replace the decoder and network combining unit. | Hari Nair | 2014-01-08 | 2015-01-22 | Paul Morris | Open |  |  | Reminder sent: 15 Jan 2015
MEP-15002-D6376-PD-NWR | Incident | NWR - Fire on Decoder Unit | NWR | D6376 | ARAMCO | MEP | C1 | The unit to be included in the preventive maintenance system and periodically inspected as per the schedule including other electrical appliances located in the camp facility. | Hari Nair | 2014-01-08 | 2015-01-22 | Paul Morris | Open |  |  | Reminder sent: 15 Jan 2015
MEP-15002-D6376-PD-NWR | Incident | NWR - Fire on Decoder Unit | NWR | D6376 | ARAMCO | MEP | C1 | Assessments should be carried out at the camp facility to ensure appropriate fire extinguisher types are located as per the requirement. | Hari Nair | 2014-01-08 | 2015-01-22 | Paul Morris | Open |  |  | Reminder sent: 15 Jan 2015
MEP-15001-D6113-NM | Incident | Excavated Cable Trench Cave-in | NM | D6113 | ARAMCO | MEP | C2 | Review the existing TRA (MACL/SFNY/GOSP 1/JSA/001) and include the hazards and controls associated with excavated trenches below 1.2 m | Hari Nair | 2014-01-10 | 2014-01-24 | Abdullah Qahtani | Open |  |  | Reminder sent: 10 Jan 2015 & 15 Jan
MEP-15001-D6113-NM | Incident | Excavated Cable Trench Cave-in | NM | D6113 | ARAMCO | MEP | C1 | Counsel the involved MACL crew consisting of Civil Engineer, E&I Engineer and Electrical Foreman for failing to conduct thorough risk assessment prior to execution of task. | Hari Nair | 2014-01-10 | 2014-01-17 | Abdullah Qahtani | Closed | 2015-01-13 |  | Copy of counsel form held on file, conducted by Ahmed Ghamdi on 12th Jan 2015 to: 39335, 35588, 92199.
MEP-15001-D6113-NM | Incident | Excavated Cable Trench Cave-in | NM | D6113 | ARAMCO | MEP | C1 | Civil Engineer and HSE Rep to conduct a physical assessment of existing trenches to identify any hazards and apply appropriate controls. | Hari Nair | 2014-01-10 | 2014-01-17 | Abdullah Qahtani | Closed | 2015-01-13 |  | Copy of HSES inspection report held on file, date of inspection 5th Jan, 2015; Report No. 01-2015.
MEP-15001-D6113-NM | Incident | Excavated Cable Trench Cave-in | NM | D6113 | ARAMCO | MEP | C2 | Mandatory HSE training (Safe Working Practices, HSE Management System awareness, Permit to work, Hazard and Risk Recognition - TRA & HIT) for Civil Engineer to be organized for attendance at the earliest. | Hari Nair | 2014-01-10 | 2014-02-09 | Abdullah Qahtani | Open |  |  | Reminder sent: 10 Jan 2015
MEP-15001-D6113-NM | Incident | Excavated Cable Trench Cave-in | NM | D6113 | ARAMCO | MEP | C1 | Discuss “MEP-15001-D6113-NM-Excavated Cable Trench Cave in” final incident report with all personnel on site currently involved in excavation/trenching activities. | Hari Nair | 2014-01-10 | 2014-01-17 | Abdullah Qahtani | Closed | 2015-01-11 |  | Copy of attendance sheet held on file conducted by Ahmed Gamdi, Civil & E&I, 10th Jan
[11 empty] | 2014-09-30 | TWI Middle East FZ LLC, UAE | Closed Overdue | 2014-10-21 | Email received from Rosalle Dizon with close out documents for AOR's
[11 empty] | 2014-12-31 | All | Open
[11 empty] | 2014-07-30 | WL/JF | Closed | 2014-07-30 | Verification documents held on file
[11 empty] | 2014-10-30 | Satheesh Kumar | Closed | 29-Oct-14 | Draft procedure reviewed by project personelle and considered complete
[11 empty] | 2014-10-30 | Dana Smith | Closed | 29-Oct-14 | Included in RFQ
[11 empty] | 2014-11-20 | Roland Cotton | Closed | 2014-11-15 | Copy of email from Roland Cotton dated 15th Nov. 14 held on file confirming warning to the employee as verbal and without other reference.
[11 empty] | 2014-11-20 | Roland Cotton | Closed | 2014-11-15 | Copy of email with pictures of the stand down/TBT from Roland Cotton thru Leo Nuarin dated 15th Nov. 14 held on file with the TBT attendance sheet.
[11 empty] | 2014-12-18 | Terry Fullerton / Asif Jamaludeen | Closed | 2014-11-17 | Copy of OSCM slide discussed 17th Nov.14 held on file
[11 empty] | 2014-12-02 | Allen Watts | Closed | 2014-11-23 | Copy of Email notification sent to Allen W. held on file dated 24th Nov. 14 confirming the inspection along with photo reference.
[11 empty] | 2014-12-02 | Steve Thibodeaux / Kosta Kathreptakis | Closed | 2014-11-17 | Copy of OSCM slide discussed 17th Nov.14 held on file
[11 empty] | 2014-11-30 | Allen Watts | Closed | 2014-11-25 | Copy of TBT held on file, conducted by Netra at the Rigging dept. dated 25th Nov. 14
[11 empty] | 2014-11-30 | Allen Watts | Closed | 2014-11-26 | Copy of email confirmation of the close-out item held on file sent by Allen Watts counseling the AC forklift operator.
[11 empty] | 2014-11-30 | Graham Stevenson | Closed | 2014-11-24 | Copy of Disciplinary action held on file. Issued to Jang Bahadur Pun 91638 at the Scaffolding Dept. dated 15th Nov.14
[11 empty] | 2014-12-04 | Anil Nair | Closed | 2014-12-03 | Email notification received from Anil Kumar confirming close out for action item received dated 3rd Dec.14
[11 empty] | 2014-12-04 | Shyam Deshmukh | Closed | 2014-12-03 | Copy of TBT held on file, conducted by Shyam Deshmukh at Fab Operations dated 2nd Dec.2014
[11 empty] | 2014-11-08 | Oleg Zhyla | Closed | 2014-11-01 | IP counseling sheet signed by (Master, Chief Engr and IP) provided as supporting document, IP agreed with the discussion.
[11 empty] | 2014-11-08 | Wade Hume | Closed | 2014-11-01 | Signed attendance sheet copy received as supporting document, incident lessons learned discussed in operations meeting and tool box talk.
[11 empty] | 2014-12-01 | Shashi Sonawane | Closed | 2014-11-01 | Pictures of signage posted indicating to remove shoe cover prior or exit provided as supporting document.
NWR
Note on K3: mfernandes03: Report released on 11 Jan 2015

## Audit1 (hidden)
CENTRAL ACTION REGISTRY- AUDIT
If External Audit (company name) | Auditor | Audit Ref Number | Audit Title/Description | Department / Project / Vessel | CAR/AOR number | Criticality | Requirement | Findings | Date Assigned | Date Target | Person Assigned | Status | Date Completed | Comment
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 1 | 3 | 1.11.3 Noise Measurement and Analysis Noise survey shall be conducted by the HSES department - Every year in all areas to determine trends or changes in noise levels - Whenever there is a change in production, process, equipment and controls | No Annual noise survey performed in the barge (2012) | 2013-02-05 |  |  | OPEN
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 2 | 3 | Operations units will implement an ergonomic hazard control system. The system will include a survey of job tasks to identify those with potential ergonomic problems. | No documented ergonomic survey performed in the barge. | 2013-02-05 | 2013-02-20 | HSES Department | CLOSED | 2013-02-20 | Verified as per the attached (Ergonomic Assement and Feedback form provided) Note: please ensure to maintain action registry on survey where actions require follow up.
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 3 | 3 | A system will be implememented for assessing potential risk of worker exposure to airborne and contact contaminates. Develop a schedule for periodic monitoring of tasks / operations to verify controls are adequate - (annual activity plan) | No annual survey (2012) performed as per the requirement. The last industrial hygiene (IH) assessment performed on March 2011 | 2013-02-05 |  |  | OPEN
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 4 | 2 | Preventive Maintenance MDR has implemented a planned preventative maintenance system to reduce injuries, environmental damage and property loss. All equipment, machinery and critical HSES equipment that requires periodic inspection and maintenance has been included in the yard / MWB computerized planned maintenance system. Critical can be defined as the potential for mechanical, electrical or strucutural failure that would likely result in human injury / illness, harm to the environment or damage of the asset. | Numerous below the hook devices with outdated color code, Monorail third party certifications noted done last 2008. | 2013-02-05 | 2013-03-30 | Chief Engineer | CLOSED | 2013-03-10 | Verified as per the attached, also added the PMS verification (see attached e-mail)
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 5 | 3 | The knowledge of Project Managers and Craft Supervisors (Superintendents, Foreman, and Leaderman levels) on the HSES Safe Work Practice will be assessed annually. | No evidence of formal assessment of HSES Work Practices knowledge of craft supervisors on past years. | 2013-02-05 | 2013-02-20 | HSES Department | CLOSED | 2013-02-20 | Verified as per the attached (SWP knowledge assessment test result provided)
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 6 | 2 | Rails around stairway, floor openings, barge decks, dry-docks, and other work surfaces above 6 feet (2 meters) that pose an injury risk due to a fall from the surface. (A work instruction shall be developed by each Operations Unit to minimize Fall hazards at Bulkheads) | Motor store ladder access opening on top without cover at boom rest (clyde crane). A number of instances where the ladder cages / straight ladder with round bar or chains are not in place to prevent fall exposure. Also chains in some mooring bollard areas left open. | 2013-02-05 | 2013-02-20 | CH Eng / HSES Department | CLOSED | 2013-02-20 | Verified as per the attached (photo provided)
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 7 | 3 | Conduct lighting surveys, using an approved lux meter at least annually, in accordance with local governing standards. The MDR HSES department shall conduct lighting surveys applicable to the HSES Activity plans. | No annual light survey performed for the barge (last survey performed on Aug 27, 2010) | 2013-02-05 |  |  | OPEN
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 8 | 2 | Shelves and bins shall be capable of withstanding the loads to be applied. | Numerous shelves and load supports without SWL stamped. See photos | 2013-02-05 |  |  | OPEN
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 9 | 2 | Fixed locations and portable fire extinguishers shall be inspected monthly as per the requirements of HSES critical equipment of the HSES Administration manual. Extinguishers will be included in PM system as per corporate guideline requirements. | Few fire extinguishers are expired and some noted corroded and not inspected. Hydrotest of fire extinguishers are delinquent. No inspection tags in place to determine internal monthly inspections. | 2013-02-05 | 2013-02-20 | L2CC / HSES Department | CLOSED | 2013-02-21 | Verified as per the attached (Full fire extinguisher inspection carried out, inspection report provided)
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 10 | 2 | The use of folding knives in the work environment is prohibited. This includes locking folding knives and multi tool devices or knives with retractable blades. Where knives are allowed OU of the following shall apply: knives must have fixed blade single edged blade. The tip of the knife shall be blunt (non - stiletto) type | Numerous riggers knives noted with sharp tip / pointed | 2013-02-05 |  |  | OPEN
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 11 | 2 | The correct personal protective equipment shall be worn during grinding work. Grinder operators shall wear approved eye protection and an impact resistant full face shield complete with appropriate hearing protection. Where the impact resistant face shield is not a welders type hood, impact resistant goggles shall be worn under the shield. Where it is not practicable to install screening, personnel working within 10 feet of the grinding operations must also wear goggles and hearing protection. | Noted employee not using faceshield while grinding. Wearing of face shield and safety glass during grinding is an accepted practice in barge, however, this is a deviation from the global standard PPE requirements and this should be subject to global HSES approval. | 2013-02-05 | 2013-02-20 | HSES Department | CLOSED | 2013-02-24 | Verified as per the attached (Toolbox meeting attendance sheet 71 attendees and photo i.e notice boards provided)
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 12 | 2 | All portable (not scaffold) ladders shall be registered and identified with a unique serial number that includes an identifier of its department. Formal ladder inspections will be performed on a quarterly basis and entered into the ladder registry. | Some ladders with no identification tag and some with number tag but not included / recorded on planned inspection program. | 2013-02-05 | 2013-02-20 | L2CC | CLOSED | 2013-02-20 | Verified as per the attached (photo and scaffold ladder monthly inspection report provided)
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 13 | 2 | All safety harnesses shall be identified with a unique serial number and registered. The date that the harness was put into service shall be logged on the fall protection equipment registry and / or clearly marked by etching / inscribing / engraving onto an ID plate that is attached to the harness and lanyard issuance once per month on an ongoing basis. | Some safety harnesses and lanyards on site are not regularly inspected as per monthly inspection report. | 2013-02-05 | 2013-02-20 | L2CC / HSES Department | CLOSED | 2013-02-21 | Verified as per attached (WO/SR 0954896: Safety harness inspection report provided)
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 14 | 2 | 5.8 Personal Floatation Devices (Buoyancy Vests / Work Vests) When worn, the wearer shall perform a pre use condition check and ensure the PFD is tight, but comfortable, that all locking clasps are secured, that reflective tape is fitted and the vest is in good condition. Damage such as missing or broken buckles, burn holes in straps or missing straps dictates that the vest is unserviceable and shall be discarded. | Some PFDs noted defective and no regular inspection records presented during audit. Last documented inspection performed on November 2012 | 2013-02-05 | 2013-02-20 | L2CC / HSES Department | CLOSED | 2013-02-21 | Verified as per the attached (Work Vests (PFD) Welders and Riggers inspection report provided)
INTERNAL | Emelblaser Espartero | GAR-013-13 | IMSAFE Audit (Silver: 91.85%) | DB30 | CAR 15 | 3 | The responsible superintendents shall conduct an annual audit of the procedures of this program. This audit shall consist of a review of procedures and a discussion with each authorized employee participating in an actual lockout / tagout procedure in order to determine the understanding of and compliance with this procedures. | No records of audit on LOTO program | 2013-02-05 |  |  | OPEN
INTERNAL | Aneesh Kumar / Manjush Sidharthan | 13/201 | Hazardous Work Areas | D6197 - 3 PDMs | 13/AOR/004 |  |  | Observed that kickboards were not fitted below the handrails at two locations on 3 PDMs decks. Kickboards shall be fitted below the handrails along all exposed edges | 2013-01-28 | 2013-01-28 | Johnson Thomas | CLOSED | 2013-01-29

## Audits (hidden)
AOR NO | AUDIT REF | AUDIT DATE | ORIGINATOR | AOR ISSUED DATE (ACKNOWLEDGED BY AUDITEE) | AOR ISSUED TO | DEFICIENCY | AGREED COMP DATE | ACTUAL CORRECTIVE ACTION COMP-LETION DATE | AOR CLOSED DATE | STATUS | PROJECT | DEPT
13/AOR/071 | 13/216 | 2013-04-24 | Fritz Gamalo | 2013-05-11 | Sridhar Rao | The electronic copy of HAZID central action registry was verified but hard copy of the central action registry with valid signature from the responsible authority was not available | 2013-05-15 |  |  | OPEN | N/A | KARAN PMT
13/AOR/069 | 13/214 | 2013-05-01 | Nolito V. | 2013-05-01 | Rosalle Dizon | Central action registry log was updated. However , there was a pending item to be closed supposedly September 2012. Criticality of action item was not mentioned | 2013-06-15 |  |  | OPEN | N/A | HSES
13/AOR/070 | 13/214 | 2013-05-01 | Nolito V. | 2013-05-01 | Rosalle Dizon | Audit was not carried out as per the schedule due to unavailability of the auditors. | 2013-06-15 |  |  | OPEN | N/A | QAQC
(Action Assigned To QA Team)
13/AOR/049 | 13/212 | 31-Mar-13 & | Joseph P | 2013-04-06 | Wade Hume / Tim Griffiths | Live HAZID registry for spools and Riser Installation by DSV TS (D6420-SAOC-SFTY-519) does not reflect close out target dates. | 2013-05-10 |  |  | OPEN | N/A | Thebaud Sea
2013-04-06
13/AOR/050 | 13/212 | 31-Mar-13 & | Joseph P | 2013-04-06 | Wade Hume / Tim Griffiths | Some of the archive TRAs or hard copies were found to be redundant and does not have index for each department | 2013-05-31 |  |  | OPEN | N/A | Thebaud Sea
2013-04-06
13/AOR/051 | 13/212 | 31-Mar-13 & | Joseph P | 2013-04-06 | Wade Hume / Tim Griffiths | No quick reference of PTW signatories was observed in the bridge as PTW is controlled by Marine group. | 2013-04-10 | 2013-04-08 | 2013-04-09 | CLOSED | N/A | Thebaud Sea
2013-04-06
13/AOR/052 | 13/212 | 31-Mar-13 & | Joseph P | 2013-04-06 | Wade Hume / Tim Griffiths | Equipment isolation for No. 1 cat. Generator was observed not having the tag | 2013-04-16 | 2013-04-14 | 2013-04-14 | CLOSED | N/A | Thebaud Sea
2013-04-06

## OTHERS (hidden)
CENTRAL ACTION REGISTRY - AUDIT
Audit Report Number | Audit Title / Description | CAR / AOR Number | Project / Department | Entity Name | Criticality | Description of Action / Deficiency | Auditor/s | Date Assigned | Date Target | Person Assigned | Status | Date Completed | Comment
14/VDR/001 | M/s Al Khobar Gate International Trading | 14-VDR-AOR-001 | IK OFFICE | IK | N/A | Lifting equipment and tools and tackles to be inspected and certified by 3rd party | Ramesh Kanase | 2014-01-11 | 2014-02-28 | Samuel Bhath | Open, Overdue
14/VDR/001 | M/s Al Khobar Gate International Trading | 14-VDR-AOR-002 | IK OFFICE | IK | N/A | HSES Management system to be developed and implemented. Risk assessment - latest copy with communication card, internal training, emergency management, workshop observations - poor housekeeping, oil storage | Ramesh Kanase | 2014-01-11 | 2014-02-28 | Samuel Bhath | Open, Overdue
14/VDR/002 | Falck Safety Services LLC. UAE | 14/VDR/AOR/003 | HSES Training | MEA | N/A | the training manager should complete the appraisals and document the trainer's developmental plan. State in the procedure that the annual appraisals are one of the documents that explain the development of the trainers | Ashley Fernandes | 2014-02-03 | 2014-01-16 | Alan Sharp | Closed, Overdue | 2014-02-03
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-AOR-001 | IK OFFICE | IK | N/A | HSE Policy is not available in Arabic Language. | Praveen Patil | 2014-01-26 | 2014-03-15 | Hussein Elhosseiny | Closed, Overdue | 2014-03-18
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-AOR-002 | IK OFFICE | IK | N/A | Display of HSE Policies and other relevant policies is not controlled | Praveen Patil | 2014-01-26 | 2014-01-15 | Hussein Elhosseiny | Closed | 2014-01-30
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-AOR-003 | IK OFFICE | IK | N/A | Organization Chart is available though the chart does not reflect clinic and security sub function of HSES function. Additionally the organization chart has no control number. | Praveen Patil | 2014-01-26 | 2014-01-25 | Hussein Elhosseiny | Closed | 2014-01-30
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-AOR-004 | IK OFFICE | IK | N/A | Arabic speaking HSES trainer is not available. | Praveen Patil | 2014-01-26 | 2014-03-15 | Hussein Elhosseiny | Closed, Overdue | 2014-03-18 | HSES lead to monitor compliance with train the trainer schedule
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-AOR-005 | IK OFFICE | IK | N/A | Centralized data management(folder) for capturing leading and lagging indicators related to Environmental Health and Safety Performance is not available. | Praveen Patil | 2014-01-26 | 2014-01-31 | Hussein Elhosseiny | Closed | 2014-01-30
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-AOR-006 | IK OFFICE | IK | N/A | CATR (Central Action Tracking Registry) is established for capturing readiness review actions however separate CATR's need to be established and maintained for capturing actions from audits, inspections, HAZID's Safety Committee meetings, incidents etc. | Praveen Patil | 2014-01-26 | 2014-01-31 | Hussein Elhosseiny | Closed | 2014-01-30
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-AOR-007 | IK OFFICE | IK | N/A | Display of sign boards needs to be improved e.g. high voltage caution boards, chevron marking mandatory PPE etc. | Praveen Patil | 2014-01-26 | 2014-01-31 | Hussein Elhosseiny | Closed, Overdue | 2014-03-18 | Delayed due to absence of paint for chevron marking & Mandatory PPE signboard due to lack of Boundary Marking on 3/15/2014 .
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-AOR-008 | IK OFFICE | IK | N/A | Observed exposed electrical cables, unsecured gas cylinders, split Air Conditioning units secured using plastic ties ,vendors & Al Blagha personnel moving in McD controlled area without appropriate PPE. | Praveen Patil | 2014-01-26 | 2014-02-15 | Hussein Elhosseiny | Closed, Overdue | 2014-03-18
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-001 | IK OFFICE | IK | 1 | Applicable legal and other requirements for the scope work not established and documented. | Praveen Patil | 2014-01-13 | 2014-02-15 | Hussein Elhosseiny | Closed, Overdue | 2014-03-18
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-002 | IK OFFICE | IK | 2 | 2014 HSE Objectives & targets set are specific to Middle East Area and no specific O & T 's are set for the fabrication facility. | Praveen Patil | 2014-01-13 | 2014-01-31 | Hussein Elhosseiny | Closed, Overdue | 2014-03-20
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-003 | IK OFFICE | IK | 1 | Training needs in the form of training matrix and training plan is not established and documented. | Praveen Patil | 2014-01-13 | 2014-02-05 | Hussein Elhosseiny | Closed, Overdue | 2014-03-18
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-004 | IK OFFICE | IK | 2 | Procedures for preventive maintenance of equipment and tools not established and documented. Visitors not made aware of work place hazards. Controls in the form of PTW for controlling potentially hazardous activities. Waste disposed through Al Blagha approved waste management service provider through PME approvals not available. | Praveen Patil | 2014-01-13 | 2014-03-15 | Hussein Elhosseiny | Closed, Overdue | 2014-03-31
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-005 | IK OFFICE | IK | 1 | Emergency Response Plan is not established and documented. Emergency equipment not maintained. Emergency procedures are not tested. | Praveen Patil | 2014-01-13 | 2014-02-28 | Hussein Elhosseiny | Closed, Overdue | 2014-03-18
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-006 | IK OFFICE | IK | 1 | Compliance with applicable legal and other requirements not evaluated. | Praveen Patil | 2014-01-13 | 2014-02-15 | Hussein Elhosseiny | Closed, Overdue | 2014-03-18
KSA14-001 | MACL Facility Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-007 | IK OFFICE | IK | 2 | No Management Reviews are conducted to evaluate opportunities for improvement and need for changes to the system as deemed necessary. | Praveen Patil | 2014-01-13 | 2014-02-28 | Hussein Elhosseiny | Closed, Overdue | 2014-03-20
14/VDR/004 | M/s Abdullah H. Balharith & Company (ABCO) | 14-VDR-AOR-005 | IK OFFICE | IK | N/A | As the ABCO is in the process of implementation of ISO 14001 system however there is no evidence related to emergency management requirement drill not being conducted, emergency equipment such as fire extinguishers and first aid kit or box is not available in the office premises | Sachin Ghandi / Ibrahim Al Shikhi | 2014-02-15 | 2014-03-03 | Khalid Ibrahim | Open, Overdue
14/VDR/004 | M/s Abdullah H. Balharith & Company (ABCO) | 14-VDR-AOR-004 | IK OFFICE | IK | N/A | Documented evidence viz HSES policy, emergency layout, risk assessment, O&T, training records, TBT records, vehicles PM records, MSDS, equipment certification, waste skip test certificate and others were not available | Sachin Ghandi / Ibrahim Al Shikhi | 2014-02-15 | 2014-03-03 | Khalid Ibrahim | Open, Overdue
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-009 | IK OFFICE | IK | N/A | Maintenance of emergency response equipment is done by utilizing a 3rd party, no evidence of existing TRA (Task Risk Assessment) for identifying hazards and controls required during maintenance of these equipment. | Praveen Patil | 2014-02-27 | 2014-03-15 | Graham Valentine | Closed | 2014-03-15 | Accepted as closed by PP 15 March. Signed copies to be forwarded to QAQC
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-010 | IK OFFICE | IK | N/A | Incorrect Level 2 procedure references used in the Environmental Aspects and Impacts Registry (MDR-ME-L3-HSES-KSO-002), Rev 0, issued in March 2013.Similarly with reference to the Legal Registry (MDR-ME-L3-HSES-KSO-005), Rev 0, issued in March 2013, three non compliance issues were identified, corrective actions have been already established and compliance achieved though the registry is not updated to reflect the same. | Praveen Patil | 2014-02-27 | 2014-03-15 | Karthik Suribabu / Ramesh Kanase | Closed, Overdue | 2014-03-30
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-011 | IK OFFICE | IK | N/A | Employee (Badge No: 39380) New Hire Orientation Training (NHOT) has expired; NHOT is valid for 2 years. Also, incident investigation report on “Dropped File Cabinet” incident which occurred in Dec 2013 was verified and observed that one of the members of the investigation team was not trained on incident investigation and root cause analysis. | Praveen Patil | 2014-02-27 | 2014-04-10 | Shirlie Macatangay | Closed | 2014-04-07
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-012 | IK OFFICE | IK | N/A | Thuraya Phone is installed in the main conference room number 1 and the purpose of this phone is for communicating with remote site personnel in the event of mobile network error however there is no guidance for operating the Thuraya phone. | Praveen Patil | 2014-02-27 | 2014-03-15 | Graham Valentine | Closed | 2014-03-10
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-013 | IK OFFICE | IK | N/A | Lighting survey was conducted in June 2013, survey report was verified and observed that standard requirement, lux meter model and calibration date not mentioned. | Praveen Patil | 2014-02-27 | 2014-03-15 | Graham Valentine | Closed | 2014-03-15 | Accepted as closed by PP 15 March. Signed copies to be forwarded to QAQC
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-014 | IK OFFICE | IK | N/A | No evidence of maintenance records for microwave and water boiler which is being used on the 2ndfloor. | Praveen Patil | 2014-02-27 | 2014-03-31 | Graham Valentine | Closed | 2014-03-31 | Procurement /sub-contractor department were advised on to follow-up with Musanadah maintenance to revise the agreement contract to include these additional inspections.
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-015 | IK OFFICE | IK | N/A | The facility has recently shifted offices from ground and mezzanine floor to 2nd and 3rd floor of the same building. Emergency contact list, escape route and equipment layout is not updated in the Office Emergency Response Plan. | Praveen Patil | 2014-02-27 | 2014-03-15 | Graham Valentine | Closed | 2014-03-09
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-016 | IK OFFICE | IK | N/A | Expired medicine was observed in one of the First Aid box located on the 5th floor also, the medicines are not maintained as per the inventory. | Praveen Patil | 2014-02-27 | 2014-03-15 | Graham Valentine | Closed | 2014-03-10
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | kSA14-AOR-017 | IK OFFICE | IK | N/A | Frequency of office emergency drills is captured on the activity plan though this plan does not reflect the type of drills to be conducted. | Praveen Patil | 2014-02-27 | 2014-03-15 | Graham Valentine | Closed | 2014-03-09
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-008 | IK OFFICE | IK | 2 | Subcontractor (Musanadha Facilities Management) person observed conducting office furniture maintenance in McDermott visitor conference room without following McDermott HSES requirements (e.g. PPE, training, TRA etc). Also Office Administration was not aware of this activity being performed in McDermott premises. | Praveen Patil | 2014-02-19 | 2014-03-20 | Graham Valentine | Closed | 2014-03-19
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-009 | IK OFFICE | IK | 2 | Following subcontractors are classified as critical as per McDermott Level 2, Subcontractors HSES Requirements procedure however there was no evidence to show if these Subcontractors HSEMS was evaluated prior to signing agreement . Musanadha Facilities Management – Used for office maintenance works Samara – Used for hiring cars Advanced Industrial Safety Solution – Used for maintenance of fire emergency response equipment. | Praveen Patil | 2014-02-19 | 2014-03-31 | Graham Valentine | Closed Overdue | 2014-05-08
KSA14-002 | McDermott Engg. Office Compliance to ISO 14001:2004 & OHSAS 18001:2007 Standards | KSA14-CAR-010 | IK OFFICE | IK | 2 | Some of the actions on the CATR (Central Action Tracking Registry) are overdue and not closed on time. Also drill findings not captured on CATR. Provision of back support for chairs – action raised through communication card on 4th Sep 2013, assigned target close-out date is 30th Jan 2014 though the action is pending close-out. Office Services Department to conduct a survey and verify the condition/stability of office accessories - action raised as part of incident investigation on 22nd Dec 2013, assigned target date 21st Feb however the action was closed on 3rd Feb 2014. No evidence of extensions being obtained. | Praveen Patil | 2014-02-19 | 2014-03-10 | Graham Valentine | Closed, Overdue | 2014-03-15 | Accepted as closed by PP 15 March. Signed copies to be forwarded to QAQC
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/010 | North Dome D6518 | SUPERCEEDED | N/A | Staffing for IK project scope not reflected on the Staffing plan or on the 30/60/90 days Look Ahead Plan. | Praveen Patil | 2014-02-26 | 2014-03-10 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18 | Project HSES Lead to ensure plan is maintained up to date
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/011 | North Dome D6518 | SUPERCEEDED | N/A | Gap analysis performed for Aramco Construction Safety Manual and Aramco Schedule ‘D’ Requirements however other relevant Client HSES documents and SOW etc. were not verified as part of the gap analysis. | Praveen Patil | 2014-02-26 | 2014-03-25 | Alpin Harcanoglu | Closed, Overdue | 2014-07-21
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/012 | North Dome D6518 | SUPERCEEDED | N/A | Relevant Project HSES Plans were reviewed by the Functional & Project Lead though the plans are still in Rev A version. | Praveen Patil | 2014-02-26 | 2014-03-15 | Alpin Harcanoglu | Closed Overdue | 2014-04-13
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/013 | North Dome D6518 | SUPERCEEDED | N/A | Development of project specific HSES Plans is captured though review schedule is not captured on the HSES Activity Plan. | Praveen Patil | 2014-02-26 | 2014-03-05 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/014 | North Dome D6518 | SUPERCEEDED | N/A | 30/60/90 days HSES Look Ahead Plan established though not maintained up to date. | Praveen Patil | 2014-02-26 | 2014-03-05 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/015 | North Dome D6518 | SUPERCEEDED | N/A | O&T's related to Zero Fatality, LTI, Environmental Spill, Motor Vehicular Incidents, TRIR-0.2, TIFR-1 are established though these are not aligned to OU's O&T's. 2014 MEA O&T's including CATR, PROSAFE, Safety Conversation etc., not considered. | Praveen Patil | 2014-02-27 | 2014-03-10 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/016 | North Dome D6518 | SUPERCEEDED | N/A | Safety TBT's for PMT not conducted though marked as completed. PMT walkthrough marked as not applicable, office inspections not conducted. Obsolete programs still being reflected on the activity plan. HSES Activity Plan not up to date, also no evidence if the Plan was reviewed and approved by the Project Lead & Functional HSES Lead. | Praveen Patil | 2014-02-26 | 2014-03-05 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/017 | North Dome D6518 | SUPERCEEDED | N/A | Project HSES Plan is established though does not capture audits related to elements of HSES Plan, Emergency Response, Critical Subcontractor HSES activities etc. | Praveen Patil | 2014-02-26 | 2014-03-05 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/018 | North Dome D6518 | SUPERCEEDED | N/A | During demolition scope for DB27, the CSSP was sent through e-mail and only addressed to onboard HSES Advisor. | Praveen Patil | 2014-02-26 | 2014-03-05 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18 | Project HSES Lead to ensure relevant project HSES Plans are furnished to concerned personnel prior to start of campaigns
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/019 | North Dome D6518 | SUPERCEEDED | N/A | OU drill plan is used however project specific drill plan covering OOK & IK activities is not established. | Praveen Patil | 2014-02-26 | 2014-03-05 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/020 | North Dome D6518 | SUPERCEEDED | N/A | Some of the key personnel (e.g. Subcontracts) not included in the Project Management Safety Committee. | Praveen Patil | 2014-02-27 | 2014-03-10 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/021 | North Dome D6518 | SUPERCEEDED | N/A | Current agenda for Project Management Safety Committee meeting does not cover status on KPI's including O&T's, Leading indicators, audits, inspections, CATR etc. | Praveen Patil | 2014-02-26 | 2014-03-31 | Alpin Harcanoglu | Closed Overdue | 2014-05-01
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/022 | North Dome D6518 | SUPERCEEDED | N/A | No specific evidence of lessons learned and best practices being considered during the past two HAZID's. | Praveen Patil | 2014-02-26 | 2014-04-30 | Alpin Harcanoglu | Open, Overdue
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/AOR/023 | North Dome D6518 | SUPERCEEDED | N/A | Some of the Leads on the Project not trained on Safety Conversations also, no schedule established for conducting conversations. Only one conversation conducted to date for 2014. | Praveen Patil | 2014-02-26 | 2014-03-10 | Alpin Harcanoglu | Closed, Overdue | 2014-03-18 | Project manager in coordination with project HSES lead to ensure program is promoted and compliance to the schedule is achieved.
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/CAR/003 | North Dome D6518 | SUPERCEEDED | 2 | No project specific O&T action plan established for contributing towards achieving OU’s HSES goals. | Praveen Patil | 2014-02-17 | 2014-03-05 | Alpin Harcanoglu | Closed Overdue | 2014-05-01
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/CAR/004 | North Dome D6518 | SUPERCEEDED | 2 | Actions from Project Management Safety Committee meeting not captured on the CATR. | Praveen Patil | 2014-02-17 | 2014-03-20 | Alpin Harcanoglu | Closed | 2014-03-20
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/CAR/005 | North Dome D6518 | SUPERCEEDED | 1 | Seven Subcontractors are identified on the draft Subcontract Plan though the criticality is not assessed as per the guideline. | Praveen Patil | 2014-02-17 | 2014-03-15 | Alpin Harcanoglu | Closed Overdue | 2014-04-23
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/CAR/006 | North Dome D6518 | SUPERCEEDED | 1 | Subcontracts SOW is reviewed though the HSES Requirements form as specified in the guideline is not completed for including in the RFQ SOW. | Praveen Patil | 2014-02-17 | 2014-03-15 | Alpin Harcanoglu | Closed Overdue | 2014-05-01
14/203 | PROSAFE Audit for North Dome Project D6518 | 14/CAR/007 | North Dome D6518 | SUPERCEEDED | 1 | Currently OU Training Matrix is implemented for the Project however Project specific training matrix and training plan is not established for capturing Client specific training requirements. | Praveen Patil | 2014-02-17 | 2014-03-15 | Alpin Harcanoglu | Closed Overdue | 2014-05-01
AR14-VDR-006 | Baker Hughes | 14/VDR/AOR/008 | 5 Jackets D6444 and Safaniya Phase 2 D6553 | MEP | N/A | No communication matrix / flow chart established | David Brawn / Nasir Shaikh | 2014-02-02 | 2014-02-12 | Muhammad Hamada | Closed | 2014-02-12
AR14-VDR-006 | Baker Hughes | 14/VDR/AOR/006 | 5 Jackets D6444 and Safaniya Phase 2 D6553 | MEP | N/A | Secondary containment not in place for storage of paint products | David Brawn / Nasir Shaikh | 2014-02-02 | 2014-02-12 | Muhammad Hamada | Closed | 2014-02-12
AR14-VDR-006 | Baker Hughes | 14/VDR/AOR/007 | 5 Jackets D6444 and Safaniya Phase 2 D6553 | MEP | N/A | Spill kit container was found empty | David Brawn / Nasir Shaikh | 2014-02-02 | 2014-02-12 | Muhammad Hamada | Closed | 2014-02-12
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/024 | Safaniya Phase 2 D6553 | MEP | N/A | Some of the incident investigation team members not trained on Incident Investigation and Root Cause Analysis. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-31 | Mireille Soeters | Closed | 2014-03-20
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/025 | Safaniya Phase 2 D6553 | MEP | N/A | One of the RWC incidents (MEF-13003-D6376-RWC) with potential severity of 15, investigation team leader was not appointed as per the guideline. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-04-07 | Mireille Soeters | Closed | 2014-04-07
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/026 | Safaniya Phase 2 D6553 | MEP | N/A | Some of the incident NOI & PII not issued within 24 hours as defined in the guideline. Also, full incident investigation report not issued as per the time frame defined in the guideline. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-04-07 | Mireille Soeters | Closed, Overdue | 2014-04-08
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/027 | Safaniya Phase 2 D6553 | MEP | N/A | With reference to Subcontract Plan, issued on 18th February 2014 some of the Subcontracts viz., JASAF, Expertise Industrial Services are marked as closed. The Auditee confirmed that these Subcontracts current scope is completed and will be further required on the Project. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-31 | Mireille Soeters | Closed | 2014-03-27
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/028 | Safaniya Phase 2 D6553 | MEP | N/A | Subcontractor’s criticality not established for Subcontractors to be used for Back Filling Pipelines & Post Burial of Cable Trench scope. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-31 | Mireille Soeters | Closed | 2014-03-27
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/029 | Safaniya Phase 2 D6553 | MEP | N/A | Project has established safety incentive program detailing safety initiatives for the project duration. Evidence for nomination on "employee of the month" was verified and confirmed by the Auditee that no nominations received to date. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-20 | Mireille Soeters | Closed | 2014-03-18
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/030 | Safaniya Phase 2 D6553 | MEP | N/A | Applicable regulatory requirements not captured in the Project HSES Plan. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-04-07 | Mireille Soeters | Closed | 2014-04-07
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/031 | Safaniya Phase 2 D6553 | MEP | N/A | ERP sent through e-mail and only addressed to onboard HSES Advisor & Medics. Operations Key personnel & other VMT members not included. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-31 | Mireille Soeters | Closed | 2014-03-31
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/032 | Safaniya Phase 2 D6553 | MEP | N/A | Project Audit plan available though has no control number on it; also PROSAFE audit is reflected on the Project specific audit plan. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-20 | Mireille Soeters | Closed | 2014-03-18
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/033 | Safaniya Phase 2 D6553 | MEP | N/A | Sub-con meetings, O&T’s follow-up not marked, review of procedures training PMT office inspection frequency marked as weekly, PMT walkthrough not reflected for Jan, HAZID study audits review of risk register not marked, project emergency drills not marked. Some obsolete programs are still captured and also some of the activities not supported with relevant evidence. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-20 | Mireille Soeters | Closed | 2014-03-20
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/034 | Safaniya Phase 2 D6553 | MEP | N/A | MEA O&T status is discussed during the committee though project specific O&T action status not covered | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-04-08 | Mireille Soeters | Closed | 2014-04-07
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/035 | Safaniya Phase 2 D6553 | MEP | N/A | O&T's action plans available however these plans were last updated in Dec 2013. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-27 | Mireille Soeters | Closed | 2014-03-27
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/036 | Safaniya Phase 2 D6553 | MEP | N/A | 30/60/90 days HSES Look Ahead Plan established though not maintained up to date, current plan reflects activities only until March 2014. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-27 | Mireille Soeters | Closed | 2014-03-18
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/037 | Safaniya Phase 2 D6553 | MEP | N/A | One of the communication card raised in 2013 (28 August 2013, BN 88246 / Palaniappan) is not registered with the Facility HSES and likely not have been communicated (unsafe condition regarding diesel tank DT 004), also not included in project CATR registry. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-04-07 | Mireille Soeters | Closed | 2014-03-18
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/038 | Safaniya Phase 2 D6553 | MEP | N/A | One of the Leads on the Project not trained on Safety Conversations also, no schedule established for conducting conversations. Only 1 conversation was done in the month of January when compared to 4 in the month of February. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-04-08 | Mireille Soeters | Closed | 2014-03-18
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/039 | Safaniya Phase 2 D6553 | MEP | N/A | Environmental and Waste Management is captured in the Project HSES Plan however Environmental monitoring during dredging, pipe-laying and cable-laying is one of the contractual obligation and this is not covered in the HSES Plan. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-04-08 | Mireille Soeters | Closed | 2014-04-08
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/040 | Safaniya Phase 2 D6553 | MEP | N/A | Reference applicable to McDermott L2 procedures on Security is captured in the Project HSES Plan though Client Security requirements are not defined for working in Client controlled sites. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-04-08 | Mireille Soeters | Closed | 2014-04-08
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/AOR/041 | Safaniya Phase 2 D6553 | MEP | N/A | HSES Organization chart available though has no control number on it. | Praveen Patil / Laya Gatus | 2014-03-10 | 2014-03-20 | Mireille Soeters | Closed | 2014-03-18
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/CAR/008 | Safaniya Phase 2 D6553 | MEP | 2 | Out of 46 incidents reported, 30 incident investigation reports were issued past the time frame as defined in the guideline. No evidence of extensions being obtained from relevant HSES Director/Manager in the event of delay in incident investigation and subsequent report issuance. | Praveen Patil / Laya Gatus | 2014-03-03 | 2014-04-08 | Mireille Soeters | Closed, Overdue | 2014-04-09
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/CAR/009 | Safaniya Phase 2 D6553 | MEP | 1 | Subcontracts SOW is reviewed though the HSES Requirements form as specified in the guideline is not completed for including in the RFQ SOW. | Praveen Patil / Laya Gatus | 2014-03-03 | 2014-04-08 | Mireille Soeters | Closed | 2014-03-27
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/CAR/010 | Safaniya Phase 2 D6553 | MEP | 2 | No evidence of external Project HSES enquiries being tracked. E.g. Client enquiry on safety action plan issued on 18th August 2013 and non compliance to PTW issued on 22nd October 2013. | Praveen Patil / Laya Gatus | 2014-03-03 | 2014-04-08 | Mireille Soeters | Closed, Overdue | 2014-04-09
14/204 | PROSAFE Audit for Safaniya Phase 2-D6376/D6553 | 14/CAR/011 | Safaniya Phase 2 D6553 | MEP | 2 | Subcontractors (Reef Subsea, Ocean King, Ecosse) proposal for Back Filling of Pipelines works was sent to relevant PMT leads for technical review though there is no evidence of Subcontractor HSES Management System evaluation. Also, HSES Lead is not included in the TBE list. | Praveen Patil / Laya Gatus | 2014-03-03 | 2014-04-15 | Mireille Soeters | Closed | 2014-03-27
14/205 | Hazard Identification Plan - K45 | 14/AOR/042 | Karan 45 D6377 | MEP | N.A | The project fabrication HAZID study report was not reviewed on quarterly basis as required in the L2-HSES Admin Manual | Manjush Sidharthan | 2014-03-10 | 2014-03-27 | Cameron White | Closed | 2014-03-27
14/205 | Hazard Identification Plan - K45 | 14/AOR/043 | Karan 45 D6377 | MEP | N.A | Some of the key project personnel are not trained in the MOC process. It is critical that those who are in a position to recognize change understand the requirement of MOC procedure. | Manjush Sidharthan | 2014-03-10 | 2014-04-09 | Cameron White | Closed | 2014-04-08
14/206 | OPITO standard for Basic H2S Training | 14/AOR/044 | HSES Training | MEA | N/A | The training session doesn’t demonstrate how the alarm system activates. An alarm system is available in the training area but it is not in working condition. | Karthikeyan Murugesan | 2014-03-12 | 2014-03-18 | Shirlie Macatangay | Closed | 2014-03-18
14/206 | OPITO standard for Basic H2S Training | 14/AOR/045 | HSES Training | MEA | N/A | The knowledge test questionnaire does not mention about the pre-use checks of personal detection devices and EBA | Karthikeyan Murugesan | 2014-03-12 | 2014-03-27 | Shirlie Macatangay | Closed | 2014-03-19
13-14/207 | HSES Training Plan - MDR-ME-L3-MEA-007 | 14/AOR/046 | HSES Training | MEA | N/A | The formats used for training records have discrepancies with the templates as per MDR L3 procedure MDR-ME-L3-HSES -MEA -007 1. Closure Material History form 2. HSES Training Attendance Sheet of E.O.T Crane. 3.HSES Contract. 4.Subcontractor/Vendor Orientation Request form. | Sankar Ram Srinivasan | 2014-02-27 | 2014-04-30 | Shirlie Macatangay/Rosalle Dizon | Open Overdue |  | Extended until 30th of June - Procedure need to be revise
13-14/207 | HSES Training Plan - MDR-ME-L3-MEA-007 | 14/AOR/047 | HSES Training | MEA | N/A | The Present Short Service Employee Program (SSE) have discrepancies as per MDR L3 procedure MDR-ME-L3-HSES -MEA -007. 1. Documented on the Job training for inexperienced SSE’s. 2. HSE Refresher training after 90,180, and 270 days. | Sankar Ram Srinivasan | 2014-02-27 | 2014-04-30 | Shirlie Macatangay/Rosalle Dizon | Open Overdue |  | Extended until 30th of June - Procedure need to be revise
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | Safety policy was not posted anywhere in the office & workshop. | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-13 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue |  | Contract not granted
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | Organization chart HSE (Function / Role) was not captured in the organization chart nobody was assigned as HSE representative. | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-26 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | Employees training program is weak, Records of HSE induction & Tool box talk were not available. | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-10 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | SESSCO does not have trained or certified First aider. | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-20 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | Task Specific risk assessments are not available for the activities. | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-26 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | MSDS for all the chemicals were not available at shops; soft copies of two MSDS were available in the office. | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-16 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | HSE Objectives & Targets not established | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-26 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | Incidents investigation and reporting procedure not established. | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-26 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | Power tool inspected randomly found a pedestal grinder with an inadequate tool rest and the inspection record for this tool was not available. | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-22 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
14-VDR-008 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO), Sharjah ,UAE | 14-VDR-008 | Karan 45 D6377 | MEP | N.A | Evidence for emergency preparedness was not observed | Manjush Sidharthan/ Sudheendra Kumar | 2014-03-19 | 2014-04-22 | AL SHAHBA ENGINEERING SAFETY & SECURITY CO.LLC (SESSCO) | Open Overdue
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 1 | Chennai Office | MEA | N/A | HSES Policies are displayed at the reception area however these are posted at a location where visibility is restricted. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-15 | Arunprasad T | Closed overdue | 20.05.14
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 2 | Chennai Office | MEA | N/A | TRA for demolition / construction of partition walls, interior office works, false ceiling works was issued on 28th December 2012; no reviews are made to date to verify the validity of the TRA. Also, MDR/Chennai/TRA/01.Rev 3 was updated in November 21, 2013 however the TRA registry is not updated to reflect the same. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-17 | Arunprasad T | Closed overdue | 13.05.14
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 3 | Chennai Office | MEA | N/A | Environmental aspects and impacts assessment are identified and documented (MDR-ME-L3-HSES-MEF-037, Rev 3, issued in July 2012) though incorrect Level 2 procedure references is used. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-15 | Arunprasad T | Closed | 2014-04-15 | SENT TO KAMIL
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 4 | Chennai Office | MEA | N/A | Bus inspection was conducted in January for four subcontracted vehicles however these inspections were conducted by incompetent personnel (McDermott hired security personnel). | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed | 2014-04-01 | Please complete section 3 of the AOR and sign and send back to me
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 5 | Chennai Office | MEA | N/A | Environmental resources and waste monitoring registry not maintained, also waste transfer form is not utilized for waste effective tracking. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed | 2014-04-10 | UPLOADED IN THE FOLDER
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 6 | Chennai Office | MEA | N/A | Lift license for all the six lifts utilized by McDermott expires on 31st March 2014 however auditee was unable to provided follow-up evidence with the building management (CBRE) for license renewal. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed | 2014-04-10 | Requested from RMZ still waiting for copies of renewed license
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 7 | Chennai Office | MEA | N/A | Cable tray laid on the floor presenting a tripping hazard, uneven surface at the door opening in both the AHU (Air Handling Unit) rooms. Step ladder observed with damaged rung also no ladder inspection records available, damaged chairs stored without signs. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-15 | Arunprasad T | Closed | 2014-04-12 | Please complete section 3 of the AOR and sign and send back to me
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 8 | Chennai Office | MEA | N/A | Expired medicine (Savlon antiseptic) was observed in one of the First Aid box (FA-CHN-Z1-001) located at the rear side office exit | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-15 | Arunprasad T | Closed | 2014-04-12 | Please complete section 3 of the AOR and sign and send back to me
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 9 | Chennai Office | MEA | N/A | Footwear policy is not being fully implemented in the office, 3 out of 5 randomly selected personnel were not complying with the requirement. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-15 | Arunprasad T | Closed | 2014-04-14 | Please complete section 3 of the AOR and sign and send back to me
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 10 | Chennai Office | MEA | N/A | Emergency escape layouts posted across the office are not in accordance to the current Emergency Response Plan. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed, Overdue | 2014-04-12 | Please complete section 3 of the AOR and sign and send back to me
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 11 | Chennai Office | MEA | N/A | Emergency drill schedule is established though this plan does not reflect the type of drills to be conducted. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed | 2014-04-01 | Please complete section 3 of the AOR and sign and send back to me
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 12 | Chennai Office | MEA | N/A | HSES activity plan not maintained, some of the activities are marked completed though there is no evidence of activity completion | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed |  | TILL MAR 2014, SENT TO LAYA AND RECEIVED THE APPROVED COPY
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 13 | Chennai Office | MEA | N/A | Schedule of equipment maintenance for emergency equipment, generators, etc is available however the schedule is not reviewed and approved by the relevant Subject Matter Expert. | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed | 2014-04-01 | Please complete section 3 of the AOR and sign and send back to me
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 14 | Chennai Office | MEA | N/A | Some of the documents are not appropriately controlled. Organization charts, emergency response team list, vehicle inspection checklist services have no control numbers. Also obsolete versions of objectives and targets status and activity plans were posted on some bulletin boards | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed | 2014-04-10 | NOTICE BOARD SNAPS UPLOADED IN THE FOLDER
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | AOR 15 | Chennai Office | MEA | N/A | No evidence of HSES communications from external parties being logged | Praveen Patil / Laya Gatus | 2014-03-18 | 2014-04-10 | Arunprasad T | Closed | 2014-04-10 | CATR UPLOADED ON THE FOLDER
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | CAR 1 | Chennai Office | MEA | C2 | Subcontractor Balaji Interiors was utilized for repairing AC ducting of the IT server room. Subcontractor checklist was utilized and completed but upon verification it was identified that TRA does not exist for activity | Praveen Patil / Laya Gatus | 2014-03-31 | 2014-04-18 | Arunprasad T | closed | 2014-04-18
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | CAR 2 | Chennai Office | MEA | C1 | Objectives and targets identified for the Operations are not aligned with MEA 2014 O&Ts. Also, specific action plan for each objective is not established and maintained | Praveen Patil / Laya Gatus | 2014-03-31 | 2014-04-18 | Arunprasad T | Closed | 2014-04-18 | UPLOADED IN THE FOLDER
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | CAR 3 | Chennai Office | MEA | C1 | No centralized HSES training database is maintained for effective tracking of training records. Training plan is established however there is no evidence of training completed as scheduled e.g. Subcontractor training validity 6 months, blood borne pathogens and incident/emergency management training with validity 1 year respectively and 1 day incident investigation/RCA analysis training with validity 3 years and etc. | Praveen Patil / Laya Gatus | 2014-03-31 | 2014-04-18 | Arunprasad T | Closed | 2014-04-18 | Blood borne pathogens trg conducted and training schedule has been sent to Dubai HSES training
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | CAR 4 | Chennai Office | MEA | C2 | Compliance to MDR-ME-L3-HSES-MEA-001 Chemical Management Plan procedure not evident. Pre-purchase risk assessment and COSHH assessment not completed for all the chemicals used at the facility. Also, chemical inventory is not established and maintained. MSDS are available however these are downloaded from Chemwatch database and not obtained from the manufacturer. | Praveen Patil / Laya Gatus | 2014-03-31 | 2014-04-18 | Arunprasad T | Closed overdue | 13.05.14
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | CAR 5 | Chennai Office | MEA | C2 | Following subcontractors are classified as critical as per McDermott Level 2, Subcontractors HSES Requirements procedure however there was no evidence to show if these Subcontractors are prequalified and their HSEMS is evaluated prior to signing agreement. Siemens and Everlife Safety Systems Pvt Ltd. – used for emergency equipment maintenance Fiesta Car Travels – used personnel transportation Balaji Interiors – used for repair of AC ducting | Praveen Patil / Laya Gatus | 2014-03-31 | 2014-04-18 | Arunprasad T | Closed | 2014-04-18 | subcon audit with Siemens scheduled 11th April.
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | CAR 6 | Chennai Office | MEA | C2 | Procedure for evaluation of compliance with legal and other requirements – Chennai Engineering Services was last updated on 13 November 2013 with a non-compliance related to low Lux (Illumination) levels when compared to OSHA and UK HSG standard requirements. The actions related to this non compliance issue are not included in the CATR for effective monitoring of close out and to date approximately 80% of the work stations have not achieved the required Lux levels. | Praveen Patil / Laya Gatus | 2014-03-31 | 2014-04-18 | Arunprasad T | Closed | 2014-04-18 | LUX LEVELS INCREASED.READINGS UPLOADED IN THE FOLDER
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | CAR 7 | Chennai Office | MEA | C2 | Central Action Tracking Registry (CATR) is established however actions from inspections, drills, meetings etc are not included in the CATR and tracked until closure. | Praveen Patil / Laya Gatus | 2014-03-31 | 2014-04-18 | Arunprasad T | Closed | 2014-04-18 | CATR UPLOADED ON THE FOLDER
TBA CHN | OHSAS 18001:2007 & ISO 14001: 2004 | CAR 8 | Chennai Office | MEA | C2 | Previous IMS Review meeting was conducted in October 2013, KPI's including O&T's, Leading indicators, audits, inspections, CATR etc was not on the agenda for review. With reference to the 2014 HSES Activity Plan Quarterly management review meetings are scheduled in January, April, July and October however no meeting has be conducted to date. | Praveen Patil / Laya Gatus | 2014-03-31 | 2014-04-18 | Arunprasad T | Closed | 2014-04-18 | MOM UPLOADED IN THE FOLDER.
KSA14-AOR-032 | Emergency Response Plan | AOR 32 | KSA | MEA |  | Employee recently assigned as Muster Point Checker (MPC) and On-Scene Commander (OSC) have not received the Basic Fire Fighting and First Aid Training . | Vijai Thampi | 2014-05-22 | 2014-06-11 | Graham Valentine | Closed | 2014-06-11
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/050 | KSA | MEA |  | MSDS not available at site (fabrication shop) for compressed gas cylinders. | Mohammed Shadab | 2014-05-22 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/051 | KSA | MEA |  | First aiders at site are not readily identifiable. List of first aiders not displayed at site. | Mohammed Shadab | 2014-05-23 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/052 | KSA | MEA |  | Fire extinguishers at site are not inspected monthly as per AQPCI inspection program. Inspection stickers on few extinguishers found with old dates. | Mohammed Shadab | 2014-05-24 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/053 | KSA | MEA |  | Objectives and targets are not well developed. No O& T for proactive HSES advisors | Mohammed Shadab | 2014-05-25 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/054 | KSA | MEA |  | Compliance towards PPE at site and shops found to be poor. There was zero compliance towards safety goggles and respiratory protection equipment inside custom shop. | Mohammed Shadab | 2014-05-26 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/055 | KSA | MEA |  | No uniform color coding found on lifting gears. Some of the lifting gears found without any color code | Mohammed Shadab | 2014-05-27 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/056 | KSA | MEA |  | Reverse horn on forklifts at site found with very low audible sound. | Mohammed Shadab | 2014-05-28 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/057 | KSA | MEA |  | Confined space permit has section for gas reading however there is no Authorized Gas Tester available for monitoring gas reading. | Mohammed Shadab | 2014-05-29 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/058 | KSA | MEA |  | The lighting arrangement at petrol and diesel fuelling station found not to be working . | Mohammed Shadab | 2014-05-30 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/059 | KSA | MEA |  | No whip checks found on compressed air lines inside custom shop. | Mohammed Shadab | 2014-05-31 | TBA |  | Open
14-VDR-025 | AL QAHTANI PIPE COATING INDUSTRIES(AQPCI) | 14/VDR/AOR/060 | KSA | MEA |  | Legal register capturing legal and other requirement applicable in KSA is not available. | Mohammed Shadab | 2014-06-01 | TBA |  | Open
Note on N15: lgatus: CAR closeout documents has submitted to PP for his review & accepatance.Delay in document submission due to management approval and suggested changes which was done on 1/26/2014. Document submitted on 3/10/2014.
Note on N17: lgatus: CAR closeout documents has submitted to PP for his review & acceptance on 3/15/2014 after getting required supporting document from operation group.
Note on N20: LGatus: 18 March: accepted as closed by auditor, waiting for close out documents to be released by QAQC. CAR closeout documents has submitted to PP for his review & acceptance. Delay in document submission. Management review meeting done on 2/12/2014. MOM circulated.

## Traffic Violation (hidden)
CENTRAL ACTION REGISTRY - MEETINGS
Control / Reference Number | Class | Action Title / Description | Type of Incident | Project / Department | Client | Entity Name | Priority / Criticality | Description of Action | Originator / Responsible Person | Date Assigned | Date Target | Person Assigned | Status | Date Completed | Closed Out Justification | Comments
| Letter | Unsafe Driving Practise# 116269 Mohammad Hajri #. 8915599 | Speeding | SFNY PH-2 | Aramco | N/A | NA

## Meetings (hidden)
CENTRAL ACTION REGISTRY - MEETINGS
Control / Reference Number | Class | Action Title / Description | Type of Incident | Project / Department | Client | Entity Name | Priority / Criticality | Description of Action | Originator / Responsible Person | Date Assigned | Date Target | Person Assigned | Status | Date Completed | Closed Out Justification | Comments

## Safety Action Plan
Safety Action Plan Template
JEA Project / Department | JEA Contractor Sponsor | Project Location | Job Description | Equipment Used | Tools Used | Incident That Could Occur Without Mitigation | Risk Factor Prior to Mitigation (RAM Score) | Steps Needed to Complete the Task | Substitution and or Design Risk Reduction Actions | Engineering Risk Reduction Actions | Administrative Risk Reduction Actions | PPE risk Reduction Actions | JEA Review Person Assigned | Task Approval Status | Date Approved | Risk Level After Mitigation (RAM Score) | Comments
Contractor Name
Contractor Name

## Drop Downs (hidden)
class | Type of Incident | Project / Department | client | Entity Name | Priority | status
Incident | NM | D6221 | ARAMCO | MEF | P1 | Open
Meeting | PD | D6376 | KJO | MEA | P2 | Open Overdue
HAZID | FAC | D6553 | ADMA | MEM | P3 | Closed
Comm Cards | MTC | MDR | NA | MEFSC | P4 | Closed Overdue
Inspection | RWC | Facility |  | MEMSC | C1
Audit | LTI | Marine |  | MEPSC | C2
| Fatality | HSES Tng. |  | MEP | NA
Security
Spill
NM
NA

## HAZIDS (hidden)
CENTRAL ACTION REGISTRY - HAZIDS
Control / Reference Number | Class | Action Title / Description | Type of Incident | Project / Department | Client | Entity Name | Priority / Criticality | Description of Action | Originator / Responsible Person | Date Assigned | Date Target | Person Assigned | Status | Date Completed | Closed Out Justification | Comments
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Kick off meeting onboard the vessel to include all supervisors FM/LM to understand the SOW and associated hazards. Meeting to include Client. Sign off sheets to be signed by all parties. • MOM to be generate during Kick-off meeting onboard MWB & all spread vessels • Related TRAs to be reviewed and/or developed. • Roles and responsibilities to be identify for all vessel • Roll out authority to stop the work with HU spread. • Familiarize with whale shark TRA/ Method statements/ SWP etc. • Safe tow route to be discuss with master • PTW hard copy to be obtained prior to start the work | HAZID Team | 2014-12-07 | 2014-12-30 | Lead HU engineer/HU Supdt. | Closed | 2014-12-31 | Kick of meeting conducted including all supervisors and client.MOM of kick of meeting generated. Related TRA reviewed/developed and signed by all concern. Authority to STOP work addressed during meeting and regularly during TBT. Process in place to obtain 7 days HOT and Cold work permit in place | PTW form ARAMCO for14 days is available and action in hand for new permit.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Valid visa to be verified prior to mobilization. | HAZID Team | 2014-12-07 | 2014-12-30 | Lead HU Engrs/ HU Admin | Closed | 2014-12-31 | HU Supdt and Admin agreed and process is monitored continuously and is considered complete
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Use direct contact (as required) with McDermott Radio Room to re-confirm weather forecasts / get closer look ahead. • Ensure Vessel Master has access to Weather Reports by Radio Room. | HAZID Team | 2014-12-07 | 2014-12-30 | Lead HU Engrs / HU Supdt (In consultation with Vessel Master) | Closed | 2014-12-31 | Radio room sent weather report to Vessel Masters including spread vessels. HU Team considers action complete | HU Supdt and HSE included in Wx report from radio room and if necessary vessel master and Supdt contacts radio room.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Deck layout to be followed as per approved drawings. • Secure materials by lashing prior to mobilization and then sea fasten when outside the port limits. • Carry out sea fastening with appropriate vessel PTW requirements for hot work activities. • Minimum lashing to be done on loaded material, prior to mobilize from any location. | HAZID Team | 2014-12-07 | 2014-12-30 |  | Closed | 2014-12-31 | Agreed by HU team Deck foreman will ensure for lashing Material loading and lashing will be done in consultation with Captain and Rig Move Master(RMM) | Monitored by HU supdt and RMM
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Acquire approval & work permit from Field Services before approaching (500m zone). • Verify access from boat to boat landing and to work location prior to personnel transfer. • Ensure rubber fenders are in place (boat landing/vessel). If damaged / missing report it to Field Services prior to setting up. • Ensure gangway & Sausage / Floating fenders are install on both side of the vessel • Selection of vessels to suit existing platform condition for approach and staying alongside • Sufficient soft mooring ropes to be in place • Certified winches and cables for the gang way rigging equipments. • Mobilize survey equipments on all vessels. • Only approved Transit route will be used (RMM approved) • Ensure latest survey information /drawing available on vessels.(special attention to be given on the UMB & power cable laid newly) • Avoid to tying a vessel to existing platform bollards or boat landing. | HAZID Team | 2014-12-07 | 2014-12-31 | Lead HU Engrs Vessel Master / HU SUpdt | Closed | 2014-12-31 | RMM will get the permit to move the barge to different locations and will plan the transit route. For vessels to approach along side RMM decides as per the site conditions. Survey equipments is available on all vessels and pre survey will be carried out before barge moves to particular location. RMM will advices regarding tying up of vessels to existing platforms or wait at Anchorage point.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Communication among vessels • Regular communication and coordination infield movement. | HAZID Team | 2014-12-07 | 2014-12-31 | HU Supdt. | Closed | 2014-12-31 | WhaleShark MDR office will have radio set and will do infield coordination. | RMM and Whaleshark updates daily in client meeting about vessel status and positions.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Specific TRAs to be developed for Personnel Transfer • Verify all offshore personnel have valid PBSR training. • Adequate number of certified Billy Pugh onboard. • Use certified gang way. | HAZID Team | 2014-12-07 | 2014-12-31 | HU Supdt. / Barge foreman. | Closed | 2015-01-01 | HU team reviewed the actions and considers complete | TRA developed and communicated to work force. 03 billy pugh on board(2 rigid)
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Well barriers installed and tested and to be confirmed with the field serves. • Portable gas detection • Information from other offshore facilities. • Gas check to be done on the platform prior to personnel transfer on platforms. • Established schedule drills • PTW, TBT’s. | HAZID Team | 2014-12-07 | 2014-12-31 | Onboard Safety/ HU Supdt. | Closed | 2015-01-01 | Daily gas test is done by onboard HSE Advisors. Drills carried out as per client/Captain advice . Client agreed to assist in obtaining 7 days PTW. Daily TBT for both shifts are conducted | Daily TBT is taken by HU Supdt and HSE Advisor
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Gangway that will be used is to be checked for suitability. • Ensure work vest is worn • Gangway to be reset/ repositioned as necessary to account for tides and weather • Use certified gang way. | HAZID Team | 2014-12-07 | 2014-12-31 | Deck Foreman/ HU Supdt | Closed |  | Gangway checked and found suitable. Wearing of work vest is mandatory and advised in TBT, | Signage's posted for wearing of work vest and gangway watch is maintained during adverse weather conditions.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Ensure Aramco approved scaffold supervisor onboard. • Specific TRA to be developed | HAZID Team | 2014-12-07 | 2014-12-31 | HU Supdt. /Scaffolding L/M | Closed | 2015-01-01 | TRA relating to each activity is developed and signed. Aramco approved scaffold supervisor is on board. | TRA communicated to work force.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • No lift taking place above 20 knots | HAZID Team | 2014-12-07 | 2014-12-31 | Deck Foremen / HU Supdt. | Closed | 2014-12-31 | HU Supdt and Master agreed no lifting will take place when wind speed above 20 knots
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Source storage location on the barge shall be identified and approved. • Adequate barriers provided, storage areas locked and access controlled. • Barge layout to be identified prior to mob of source. • Layout must be approved by Aramco • Tech will be hired (Subcon) to check compliance of the source handling and transportation • PTW • Plan activity during periods of low activity where possible. • PA announcement • Barriers / Signs / amber lights | HAZID Team | 2014-12-07 | 2015-01-15 | NDT/RPS Supv HU Supt QC Supv | Closed | 2015-01-23 | Aramco Pit Approval obtained All other control measures reviewed by HU team and considers complete
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Competent personnel • Strict compliance with PTW / LOTO • TRA • Signs / Barriers / Identified Exclusion Zones. • Risk of impact to be discussed in TBT and made awareness. | HAZID Team | 2014-12-07 | 2015-01-20 | HU Engrs/ HU Supdt. | Closed |  | Control measures reviewed by project personnel and considered complete
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • PTW • Signs / Barriers • Function test prior to mob offshore. • Lessons learnt from Previous incidents (MEF-14002-D6376-RWC- Hydraulic torquing thumb injury) • Awareness of pinch point to be discussed in TBT | HAZID Team | 2014-12-07 | 2015-01-20 | HU Engrs/ HU Supdt | Closed |  | Control measures reviewed by project personnel and considered complete
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Correct Manual Handling techniques • Kevlar gloves when working with cable trays • Subcontract tools and equipments to be inspected to ensure compliance with MDR procedure • Relevant TRA | HAZID Team | 2014-12-07 | 2015-01-20 | HU Supt / E & I Engr | Closed | 2015-01-12 | TRA & TBT relating to activity communicated to involved employees Certified tools and equipments are on site
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Specific TRA to be developed at each location. • Cable manufacturer presence and supervision • Subcon presence for cable glanding • LOTO to be verified | HAZID Team | 2014-12-07 | 2015-01-20 | HU Supt Comm Mgr | Open |  |  | Not applicable for 342/347 will be reviewed before commencing pre commissioning activity
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Proper P.P.E to be in place considering existing platform with possible lead paints. • Develop specific TRA including COSHH assessment. | HAZID Team | 2014-12-07 | 2014-12-31 | Painting L/M/HU Engrs | Closed | 2015-01-01 | TRA with COSHH assessment in place. | signage's posted for wearing of workvest and gangway watch is maintained during adverse weather conditions.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Controlled Access to Control Room • Specified PPE • Correct Connection • Preventive Maintenance / Inspection of electrical system / equipment • Proper Earthing / Grounding of equipment • Insulated hook / rated gloves in place. • Suitable barriers and signs on affected area of commissioning. Follow the project specific procedures. Refer project specific activity related TRA for identified risk and necessary control measures. • First Aider electricians • Rubber matting | HAZID Team | 2014-12-07 | 2015-01-20 | Comm Mgr/ HU Supt// Lead Commissioning Engineers. | Closed | 2015-02-16 | Pre commissioning team reviewed the control measures onboard. TRA in place.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Competent personnel • PTW System • LOTO System • Controlled Access • Specified PPE | HAZID Team | 2014-12-07 | 2015-01-20 | Comm Mgr./ HU Supt// Lead Commissioning Engineers. | Closed | 2015-01-12 | HU team reviewed the control measures and considered complete
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Check the compatibility of the fittings • SOPEP/Spill kits • PPE • Check rating hoses and fittings • MSDS • Method Statement for First Fills. • IMDG ISO tanks • Emergency Response Plan • Drip trays | HAZID Team | 2014-12-07 | 2015-01-20 | Comm Mgr./ HU Supt// Lead Commissioning Engineers. | Closed | 2015-02-16 | Pre commissioning team reviewed the control measures onboard. Oil spill kit and Drip tray in place. MSDS of oil available.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Manning level shall have adequate competent supervision and skilled crew for commissioning activities. | HAZID Team | 2014-12-07 |  | Comm Mgr./ HU Supt// Lead Commissioning Engineers. | Closed | 2015-02-16 | Precommissioning Engineers and skilled crew onboard.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Correct Manual Handling techniques • Kevlar gloves when working with cable trays • Subcontract tools and equipments to be inspected to ensure compliance with MDR procedure • Relevant TRA | HAZID Team | 2014-12-07 | 2015-01-20 | HUP Sup./ E & I Engr. | Closed | 2015-01-12 | E&I Team reviewed the action onboard and TRA in place.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • Approved TRA for Systems • PTW System • LOTO system • Preventive Maintenance. • Pre-Checks prior to Energization. • Proper Earthing / Grounding of equipment • Competent Personnel. • Suitable barriers and signs on affected area of commissioning. • Proper PPE. | HAZID Team | 2014-12-07 | 2015-01-20 | Comm. Mgr/ Lead Commissioning Engrs. HU Supt | Closed | 2015-02-16 | Pre commissioning team reviewed the action onboard. PTW (MDR & ARAMCO) in place. MDR LOTO Procedure followed.
D6376/D6553-AOC-PAT-126 | HAZID | WhaleShark Hook-up HAZID | NA | D6553 | ARAMCO | MEP | C1 | • TBT on proper waste disposal • Skips to be color coded • Left over chemicals to be delivered to Tanajib • LL to be discussed in TBT (to be provided by HSE) | HAZID Team | 2014-12-07 | 2014-12-31 | Deck Foreman | Closed | 2015-01-01 | HU team reviewed the actions and considers complete