## Estimate Reconciliation (hidden)
30% Cost Estimate |  |  | 30% vs PD | Reasons for Significant Differences Between 30% and PD Estimates | 60% Cost Estimate |  |  | 60% vs 30% | Reasons for Significant Differences Between 60% and 30% Estimates | 90% Cost Estimate |  |  | 90% vs 60% | Reasons for Significant Differences Between 90% and 60% Estimates | 100% Cost Estimate |  |  | 100% vs 90% | Reasons for Significant Differences Between 100% and 90% Estimates | Final Cost Estimate |  |  | Final vs 100% | Reasons for Significant Differences Between Final and 100% Estimates
Class 3 w/ Expected Accuracy -20% to +30% |  |  |  |  | Class 2 w/ Expected Accuracy -15% to +20% |  |  |  |  | Class 1 w/ Expected Accuracy -10% to +15% |  |  |  |  | Class 1 w/ Expected Accuracy -10% to +15% |  |  |  |  | Class 1 w/ Expected Accuracy -10% to +15%
Direct Construction Costs |  |  |  |  | Direct Construction Costs |  |  |  |  | Direct Construction Costs |  |  |  |  | Direct Construction Costs |  |  |  |  | Direct Construction Costs
[8 empty] | 0 |  | FORCE MAIN |  |  |  |  | FORCE MAIN |  |  |  |  | FORCE MAIN
[15 empty] | Abandon MH in place |  | 1000 | 1000 | Added | Abandon Manhole in place |  | 800 | -200 | Updated unit cost; Remove Division 1
[8 empty] | 0 | [11 empty] | Abandon 4" Pipe- Sealing |  | 1500 | 1500 | Added to final drawings
[10 empty] | Abandon 16" DI Pipe - Grout Filling |  | 68500 |  |  | Abandon 16" DI Pipe - Grout Filling |  | 68500 | 0 |  | Abandon 16" DI Pipe - Grout Filling |  | 41100 | -27400 | Updated unit cost; Remove Division 1
[10 empty] | Remove 10" PVC Pipe, below grade |  | 437.5 |  |  | Remove 10" PVC Pipe, below grade |  | 287.5 | -150 | Quantity Updated | Remove 10" PVC Pipe, below grade |  | 805 | 517.5 | Updated unit cost
[10 empty] | Remove 16" DI Pipe, below grade |  | 28890 |  |  | Remove 16" DI Pipe, below grade |  | 26532 | -2358 | Quantity Updated | Remove 16" DI Pipe, below grade |  | 29480 | 2948 | Updated unit cost
[10 empty] | Remove 16" PVC, below grade |  | 420 |  |  | Remove 16" PVC, below grade |  | 420 | 0 |  | Remove 16" PVC, below grade |  | 560 | 140 | Updated unit cost
[10 empty] | Remove 2" Galvanized Pipe, below grade |  | 130 |  |  | Remove 2" Galvanized Pipe, below grade |  | 100 | -30 | Quantity Updated | Remove 2" Galvanized Pipe, below grade |  | 400 | 300 | Updated unit cost
[10 empty] | Remove 4" PVC DR 18 Pipe, below grade |  | 660 |  |  | Remove 4" PVC DR 18 Pipe, below grade |  | 660 | 0 |  | Remove 4" PVC DR 18 Pipe, below grade |  | 960 | 300 | Reduced quantity on final drawings; updated unit cost
[10 empty] | Remove 6" PVC Pipe, below grade |  | 770 |  |  | Remove 6" PVC Pipe, below grade |  | 1070 | 300 | Quantity Updated | Remove 6" PVC Pipe, below grade |  | 3477.5 | 2407.5 | Updated unit cost
[15 empty] | Remove 8" PVC Pipe, below grade |  | 299 | 299 | Added | Remove 8" PVC Pipe, below grade |  | 910 | 611 | Updated unit cost
[10 empty] | Flowable Fill |  | 10000 |  |  | Flowable Fill |  | 10138 | 138 | Quantity Updated | Flowable Fill |  | 10138 | 0 | No change
[10 empty] | Pavement Removal (COJ) |  | 35274 |  |  | Pavement Removal (COJ) |  | 35274 | 0 |  | Pavement Removal (COJ) |  | 35274 | 0 | No change
[10 empty] | Pavement Removal (FDOT) |  | 850 |  |  | Pavement Removal (FDOT) |  | 850 | 0 |  | Pavement Removal (FDOT) |  | 850 | 0 | No change
[10 empty] | Paving Repair - Cross Cuts and Patches - Asphalt (COJ Case X) |  | 470325.2 |  |  | Paving Repair - Cross Cuts and Patches - Asphalt (COJ Case X) |  | 472326 | 2000.8 | Quantity Updated | Paving Repair - Cross Cuts and Patches - Asphalt (COJ Case X) |  | 472326 | 0 | No change
[10 empty] | Paving Repair - Cross Cuts and Patches - Asphalt (FDOT) |  | 10183.8 |  |  | Paving Repair - Cross Cuts and Patches - Asphalt (FDOT) |  | 6922.8 | -3261 | Quantity Updated | Paving Repair - Cross Cuts and Patches - Asphalt (FDOT) |  | 6922.8 | 0 | No change
[10 empty] | Paving Repair - Cross Cuts and Patches - Base (COJ Case X) |  | 154308.75 |  |  | Paving Repair - Cross Cuts and Patches - Base (COJ Case X) |  | 155103.6 | 794.85 | Quantity Updated | Paving Repair - Cross Cuts and Patches - Base (COJ Case X) |  | 155103.6 | 0 | No change
[10 empty] | Paving Repair - Cross Cuts and Patches - Base (FDOT) |  | 3774 |  |  | Paving Repair - Cross Cuts and Patches - Base (FDOT) |  | 2527.25 | -1246.75 | Quantity Updated | Paving Repair - Cross Cuts and Patches - Base (FDOT) |  | 2527.25 | 0 | No change
[15 empty] | Existing Pavement - Milling & Resurfacing (COJ Wiley Park) |  | 9622.305 | 9622.305 | Added | Existing Pavement - Milling & Resurfacing (COJ Wiley Park) |  | 21382.9 | 11760.595 | Updated unit cost
[10 empty] | Existing Pavement - Milling & Resurfacing (COJ) |  | 169827.39 |  |  | Existing Pavement - Milling & Resurfacing (COJ) |  | 159369.75 | -10457.64 | Quantity Updated | Existing Pavement - Milling & Resurfacing (COJ) |  | 357000 | 197630.25 | Updated unit cost
[10 empty] | Existing Pavement - Milling & Resurfacing (FDOT) |  | 12957.5 |  |  | Existing Pavement - Milling & Resurfacing (FDOT) |  | 9574.8 | -3382.7 | Quantity Updated | Existing Pavement - Milling & Resurfacing (FDOT) |  | 11968.5 | 2393.7 | Updated unit cost
[10 empty] | Grassing |  | 4672.5 |  |  | Grassing/Sodding |  | 4545 | -127.5 | Quantity Updated | Grassing |  | 4560 | 15 | Quantity increased on final drawings
[10 empty] | Remove Concrete Sidewalk (COJ) |  | 439 |  |  | Remove Concrete Sidewalk (COJ) |  | 1788.5 | 1349.5 | Quantity Updated | Remove Concrete Sidewalk (COJ) |  | 2200 | 411.5 | Quantity increased on final drawings
[10 empty] | Remove Concrete Sidewalk (FDOT) |  | 3842 |  |  | Remove Concrete Sidewalk (FDOT) |  | 1843 | -1999 | Quantity Updated | Remove Concrete Sidewalk (FDOT) |  | 1843 | 0 | No change
[10 empty] | Remove Concrete Driveway (COJ) |  | 18257.25 |  |  | Remove Concrete Driveway (COJ) |  | 20975.9 | 2718.65 | Quantity Updated | Remove Concrete Driveway (COJ) |  | 18205 | -2770.9 | Quantity decreased on final drawings
[20 empty] | Remove Asphalt Driveway (COJ) |  | 2080 | 2080 | Added to final drawings
[10 empty] | Remove Curb and Gutter (COJ) |  | 4097.52 |  |  | Remove Curb and Gutter (COJ) |  | 4314.975 | 217.455 | Quantity Updated | Remove Curb and Gutter (COJ) |  | 32538.25 | 28223.275 | Quantity increased on final drawings
[10 empty] | Remove Curb and Gutter (FDOT) |  | 653.31 |  |  | Remove Curb and Gutter (FDOT) |  | 225.33 | -427.98 | Quantity Updated | Remove Curb and Gutter (FDOT) |  | 536.5 | 311.17 | Updated unit cost
[10 empty] | Replace Concrete Sidewalk (COJ) |  | 878 |  |  | Replace Concrete Sidewalk (COJ) |  | 3578 | 2700 | Quantity Updated | Replace Concrete Sidewalk (COJ) |  | 4400 | 822 | Quantity increased on final drawings
[10 empty] | Replace Concrete Sidewalk (FDOT) |  | 7684 |  |  | Replace Concrete Sidewalk (FDOT) |  | 3686 | -3998 | Quantity Updated | Replace Concrete Sidewalk (FDOT) |  | 3686 | 0 | No change
[10 empty] | Replace Concrete Driveway (COJ) |  | 41493.75 |  |  | Replace Concrete Driveway (COJ) |  | 47625 | 6131.25 | Quantity Updated | Replace Concrete Driveway (COJ) |  | 41375 | -6250 | Quantity decreased on final drawings
[20 empty] | Replace Asphalt Driveway (COJ) |  | 5200 | 5200 | Added to final drawings
[10 empty] | Replace Curb and Gutter (COJ) |  | 9756 |  |  | Replace Curb and Gutter (COJ) |  | 10263.5 | 507.5 | Quantity Updated | Replace Curb and Gutter (COJ) |  | 32538.25 | 22274.75 | Quantity increased on final drawings
[10 empty] | Replace Curb and Gutter (FDOT) |  | 1555.5 |  |  | Replace Curb and Gutter (FDOT) |  | 536.5 | -1019 | Quantity Updated | Replace Curb and Gutter (FDOT) |  | 536.5 | 0 | No change
[10 empty] | 10" PVC DR 18 Pipe |  | 2152.5 |  |  | 10" PVC DR 18 Pipe |  | 1414.5 | -738 | Quantity Updated | 10" PVC DR 18 Pipe |  | 1414.5 | 0 | No change
[10 empty] | 8" PVC DR 25 Pipe |  | 250 |  |  | 8" PVC DR 25 Pipe |  | 250 | 0 |  |  |  |  | -250 | Removed from final drawings
[10 empty] | 6" PVC DR 18 Pipe |  | 8170 |  |  | 6" PVC DR 18 Pipe |  | 8360 | 190 | Quantity Updated | 6" PVC DR 18 Pipe |  | 9607.5 | 1247.5 | Quantity increased on final drawings; Updated unit cost
[10 empty] | 4" PVC DR 18 Pipe |  | 150 |  |  | 4" PVC DR 18 Pipe |  | 1320 | 1170 | Quantity Updated | 4" PVC DR 18 Pipe |  | 1320 | 0 | No change
[10 empty] | 2" PVC DR 18 Pipe |  | 520 |  |  | 2" PVC DR 18 Pipe |  | 210 | -310 | Quantity Updated and Revised Unit Cost |  |  |  | -210 | Removed from final drawings
[20 empty] | 2" PVC Schedule 80 Pipe |  | 150 | 150 | Added to final drawings
[10 empty] | 10" MJ 45° Bend |  | 1400 |  |  | 10" MJ 45° Bend |  | 1400 | 0 |  | 10" MJ 45° Bend |  | 1400 | 0 | No change
[10 empty] | 6" MJ 45° Bend |  | 1800 |  |  | 6" MJ 45° Bend |  | 2550 | 750 | Quantity Updated | 6" MJ 45° Bend |  | 2550 | 0 | No change
[15 empty] | 6" MJ 90° Bend |  | 200 | 200 | Added | 6" MJ 90° Bend |  | 200 | 0 | No change
[15 empty] | 6" MJ Tee |  | 500 | 500 | Added | 6" x 6" MJ Tee |  | 500 | 0 | No change
[20 empty] | 6" MJ Plug |  | 2250 | 2250 | Added to final drawings
[10 empty] | 6" Plug W/2" Tap |  | 2250 |  |  | 6" Plug W/2" Tap |  | 2250 | 0 |  | 6" Plug with 2" Tap |  | 800 | -1450 | Quantity decreased on final drawings; Updated unit cost
[10 empty] | 6"x4" MJ Tee |  | 1300 |  |  | 6"x4" MJ Tee |  | 800 | -500 | Revised Unit Cost | 6"x4" MJ Tee |  | 400 | -400 | Quantity decreased on final drawings
[15 empty] | 4" MJ 45° Bend |  | 1500 | 1500 | Added | 4" MJ 45° Bend |  | 1000 | -500 | Quantity decreased on final drawings
[10 empty] | 4" MJ 90° Bend |  | 3800 |  |  | 4" MJ 90° Bend |  | 500 | -3300 | Quantity Updated | 4" MJ 90° Bend |  | 250 | -250 | Quantity decreased on final drawings
[15 empty] | Sample Tap |  | 4550 | 4550 | Added | Compliance Sample Taps (W-27) |  | 8000 | 3450 | Quantity increased per JEA
[18 empty] | 0 |  | Temporary Sample Taps (W-25) |  | 1950 | 1950 | Added per JEA
[10 empty] | 6" Gate Valve |  | 4600 |  |  | 6" Gate Valve |  | 2300 | -2300 | Quantity Updated | 6" MJ Gate Valve |  | 3450 | 1150 | Quantity increased on final drawings
[10 empty] | 4" MJ Gate Valve |  | 1080 |  |  | 4" MJ Gate Valve |  | 1080 | 0 |  | 4" MJ Gate Valve |  | 540 | -540 | Quantity decreased on final drawings
[10 empty] | 10" Full Circle Sleeve |  | 650 |  |  | 10" Full Circle Sleeve |  | 650 | 0 |  | 10" Sleeve |  | 650 | 0 | No change
[10 empty] | 8" MJ Sleeve |  | 1350 |  |  | 8" MJ Sleeve |  | 12150 | 10800 | Quantity Updated |  |  |  | -12150 | Removed from final drawings
[10 empty] | 6" Full Circle Sleeve |  | 1500 |  |  | 6" Full Circle Sleeve |  | 2000 | 500 | Quantity Updated |  |  |  | -2000 | Removed from final drawings
[15 empty] | 6" MJ Sleeve |  | 1100 | 1100 | Added | 6" Sleeve |  | 1100 | 0 | No change
[10 empty] | 4" MJ Sleeve |  | 1600 |  |  | 4" MJ Sleeve |  | 3200 | 1600 | Quantity Updated | 4" Sleeve |  | 300 | -2900 | Quantity decreased on final drawings; Updated unit cost
[10 empty] | 2" MJ 45° Bend |  | 360 | [5 empty] | -360 | 2" fittings not paid for separately
[10 empty] | 2" Full Circle Sleeve |  | 350 |  |  | 2" Full Circle Sleeve |  | 350 | 0 |  |  |  |  | -350 | 2" fittings not paid for separately
[10 empty] | 2" Corporation Stop |  | 370 |  |  | 2" Corporation Stop |  | 370 | 0 |  |  |  |  | -370 | 2" fittings not paid for separately
[10 empty] | 2" Service Saddle |  | 650 |  |  | 2" Service Saddle |  | 650 | 0 |  |  |  |  | -650 | Removed from final drawings
[15 empty] | Furnish and Install Type A MH |  | 9800 | 9800 | Added | Furnish and Install Type A Manhole |  | 9800 | 0 | No change
[15 empty] | Remove Existing MH |  | 1000 | 1000 | Added | Remove Existing Manhole |  | 1000 | 0 | No change
[10 empty] | Wastewater Lateral Piping - Remove and Replace, 8" |  | 6000 |  |  | Wastewater Lateral Piping - Remove and Replace, 8" |  | 12000 | 6000 | Quantity Updated | Wastewater Piping - Remove and Replace, 8" |  | 15000 | 3000 | Quantity increased on final drawings
[10 empty] | Wastewater Lateral Piping - Remove and Replace, 6" |  | 2400 |  |  | Wastewater Lateral Piping - Remove and Replace, 6" |  | 5000 | 4000 | Quantity Updated |  |  |  | -5000 | See line item for Wastewater Piping- Remove and Replace 4"-6" below
[10 empty] | Wastewater Lateral Piping - Remove and Replace, 4" |  | 1000 |  |  | Wastewater Lateral Piping - Remove and Replace, 4" |  | 2000 | -400 | Quantity Updated |  |  |  | -2000 | See line item for Wastewater Piping- Remove and Replace 4"-6" below
[10 empty] | 16" PVC DR 25 Pipe |  | 12880 |  |  | 16" PVC DR 25 Pipe |  | 12160 | -720 | Quantity Updated | 16" PVC DR 25 Pipe |  | 24320 | 12160 | Updated unit cost
[10 empty] | 24" PVC DR 25 Pipe |  | 2085075 |  |  | 24" PVC DR 25 Pipe |  | 2085075 | 0 |  | 24" PVC DR 25 Pipe |  | 2316750 | 231675 | Include MOT, tree protection, erosion control, landscape restoration, remove Division 1
[10 empty] | 30" PVC DR 25 Pipe |  | 9150 |  |  | 30" PVC DR 25 Pipe |  | 9150 | 0 |  | 30" PVC DR 25 Pipe |  | 9150 | 0 | No change
[10 empty] | 16" MJ 45° Bend |  | 24750 |  |  | 16" MJ 45° Bend |  | 8250 | -16500 | Quantity Updated | 16" MJ 45° Bend |  | 8250 | 0 | No change
[10 empty] | 16" MJ 90° Bend |  | 8400 |  |  | 16" MJ 90° Bend |  | 8400 | 0 |  | 16" MJ 90° Bend |  | 8400 | 0 | No change
[10 empty] | 16" MJ Cap |  | 16000 |  |  | 16" MJ Cap |  | 14000 | -2000 | Quantity Updated | 16" MJ Cap |  | 12000 | -2000 | Quantity decreased on final drawings
[10 empty] | 16"x16" MJ Tee |  | 4550 |  |  | 16"x16" MJ Tee |  | 4550 | 0 |  | 16"x16" MJ Tee |  | 4550 | 0 | No change
[10 empty] | 24" MJ 11.25° Bend |  | 43200 |  |  | 24" MJ 11.25° Bend |  | 40500 | -2700 | Quantity Updated | 24" MJ 11.25° Bend |  | 40500 | 0 | No change
[10 empty] | 24" MJ 22.5° Bend |  | 42000 |  |  | 24" MJ 22.5° Bend |  | 42000 | 0 |  | 24" MJ 22.5° Bend |  | 42000 | 0 | No change
[10 empty] | 24" MJ 45° Bend |  | 148200 |  |  | 24" MJ 45° Bend |  | 153900 | 5700 | Quantity Updated | 24" MJ 45° Bend |  | 153900 | 0 | No change
[10 empty] | 24" MJ 90° Bend |  | 3100 | [5 empty] | -3100 | Removed
[10 empty] | 24" MJxFLG 45° Bend |  | 3100 |  |  | 24" MJxFLG 45° Bend |  | 6200 | 3100 | Quantity Updated | 24" MJxFLG 45° Bend |  | 6200 | 0 | No change
[10 empty] | 24" MJxFLG 90° Bend |  | 3500 | [5 empty] | -3500 | Removed
[10 empty] | 24" x 16" MJ Tee |  | 5650 |  |  | 24" x 16" MJ Tee |  | 5650 | 0 |  | 24" x 16" MJ Tee |  | 5650 | 0 | No change
[10 empty] | 24"x16" MJ Tee |  | 5700 | [5 empty] | -5700 | Removed
[10 empty] | 24"x30" Reducer |  | 6050 |  |  | 24"x30" Reducer |  | 6050 | 0 |  | 24"x30" MJ Reducer |  | 6050 | 0 | No change
[10 empty] | 30" MJ Cap |  | 5600 |  |  | 30" MJ Cap |  | 5600 | 0 |  | 30" MJ Cap |  | 5600 | 0 | No change
[10 empty] | 30"x16" MJ Tee |  | 21000 |  |  | 30"x16" MJ Tee |  | 21000 | 0 |  | 30"x16" MJ Tee |  | 21000 | 0 | No change
[18 empty] | 0 |  | 4" MJ 45° Bend |  | 500 | 500 | Added to final drawings
[18 empty] | 0 |  | 4" MJ 90° Bend |  | 250 | 250 | Added to final drawings
[10 empty] | 4" HDPE MJ adapter |  | 500 |  |  | 4" HDPE MJ adapter |  | 500 | 0 |  | 4" HDPE MJ adapter |  | 500 | 0 | No change
[10 empty] | 4" Solid Sleeve with HDPE adapter |  | 750 |  |  | 4" Solid Sleeve with HDPE adapter |  | 750 | 0 |  | 4" Solid Sleeve and HDPE adapter |  | 750 | 0 | No change
[10 empty] | 16" Restrained Joint |  | 4500 |  |  | 16" Restrained Joint |  | 4500 | 0 |  | 16" Restrained Joint |  | 4500 | 0 | No change
[10 empty] | 24" Restrained joint |  | 201500 |  |  | 24" Restrained joint |  | 201500 | 0 |  | 24" Restrained joint |  | 201500 | 0 | No change
[10 empty] | 30" Restrained Joint |  | 1300 |  |  | 30" Restrained Joint |  | 1300 | 0 |  | 30" Restrained Joint |  | 1300 | 0 | No change
[10 empty] | 16" MJ Gate Valve |  | 16400 |  |  | 16" MJ Gate Valve |  | 16400 | 0 |  | 16" MJ Gate Valve |  | 28000 | 11600 | Updated unit cost
[10 empty] | 24" MJ Gate Valve |  | 132000 |  |  | 24" MJ Gate Valve |  | 115500 | -16500 |  | 24" MJ Gate Valve |  | 140000 | 24500 | Updated unit cost
[10 empty] | 30" MJ Gate Valve |  | 35500 |  |  | 30" MJ Gate Valve |  | 35500 | 0 |  | 30" MJ Gate Valve |  | 35500 | 0 | No change
[10 empty] | 24" x 16" Tapping Sleeve & Valve |  | 22500 |  |  | 24" x 16" Tapping Sleeve & Valve |  | 22500 | 0 |  | 24" x 16" Tapping Sleeve & Valve (Type 316 Stainless Steel) |  | 22500 | 0 | No change
[10 empty] | 16" Solid Sleeve |  | 5250 |  |  | 16" Solid Sleeve |  | 7000 | 1750 | Quantity Updated | 16" MJ Sleeve |  | 7000 | 0 | No change
[10 empty] | 24" MJ Sleeve |  | 5000 |  |  | 24" MJ Sleeve |  | 5000 | 0 |  | 24" MJ Sleeve |  | 5000 | 0 | No change
[10 empty] | 24" 316L SST Pipe |  | 56840 |  |  | 24" 316L SST Pipe |  | 55125 | -1715 | Quantity Updated and Revised Unit Cost |  |  |  | -55125 | Included in Mt. Vernon Aerial Force Main Crossing line items above
[10 empty] | 24" 316L SST FLG 45° Bend |  | 4200 |  |  | 24" 316L SST FLG 45° Bend |  | 15000 | 10800 | Revised Unit Cost |  |  |  | -15000 | Included in Mt. Vernon Aerial Force Main Crossing line items above
[10 empty] | 24" Dielectric Gaskets |  | 1000 |  |  | 24" Dielectric Gaskets |  | 1000 | 0 |  |  |  |  | -1000 | Included in Mt. Vernon Aerial Force Main Crossing line items above
[10 empty] | 16" Tapping Sleeve and Valve |  | 20000 | [5 empty] | -20000 | Removed
[10 empty] | SST ARV, above grade |  | 4500 |  |  | SST ARV, above grade |  | 4500 | 0 |  |  |  |  | -4500 | Included in Mt. Vernon Aerial Force Main Crossing line items above
[10 empty] | 16" DIP FM Grout Filled Annular Space |  | 7150 |  |  | 16" DIP FM Grout Filled Annular Space |  | 7150 | 0 |  |  |  |  | -7150 | Included in Mt. Vernon Aerial Force Main Crossing line items above
[20 empty] | Furnish and Install 16" Gate Valve in Existing Pipeline (Lane/Wilson) |  | 13500 | 13500 | Added to final drawings; include MOT; Remove Division 1
[10 empty] | ARV |  | 66000 |  |  | ARV |  | 72600 | 6600 | Quantity Updated | ARV |  | 72600 | 0 | No change
[15 empty] | Remove 16" DI Pipe Above Grade - Lane Ave Bridge |  | 15400 | 15400 | Added | Remove 16" DI Pipe Above Grade - Lane Avenue Bridge |  | 19250 | 3850 | Include MOT; Remove division 1
[10 empty] | Tree Removal |  | 6000 |  |  | Tree Removal |  | 1200 | -4800 | Quantity Updated | Tree Removal/Replacement/Relocation |  | 6000 | 4800 | Quantity increased on final drawings; Updated unit cost
[20 empty] | Mt. Vernon Aerial Force Main Crossing |  | 125000 | 125000 | Combined line items noted above; Include MOT; Remove division 1
[10 empty] | 4" HDPE, slip lining |  | 39325 |  |  | 4" HDPE, slip lining |  | 39325 | 0 |  | Sliplining 4" HDPE DR 11 |  | 21450 | -17875 | Include MOT; Remove division 1; Assume no dewatering required based on updated geotech
[10 empty] | ARV, above grade |  | 6000 |  |  | ARV, above grade |  | 6000 | 0 |  | ARV, Above Grade ARV Assembly and Enclosure |  | 6000 | 0 | No change
[15 empty] | Wastewater Lateral Piping - Remove and Replace, 4-6" |  | 108000 | 108000 | Added quantity for replacing sewer laterals encountered during pipeline construction | Wastewater Lateral Piping - Remove and Replace, 4-6" |  | 108000 | 0 | No change
[15 empty] | 6217 Wilson Boulevard Pump Station Tie-in |  | 40000 | 40000 | Changed tie-in configuration to avoid bypass pumping or vactor trucks | 6217 Wilson Boulevard Pump Station Tie-in |  | 37500 | -2500 | Updated cost
[10 empty] | 8"x6" Tee |  | 850 |  |  | 8"x6" Tee |  | 450 | -400 | Revised Unit Cost |  |  |  | -450 | Removed from final drawings
[10 empty] | Pipe Support |  | 63500 |  |  | Pipe Support |  | 63500 | 0 |  |  |  |  | -63500 | Included in Mt. Vernon Aerial Force Main Crossing line items above
[10 empty] | Cash Allowance |  |  |  |  | Cash Allowance |  |  |  |  | Cash Allowances |  |  | 0 | No change
[15 empty] | Sewage Removal and Disposal |  | 40000 | 40000 | Allowance added for sewage removal | Sewage Removal and Disposal |  | 40000 | 0 | No change
[10 empty] | Law Enforcement |  | 50000 |  |  | Law Enforcement |  | 40000 | -10000 | Reduced allowance per JEA | Law Enforcement |  | 40000 | 0 | No change
[10 empty] | Soil and Concrete Testing |  | 50000 |  |  | Soil and Concrete Testing |  | 40000 | -10000 | Reduced allowance per JEA | Soil and Concrete Testing |  | 40000 | 0 | No change
[10 empty] | Landscape Restoration |  | 75000 |  |  | Landscape Restoration |  | 75000 | 0 |  |  |  |  | -75000 | Included in line items noted above
[10 empty] | Tree Protection |  | 3580 |  |  | Tree Protection |  | 3660 | 80 | Quantity Updated |  |  |  | -3660 | Included in line items noted above
[10 empty] | Soil and Erosion Control |  | 40000 |  |  | Soil and Erosion Control |  | 40000 | 0 |  |  |  |  | -40000 | Included in line items noted above
[10 empty] | Maintenance of Traffic |  | 307800 |  |  | Maintenance of Traffic |  | 307800 | 0 |  |  |  |  | -307800 | Included in line items noted above
[15 empty] | JEA SWA |  | 250000 | 250000 | SWA included at 100% per JEA | SWA Allowance |  | 250000 | 0 | No change
[15 empty] | Vactor Truck |  | 5000 | 5000 | Allowance added for bypassing flow at affected upstream lift stations during the Lane/Wilson valve tie-in connection to minimize impact to operations | Vactor Truck |  | 5000 | 0 | No change
[15 empty] | Geotechnical Testing - Auger Cast Piles |  | 10000 | 10000 | Added field quality control based on geotechnical recommendation | Geotechnical Testing - Auger Cast Piles |  | 10000 | 0 | No change
[10 empty] | * * * ADDITIONAL WORK IF ORDERED BY THE ENGINEER * * * |  |  |  |  | * * * ADDITIONAL WORK IF ORDERED BY THE ENGINEER * * * | [7 empty] | 0 | No change
[10 empty] | Trench Stabilization |  | 5000 |  |  | Trench Stabilization |  | 5000 | 0 |  |  |  |  | -5000 | Removed per JEA
[23 empty] | 0 | No change
[10 empty] | WATER MAIN |  |  |  |  | WATER MAIN |  |  |  |  | WATER MAIN |  |  | 0 | No change
[10 empty] | FH removal |  | 1500 |  |  | FH removal |  | 1500 | 0 |  | Fire Hydrant removal |  | 1500 | 0 | No change
[10 empty] | Abandon 6" Pipe - Sealing |  | 1800 |  |  | Abandon 6" Pipe - Sealing |  | 1800 | 0 |  | Abandon 6" Pipe - Sealing |  | 1800 | 0 | No change
[10 empty] | Abandon 8" Pipe - Sealing |  | 1800 |  |  | Abandon 8" Pipe - Sealing |  | 1800 | 0 |  | Abandon 8" Pipe - Sealing |  | 1800 | 0 | No change
[10 empty] | Pavement Removal (COJ) |  | 2054 |  |  | Pavement Removal (COJ) |  | 2054 | 0 |  | Pavement Removal (COJ) |  | 2054 | 0 | No change
[10 empty] | Paving Repair - Cross Cuts and Patches - Asphalt (COJ Case X) |  | 41078 |  |  | Paving Repair - Cross Cuts and Patches - Asphalt (COJ Case X) |  | 42479.6 | 1401.6 | Quantity Updated | Paving Repair - Cross Cuts and Patches - Asphalt (COJ Case X) |  | 42479.6 | 0 | No change
[10 empty] | Paving Repair - Cross Cuts and Patches - Base (COJ Case X) |  | 13467.45 |  |  | Paving Repair - Cross Cuts and Patches - Base (COJ Case X) |  | 13896 | 428.55 | Quantity Updated | Paving Repair - Cross Cuts and Patches - Base (COJ Case X) |  | 13896 | 0 | No change
[10 empty] | Grassing |  | 405 |  |  | Grassing/Sodding |  | 367.5 | -37.5 | Quantity Updated | Grassing |  | 367.5 | 0 | No change
[10 empty] | Remove Concrete Sidewalk (COJ) |  | 2240 |  |  | Remove Concrete Sidewalk (COJ) |  | 2240 | 0 |  | Remove Concrete Sidewalk (COJ) |  | 2240 | 0 | No change
[10 empty] | Remove Curb and Gutter (COJ) |  | 1927.8 |  |  | Remove Curb and Gutter (COJ) |  | 1931.58 | 3.78 | Quantity Updated | Remove Curb and Gutter (COJ) |  | 4599 | 2667.42 | Updated unit cost
[10 empty] | Replace Concrete Sidewalk (COJ) |  | 4480 |  |  | Replace Concrete Sidewalk (COJ) |  | 4480 | 0 |  | Replace Concrete Sidewalk (COJ) |  | 4480 | 0 | No change
[10 empty] | Replace Curb and Gutter (COJ) |  | 4590 |  |  | Replace Curb and Gutter (COJ) |  | 4590 | 0 |  | Replace Curb and Gutter (COJ) |  | 4590 | 0 | No change
[10 empty] | 6" PVC DR 18 Pipe |  | 1840 |  |  | 6" PVC DR 18 Pipe |  | 1560 | -280 | Quantity Updated | 6" PVC DR 18 Pipe |  | 6150 | 4590 | Quantity increased and unit cost updated; Include MOT; Remove division 1
[10 empty] | 8" PVC DR 18 Pipe |  | 69885 |  |  | 8" PVC DR 18 Pipe |  | 57600 | -12285 | Quantity Updated | 8" PVC DR 18 Pipe |  | 92950 | 35350 | Quantity increased and unit cost updated; Include MOT; Remove division 1
[10 empty] | 6" MJ 90° Bend |  | 2400 |  |  | 6" MJ 90° Bend |  | 2400 | 0 |  | 6" MJ 90° Bend |  | 2400 | 0 | No change
[10 empty] | 8" MJ 11.25° Bend |  | 425 |  |  | 8" MJ 11.25° Bend |  | 425 | 0 |  | 8" MJ 11.25° Bend |  | 425 | 0 | No change
[10 empty] | 8" MJ 22.5° Bend |  | 850 |  |  | 8" MJ 22.5° Bend |  | 850 | 0 |  | 8" MJ 22.5° Bend |  | 850 | 0 | No change
[10 empty] | 8" MJ 45° Bend |  | 450 |  |  | 8" MJ 45° Bend |  | 450 | 0 |  | 8" MJ 45° Bend |  | 450 | 0 | No change
[10 empty] | 8" MJ 90° Bend |  | 1000 |  |  | 8" MJ 90° Bend |  | 1000 | 0 |  | 8" MJ 90° Bend |  | 1000 | 0 | No change
[10 empty] | 8" Plug |  | 2280 |  |  | 8" Plug |  | 1900 | -380 | Quantity Updated | 8" Plug |  | 1900 | 0 | No change
[10 empty] | 8"x6" Tee |  | 5400 |  |  | 8"x6" Tee |  | 4800 | -600 | Quantity Updated | 8"x6" MJ Tee |  | 4800 | 0 | No change
[10 empty] | 8" Restrained Joint |  | 2160 |  |  | 8" Restrained Joint |  | 1800 | -360 | Quantity Updated | 8" Restrained Joint |  | 1800 | 0 | No change
[10 empty] | New Water Service Connection (short) |  | 3250 |  |  | New Water Service Connection (short) |  | 1950 | -1300 | Quantity Updated | New Water Service Connection (short) |  | 2100 | 150 | Updated unit cost
[10 empty] | Replace/Relocate Water Service Connection (long) |  | 15000 |  |  | Replace/Relocate Water Service Connection (long) |  | 15000 | 0 |  | Replace/Relocate Water Service Connection (long) |  | 15000 | 0 | No change
[10 empty] | Replace/Relocate Water Service Connection (short) |  | 3200 |  |  | Replace/Relocate Water Service Connection (short) |  | 3200 | 0 |  | Replace/Relocate Water Service Connection (short) |  | 3200 | 0 | No change
[10 empty] | 2" Sample Tap |  | 5200 |  |  | 2" Sample Tap |  | 5200 | 0 |  | Compliance Sample Taps (W-27) |  | 6400 | 1200 | Updated unit cost
[20 empty] | Temporary Sample Taps (W-25) |  | 2600 | 2600 | Added per JEA
[8 empty] | 0 |  | Fire Hydrant (FH) |  | 7500 |  |  | Fire Hydrant (FH) |  | 6000 | -1500 | Quantity Updated | Fire Hydrant (FH) |  | 6000 | 0 | No change
[8 empty] | 0 |  | 6" Gate Valve |  | 9200 |  |  | 6" Gate Valve |  | 8050 | -1150 | Quantity Updated | 6" MJ Gate Valve |  | 8050 | 0 | No change
[10 empty] | 8" Gate Valve |  | 11600 |  |  | 8" Gate Valve |  | 11600 | 0 |  | 8" MJ Gate Valve |  | 11600 | 0 | No change
[15 empty] | 8"x8" Tee |  | 2200 | 2200 | Added | 8"x8" MJ Tee |  | 2200 | 0 | No change
[10 empty] | 6" Full Circle Sleeve |  | 2000 |  |  | 6" Full Circle Sleeve |  | 2000 | 0 |  | 6" MJ Sleeve |  | 2000 | 0 | No change
[10 empty] | 8" MJ Sleeve |  | 1500 |  |  | 8" MJ Sleeve |  | 1500 | 0 |  | 8" MJ Sleeve |  | 1500 | 0 | No change
[20 empty] | 6" MJ Gate Valve |  | 2300 | 2300 | Added to final drawings
[15 empty] | Wastewater Lateral Piping - Remove and Replace, 8" |  | 3000 | 3000 | Added | Wastewater Piping - Remove and Replace, 8" |  | 3000 | 0 | No change
[10 empty] | Cash Allowances |  |  |  |  | Cash Allowances |  |  |  |  | Cash Allowances
[10 empty] | Soil and Concrete Testing |  | 15000 |  |  | Soil and Concrete Testing |  | 15000 | 0 |  | Soil and Concrete Testing |  | 700 | -14300 | Reduced allowance per JEA
[10 empty] | Landscape Restoration |  | 25000 |  |  | Landscape Restoration |  | 25000 | 0 |  |  |  |  | -25000 | Included in line items noted above
[10 empty] | Tree Protection |  | 400 |  |  | Tree Protection |  | 380 | -20 | Quantity Updated |  |  |  | -380 | Included in line items noted above
[10 empty] | Soil and Erosion Control |  | 3200 |  |  | Soil and Erosion Control |  | 700 | -2500 | Quantity Updated |  |  |  | -700 | Included in line items noted above
[10 empty] | * * * ADDITIONAL WORK IF ORDERED BY THE ENGINEER * * * |  |  |  |  | * * * ADDITIONAL WORK IF ORDERED BY THE ENGINEER * * *
[10 empty] | Trench Stabilization |  | 5000 |  |  | Trench Stabilization |  | 5000 | 0 |  |  |  |  | -5000 | Removed per JEA
0
|  | 0 | [5 empty] | 0 |  | JEA SWA (not used at 90% per JEA) |  |  | 0 | Not used at 90% | JEA SWA (see above)
JEA SWA |  | 0 |  | Not used at 30% | JEA SWA |  | 0 | 0 | Not used at 60% | Subtotal |  | 5053271.72 | 5053271.72 |  | Subtotal |  | 5473800 | 420528.28 |  | Subtotal |  | 5531917.15 | 58117.15
Subtotal |  | 0 |  |  | Subtotal |  | 0 | 0 |  | General Conditions (incl. in individual line items above) |  |  | 0 |  | General Conditions (incl. in individual line items above) |  |  | 0 |  | General Conditions (up to 10%) |  | 553200 | 553200
General Conditions | 10% | 0 |  |  | General Conditions | 10% | 0 | 0 |  | Subtotal |  | 5053271.72 | 5053271.72 |  | Subtotal |  | 5473800 | 420528.28 |  | Subtotal |  | 6085117.15 | 611317.15
Subtotal |  | 0 |  |  | Subtotal |  | 0 | 0 |  | Contingency on Previous Subtotal |  | 500000 | 500000 |  | Contingency |  |  | -500000 | Not used at 100% per JEA, replaced by SWA | Contingency |  |  | 0 | Not used at Final per JEA
Contingency | 15% | 0 |  |  | Contingency | 10% | 0 | 0 |  | Total Contractor Cost |  | 5553271.72 | 5553271.72 |  | Total Contractor Cost |  | 5473800 | -79471.72 |  | Total Contractor Cost |  | 6085117.15 | 611317.15
Total Contractor Cost |  | 0 |  |  | Total Contractor Cost |  | 0 | 0
[10 empty] | Additional Direct Costs |  |  |  |  | Additional Direct Costs |  |  |  |  | Additional Direct Costs
Additional Direct Costs |  |  |  |  | Additional Direct Costs |  |  |  |  | JEA Supplied Material & Labor |  | 4000 | 4000 |  | JEA Supplied Material & Labor |  | 4000 | 0 |  | JEA Supplied Material & Labor |  | 4000 | 0
JEA Supplied Material & Labor |  | 0 |  |  | JEA Supplied Material & Labor |  | 0 | 0 |  | Subtotal |  | 4000 | 4000 |  | Subtotal |  | 4000 | 0 |  | Subtotal |  | 4000 | 0
Subtotal |  | 0 |  |  | Subtotal |  | 0 | 0 |  | Total Direct Cost |  | 5557271.72 | 5557271.72 |  | Total Direct Cost |  | 5477800 | -79471.72 |  | Total Direct Cost |  | 6089117.15 | -79471.72
Total Direct Cost |  | 0 |  |  | Total Direct Cost |  | 0 | 0
[10 empty] | Indirect Costs |  |  |  |  | Indirect Costs |  |  |  |  | Indirect Costs
Indirect Costs |  |  |  |  | Indirect Costs |  |  |  |  | Project Management | 3% | 166598.1516 | 166598.1516 |  | Project Management | 3% | 164214 | -2384.1516 | Reduction of Total Contractor Cost | Project Management | 3% | 182553.5145 | 18339.5145
Project Management |  |  |  |  | Project Management |  |  | 0 |  | Engineering | 16.5% | 915953.5 | 915953.5 |  | Engineering | 17.06% | 933588 | 17634.5 | Added additional geotech work for JEA IP Sampling | Engineering | 15.34% | 933588 | 0
Engineering |  |  |  |  | Engineering |  |  | 0 |  | Services During Construction | 5% | 277663.586 | 277663.586 |  | Services During Construction | 5% | 273690 | -3973.586 | Reduction of Total Contractor Cost | Services During Construction | 5% | 304255.8575 | 30565.8575
Services During Construction |  |  |  |  | Services During Construction |  |  | 0 |  | Project Support | 1.4% | 77745.8041 | 77745.8041 |  | Miscellaneous | 1.4% | 76633.2 | -1112.6041 | Reduction of Total Contractor Cost | Miscellaneous | 1.4% | 85191.6401 | 8558.4401
[15 empty] | Easement - Wiley Park |  | 65000 | 65000 | Added per JEA | Easement - Wiley Park |  | 65000 | 0
Project Support |  |  |  |  | Project Support |  |  | 0 |  | Subtotal |  | 1437961.0417 | 1437961.0417 |  | Subtotal |  | 1513125.2 | 75164.1583 |  | Subtotal |  | 1570589.0121 | 57463.8121
Subtotal |  | 0 |  |  | Subtotal |  | 0 | 0 |  | Total Indirect Cost |  | 1437961.0417 | 1437961.0417 |  | Total Indirect Cost |  | 1513125.2 | 75164.1583 |  | Total Indirect Cost |  | 1570589.0121 | 57463.8121
Total Indirect Cost |  | 0 |  |  | Total Indirect Cost |  | 0 | 0 |  | Total Project Cost |  | 6995232.7617 | 6995232.7617 |  | Total Project Cost |  | 6990925.2 | -4307.5617 |  | Total Project Cost |  | 7659706.1621 | 668780.9621
Total Project Cost |  | 0 |  |  | Total Project Cost |  | 0 | 0

## APPENDIX B-BID Force Main
022-21 Appendix B - Bid Workbook
Durbin Pkwy N Manhole Installation (Only complete the Prices in Yellow Cells)
*Unless otherwise noted, this column refers to paragraphs /sections found in the latest edition of the JEA’s Water and Wastewater Standards Manual. **Reference found in this solicitation. ***Refer to Appendix A - Technical Specifications.
|  | Manhole # | Manhole # | Manhole # | Manhole # | Manhole #
Item | Spec | MH-021517 | MH-051632 | MH-026790 | MH-031652 | MH-036647 | Total Est. | Unit | Description | Unit Price | Extended Price
No. | No.* | Qty. | Qty. | Qty. | Qty. | Qty. | Qty.
1 | 801.IV.5 | 20 | 20 | 20 | 20 | 20 | 100 | CY | A-3 Sand Backfill |  | 0
2 | 801.VIII | 17.7778 | 17.7778 | 17.7778 | 92.2222 | 17.7778 | 163.3333 | SY | Sod |  | 0
3 | 801.IX.1 | 44.4444 | 44.4444 | 44.4444 | 44.4444 | 44.4444 | 222.2222 | SY | Asph Pavt Removal |  | 0
4 | 801.IX.2 | 44.4444 | 44.4444 | 44.4444 | 44.4444 | 44.4444 | 222.2222 | SY | Paving Repair Cross Cuts & Patches |  | 0
5 | 801.IX.6 & SJC D201 | 222.2222 | 222.2222 | 222.2222 | 222.2222 | 222.2222 | 1111.1111 | SY | 1.5" Mill & Overlay 50' each Way per SJC D201 |  | 0
6 | 801.X.1 | 38.8889 | 0 | 0 | 0 | 0 | 38.8889 | SY | Removal of Concrete Sidewalk |  | 0
7 | 801.X.2 | 0 | 0 | 0 | 0 | 10 | 10 | SY | Removal of Driveway |  | 0
8 | 801.X.3 | 85 | 40 | 40 | 40 | 40 | 245 | LF | Remove of Curb and Gutter |  | 0
9 | 801.X.4 | 38.8889 | 0 | 0 | 0 | 0 | 38.8889 | SY | Installation of Sidewalk |  | 0
10 | 801.X.5 | 0 | 0 | 0 | 0 | 10 | 10 | SY | Installation of Driveway |  | 0
11 | 801.X.6 | 85 | 40 | 40 | 40 | 40 | 245 | LF | Installation of Curb and Gutter |  | 0
12 | 905*** | 0 | 1 | 1 | 1 | 0 | 3 | EA | Remove and Construct Type "A" 4' Diameter Polymer Manhole - 18' - 20' Deep |  | 0
13 | 905*** | 0 | 0 | 0 | 0 | 1 | 1 | EA | Remove and Construct Type "A" 4' Diameter Polymer Manhole - 16' - 18' Deep |  | 0
14 | 905*** | 1 | 0 | 0 | 0 | 0 | 1 | EA | Remove and Construct Type "B" 4' Diameter Polymer Manhole - 16' - 18' Deep |  | 0
Cash Allowances
Item | Spec | [5 empty] | Est. | Unit | Description | Unit Price | Extended Price
No. | No. | [5 empty] | Qty.
15 | 2.17.10** | [5 empty] | 1 | LS | SWA Allowance | 50000 | 50000
16 | XVII.2 | [5 empty] | 1 | LS | Sewage Removal and Disposal Allowance | 50000 | 50000
[9 empty] | SUBTOTAL |  | 100000
%
[9 empty] | GENERAL/SPECIAL CONDITIONS (MAX. 10% OF SUBTOTAL) |  | 0
[10 empty] | TOTAL (Subtotal plus General Conditions & Special Conditions, inclusive transfer total to Page 1 Appendix B - Bid Form) | 100000