## Combined Bid Form
1410330446 Appendix B - Bid Workbook Galvanized Pipe Replacement Program College St. Area (Only Complete the Prices in Yellow Cells)
Galvanized Pipe Replacement Program - Packages C & G
Package C
PART I - WATER MAIN CONSTRUCTION
Item | Spec No. | Description | Est. Qty | Unit | Unit Price | Cost
1 | 801.III.2.2. | Abandon 2" Galvanized Water Main by Plugging | 3 | EA |  | 0
2 | 801.XIII.1 | 2" HDPE SDR-9 CTS Water Main | 22 | LF |  | 0
3 | 801.XIV.7. | Connect to Existing 2" Water Main | 1 | EA |  | 0
4 | 801.XIII.1 | 4" PVC DR-18 Water Main (JEA Supplied Pipe) | 24 | LF |  | 0
5 | 801.XIII.2 | 4" DI MJ Cap, Tapped 2" | 1 | EA |  | 0
6 | 801.XIII.2 | 4" Gate Valve | 1 | EA |  | 0
7 | 801.XIV.4 | Connect to Existing 6" Water Main: 6" x 6" Tapping Sleeve & Valve | 2 | EA |  | 0
8 | 801.XIII.1 | 6" PVC DR-18 Water Main (JEA Supplied Pipe) | 332 | LF |  | 0
9 | 801.XIII.2 | 6" Gate Valve | 4 | EA |  | 0
10 | 801.XIII.2 | 6" DI MJ 90 Degree Bend | 1 | EA |  | 0
11 | 801.XIII.2 | 6" DI MJ 45 Degree Bend | 2 | EA |  | 0
12 | 801.XIII.6 | 6" Pipe Bell Restraints | 1 | EA |  | 0
13 | 801.XIV.1 | Fire Hydrant Assembly | 4 | EA |  | 0
14 | 801.XIV.4 | Connect to Existing 12" Water Main: 12" x 8" Tapping Sleeve & Valve | 1 | EA |  | 0
15 | 801.XIII.1 | 8" PVC DR-18 Water Main (JEA Supplied Pipe) | 2210 | LF |  | 0
16 | 801.XIII.2 | 8" x 6" DI MJ Reducer | 1 | EA |  | 0
17 | 801.XIII.2 | 8" x 8"x 6" DI MJ Tee | 5 | EA |  | 0
18 | 801.XIII.2 | 8" x 8"x 4" DI MJ Tee | 1 | EA |  | 0
19 | 801.XIII.2 | 8" 45 Degree DI MJ Bend | 18 | EA |  | 0
20 | 801.XIII.2 | 8" Gate Valve | 2 | EA |  | 0
21 | 801.XIII.6. | 8" Pipe Bell Restraints | 22 | EA |  | 0
22 | 801.XIII.9. | Remove & Replace Existing 1" Water Service - (Short) | 35 | EA |  | 0
23 | 801.XIII.9. | Remove & Replace Existing 1" Water Service - (Long) | 21 | EA |  | 0
24 | 801.XIII.9. | Remove & Relocate Existing 1" Water Service - (Short) | 5 | EA |  | 0
25 | 801.XIII.9. | Remove & Relocate Existing 1" Water Service - (Long) | 18 | EA |  | 0
26 | 801.XIII.8 | Furnish & Install New 1" Water Service - (Short) | 1 | EA |  | 0
27 | 801.XIII.8 | Furnish & Install New 1" Water Service - (Long) | 1 | EA |  | 0
28 | 801.XIII.12 | Temporary Sample Tap (W-25, W-26) | 5 | EA |  | 0
29 | NA | Testing Allowance | 1 | LS |  | 4000
30 | NA | SWA Allowance | 1 | LS |  | 20000
|  | Part I Water Main Subtotal |  |  |  | 24000
PART II - PAVING & DRAINAGE CONSTRUCTION
Item | Spec No. | Description | Est. Qty | Unit | Unit Price | Cost
1 | 801.IX.1 | Pavement Removal | 1793 | SY |  | 0
2 | 801.IX.2/S.C. 16 | Case X Pavement Repair Permanent | 1793 | SY |  | 0
3 | 801.IX.6 | 1.5" Mill & Resurface | 3894 | SY |  | 0
4 | 801.X.1 | Concrete Sidewalk Removal (all thicknesses) | 47 | SY |  | 0
5 | 801.X.4 | 4" Thick Concrete Sidewalk Replacement | 47 | SY |  | 0
6 | 801.X.2 | Driveway Removal (all types) | 416 | SY |  | 0
7 | 801.X.5 | 5" Thick Concrete Driveway | 416 | SY |  | 0
8 | 801.XII.1 | 48" RCP | 16 | LF |  | 0
9 | 801.III.2.4 | Remove Storm Piping (All types/sizes) | 16 | LF |  | 0
10 | 801.VIII | Sodding | 173 | SY |  | 0
|  | Part II Paving & Drainage Subtotal |  |  |  | 0
PART III - FORCE MAIN CONSTRUCTION
Item | Spec No. | Description | Est. Qty | Unit | Unit Price | Cost
1 | 801.III.2.3. | 6" Force Main Grout Fill | 2460 | LF |  | 0
|  | Part III Force Main Subtotal |  |  |  | 0
|  | Package C PARTS I THRU III TOTAL |  |  |  | 24000
|  | General Conditions Percentage (10% max) |  |  |  | 0
|  |  | Package C Bid Total |  |  | 24000
Package G
PART I - WATER MAIN CONSTRUCTION
Item | Spec No. | Description | Est. Qty | Unit | Unit Price | Cost
1 | 801.III.2.2. | Abandon 2" Galvanized Water Main by Plugging | 6 | EA |  | 0
2 | 801.XIII.1 | 2" Plug | 6 | EA |  | 0
3 | 801.XIV.7. | Connect to Existing 4" Water Main 4" x 4" Tapping Sleeve & Valve | 1 | EA |  | 0
4 | 801.XIII.1 | 4" PVC DR-18 Water Main (JEA Supplied Pipe) | 220 | LF |  | 0
5 | 801.XIII.2 | 2" DI MJ Cap, Tapped 2" | 1 | EA |  | 0
6 | 801.XIII.2 | 4" DI MJ 45 Degree Bend | 4 | EA |  | 0
7 | 801.XIII.2 | 4" Gate Valve with C.I. Valve Box | 1 | EA |  | 0
8 | 801.XIII.6 | 4" Pipe Bell Restraints | 3 | EA |  | 0
9 | 801.XIII.2 | 6" x 4" DI MJ Reducer | 1 | EA |  | 0
10 | 801.XIV.4 | Connect to Existing 6" Water Main: 6" x 6" Tapping Sleeve & Valve | 1 | EA |  | 0
11 | 801.XIV.4 | Connect to Existing 6" Water Main: 8" x 6" Tapping Sleeve & Valve | 1 | EA |  | 0
12 | 801.XIII.1 | 6" PVC DR-18 Water Main (JEA Supplied Pipe) | 2150 | LF |  | 0
13 | 801.XIII.2 | 6" Gate Valve w/C.I. Valve Box | 11 | EA |  | 0
14 | 801.XIII.2 | 6" DI MJ Tee | 5 | EA |  | 0
15 | 801.XIII.2 | 6" DI MJ 11.25 Degree Bend | 17 | EA |  | 0
16 | 801.XIII.2 | 6" DI MJ 22.5 Degree Bend | 10 | EA |  | 0
17 | 801.XIII.2 | 6" DI MJ 45 Degree Bend | 10 | EA |  | 0
18 | 801.XIII.6 | 6" Pipe Bell Restraints | 39 | EA |  | 0
19 | 801.XIV.1 | Fire Hydrant Assembly | 5 | EA |  | 0
20 | 801.XIV.4 | Connect to Existing 8" Water Main: 8" x 8" Tapping Sleeve & Valve | 2 | EA |  | 0
21 | 801.XIII.1 | 8" PVC DR-18 Water Main (JEA Supplied Pipe) | 740 | LF |  | 0
22 | 801.XIII.2 | 8" x 6" DI MJ Reducer | 4 | EA |  | 0
23 | 801.XIII.2 | 8" x 8"x 6" DI MJ Tee | 2 | EA |  | 0
24 | 801.XIII.2 | 8" x 8"x 8" DI MJ Tee | 1 | EA |  | 0
25 | 801.XIII.2 | 8" 11.25 Degree DI MJ Bend | 2 | EA |  | 0
26 | 801.XIII.2 | 8" 45 Degree DI MJ Bend | 12 | EA |  | 0
27 | 801.XIII.2 | 8" Gate Valve | 3 | EA |  | 0
28 | 801.XIII.6 | 8" Pipe Bell Restraints | 14 | EA |  | 0
29 | 801.XIII.1 | 18" DR-17 HDPE DIPS Pipe [for casing] | 160 | LF |  | 0
30 | 801.XIII.9. | Remove & Replace Existing 1" Water Service - (Short) | 16 | EA |  | 0
31 | 801.XIII.9. | Remove & Replace Existing 1" Water Service - (Long) | 12 | EA |  | 0
32 | 801.XIII.9. | Remove & Relocate Existing 1" Water Service - (Short) | 1 | EA |  | 0
33 | 801.XIII.8 | Furnish & Install New 1" Water Service - (Short) | 8 | EA |  | 0
34 | 801.XIII.8 | Furnish & Install New 1" Water Service - (Long) | 16 | EA |  | 0
35 | 801.XIII.12 | Temporary Sample Tap (W-25, W-26) | 7 | EA |  | 0
36 | 801.IV.4 | AASHTO Class A-3 Soil | 288 | CY |  | 0
37 | N/A | Testing Allowance | 1 | LS | - | 4000
38 | N/A | SWA Allowance | 1 | LS | - | 20000
|  | Part I Water Main Subtotal |  |  |  | 24000
PART II - PAVING & DRAINAGE CONSTRUCTION
Item | Spec No. | Description | Est. Qty | Unit | Unit Price | Cost
1 | 801.IX.1 | Pavement Removal | 615 | SY |  | 0
2 | 801.IX.2/S.C. 16 | Case X Pavement Repair Permanent | 615 | SY |  | 0
3 | 801.IX.6 | 1.5" Mill & Resurface | 1629 | SY |  | 0
4 | 801.X.1 | Concrete Sidewalk Removal (all thicknesses) | 659 | SY |  | 0
5 | 801.X.4 | 4" Thick Concrete Sidewalk Replacement | 646 | SY |  | 0
6 | 801.X.2 | Driveway Removal (all types) | 500 | SY |  | 0
7 | 801.X.5 | 5" Thick Concrete Driveway | 75 | SY |  | 0
8 | 801.X.5 | Asphalt/Dirt Driveway | 425 | SY |  | 0
9 | 801.X.5 | ADA Ramp Installation | 7 | EA |  | 0
10 | 801.X.3 | Removal Of Curb And Gutter | 270 | LF |  | 0
11 | 801.X.6. | Installation Of Curb And Gutter | 270 | LF |  | 0
12 | 801.XII.1 | 12", 15", and 18" RCP | 200 | LF |  | 0
13 | 801.III.2.4 | Remove Storm Piping (All types/sizes) | 150 | LF |  | 0
14 | 801.VIII | Sodding | 1444 | SY |  | 0
|  | Part II Paving & Drainage Subtotal |  |  |  | 0
|  | Package G PARTS I THRU IV TOTAL |  |  |  | 24000
|  | General Conditions Percentage (10% max) |  |  |  | 0
|  |  | Package G Bid Total |  |  | 24000
[5 empty] | Total Bid Price (Packages C & G, transfer total to Page 1 Appendix B - Bid Form) | 48000
|  | Total Bid Price less General Conditions, SWAs and Allowances: |  |  |  | 0
|  | JSEB Requirement: |  |  |  | 12%
|  |  | JSEB Requirement (dollars): |  |  | 0