XXXXX APPENDIX A - CRITICAL PATH METHOD (CPM) SCHEDULING REQUIREMENTS

The Company shall use the Critical Path Method (CPM) to schedule and manage the Work. A qualified member of the Company's personnel shall create the schedule. If the Company does not have staff capable of preparing and managing CPM schedules, the Company shall obtain such qualified personnel on a subcontract basis for supporting this Contract.

All CPM scheduling will be performed using CPM precedence diagramming method (PDM) scheduling software such as Primavera P6, Primavera Contractor or a CPM scheduling software compatible with Primavera P6 import capabilities (.xer file format). The Company shall submit all schedules and associated reports to the Contract Administrator in paper and electronic formats as described below in order to allow both complete analysis of the schedules and accurate record keeping.

In addition, all construction contracts will have a cost-loaded schedule.

Project Schedule Definitions

Activity – A single, continuous, and identifiable task in the total Work. The project work scope is sub-divided into work tasks that are represented in the schedule software as activities. How finely the project scope is subdivided into tasks determines the "level of detail" within the schedule. JEA retains the right to reject a schedule for insufficient levels of activity detail.

Baseline Schedule – The Baseline Schedule comprises the plan and schedule that the Company intends to use to perform and complete the Work. Upon approval by the JEA Representative, the Baseline Schedule shall be the schedule of record from which entitlement for adjustments in the completion deadline(s) shall be measured until a Revised Baseline Schedule is approved by the JEA Representative.

Contract Float – Contract Float is the number of days between the Company’s anticipated date for early completion of the Work, or specified part, and the corresponding Contract Time.

Contract Milestone – A Contract Milestone is a Milestone required in every project schedule to identify significant Contract events. Required Contract Milestones include Notice to Proceed (NTP), Substantial Completion (SC) and Final Completion (FC).

CPM Network – The CPM Network is a transferable electronic copy of project software data and files. It includes, but is not limited to, activities, milestones, calendar definitions, precedence relationships including any relationship lag periods, date constraints, baseline schedules, project and activity code definitions, resource definitions, resource assignments, project values (e.g. the data date/time now value, settings for project-activity processing options, etc.), and all information that can be generated from such data.

Critical Path – The Critical Path is defined as the longest continuous series of activities through the network to the Substantial Completion Contract Milestone.

Current Schedule – The Current Schedule has progress information (updates) reported against in-progress and completed activities. Update information is used to re-calculate / reforecast the most likely "early start" dates of the remaining incomplete activities as sequenced by the network. This calculation establishes the earliest forecasted completion date of the project, which allows Project Managers to determine if they are ahead, on, or behind schedule to meet the Contract Milestones. A current schedule is used to evaluate Company progress against the Baseline Schedule.

Interim Contract Milestone – An Interim Contract Milestone is a Milestone that is specifically called out by the Contract to be included in the project schedule. Example Interim Contract Milestones could be completion of specific phases of work at a specific number of contract days from NTP or required delivery dates of material or equipment.

Interim Schedule – The Interim Schedule and schedule narrative describes the activities to be performed within the first 120 calendar days after NTP and their interdependencies subject to all requirements of the Contract. The Interim Schedule shall include a separate proposed payment plan for its duration, which upon written approval by JEA, shall be used by the Company for payment purposes during the Interim Schedule period.

Milestone – A task with zero duration that identifies the instant of time at which a significant task within the project is starting or stopping. Start Milestones shall be used to represent the start of a significant task while Finish Milestones shall be used to represent the completion of a significant task.

Precedence Relationships – The logical relationships created in the scheduling software to sequence the performance of the work tasks identified by activities or milestones. Precedence relationships can be categorized in 4 groups - Finish-to-start, Start-to-Start, Finish-to-Finish, and Start-to-Finish. The interface between activities created by precedence relationships creates a PDM network logic. A PDM logic where estimated durations have not been assigned to the activities constitutes a network "Plan". Once activities are assigned estimated durations, the software interfaces durations and the network logic to calculate a "Schedule" based on the Plan.

Proposed Schedules – Proposed schedules are schedules in which the Company proposes revisions and/or changes to the Baseline Schedule for JEA’s acceptance. If a Proposed Schedule is accepted by JEA, it shall be incorporated into a Revised Baseline Schedule and all work progress shall be reported against it going forward.

Revised Baseline Schedule – A Revised Baseline Schedule is submitted by the Company whenever changes in the Current Baseline Schedule are required to accurately reflect any changes in the Company’s plan for performing the Work or the impact of any approved changes in the Work. The Revised Baseline Schedule, once approved by JEA, comes the Baseline Schedule from which progress and entitlement for adjustments to the Completion Deadline is measured.

Schedule Progress Updates – Schedule Progress Updates are submitted monthly by the Company to update the Current Schedule with status during the period of the update and to reflect the Company’s current plan for performing the Work.

Three Week Look-ahead Schedule – A schedule, submitted by the Company, of all planned work to be performed over the next three weeks in sufficient detail to enable the tracking of the day-to-day field activities. The detail and format are as directed by the JEA project representative but a Three Week Look-Ahead produced from the Current Schedule is preferred. These Three Week Look-ahead Schedules are to be submitted weekly by the Company in PDF format.

Total Float – Total Float is the amount of time a scheduled activity can be delayed without delaying the completion of the Work beyond the Contract Milestones.

Purpose of the Project Schedule

Project schedules shall be used for evaluating all issues related to time for this Contract. The project schedules shall be used by JEA and the Company for the following purposes as well as any other purpose where the issue of time is relevant:

- To communicate to JEA the Company’s current plan for carrying out the Work;

- To identify work paths that are critical to the timely completion of the Work;

- To identify upcoming activities on the critical path(s);

- To evaluate the best course of action for mitigating the impact of unforeseen events;

- As the basis of establishing the predecessors for each contract milestone;

- As the basis for analyzing the time impact of changes in the Work;

- As a reference in determining the cost associated with increases or decreases in the Work;

- To prioritize activities for which JEA is responsible;

- To document the actual progress of the Work;

- To evaluate the resource requirements of the Company;

- To integrate the Work with the operational requirements of JEA’s facilities;

- To schedule and coordinate interfaces with adjacent contracts;

- As a basis for determining valid acceleration plans;

- To facilitate efforts to complete the Work in a timely manner;

- To verify progress of the Work as it pertains to billing periods and invoices for payment.

The project schedules provide a basis for decisions that may affect the Work under this Contract, as well as other concurrent or future contracts. The Company shall submit schedule submittals per the requirements of this specification. Project schedules should always reflect the Company’s current plan for the Work and be updated as described in this specification.

Schedule Type

All project schedules shall be a computer generated, Critical Path Method (CPM) network utilizing the precedence diagram method of scheduling.

Software

The Project Schedule in CPM format (the “CPM schedule”) shall be created in a format compatible with the latest version of Primavera P6, or as otherwise specified by JEA. The Company shall purchase and maintain a valid software maintenance agreement for each license of software necessary to produce the Project Schedule. The Company shall not upgrade to a new version of the scheduling software during a project unless previously approved in writing by JEA. If the Company desires, they may procure the services of a third party to provide scheduling services at no additional cost to JEA.

JEA currently uses Primavera P6 version 18.8 and require the Company’s use either Primavera P6 or Primavera Company.

Use of Float

Total Float and Contract Float are not for the exclusive use or benefit of either JEA or the Company, but must be used in the best interest of completing the project within the Contract Time relative to the contract milestones. If the Early Dates in any Progress Schedule Submittal forecasts any slippage or overrun of the contract milestones, the Company shall indicate such slippage or overrun by reporting negative float. Total and Contract Float shall be available to JEA, consultants, or the Company to accommodate changes in the Work or to mitigate the effect of events which may delay performance or completion. Total and Contract Float are an expiring resource available to all parties, acting in good faith, as needed to meet the contract milestones. JEA will monitor and optimize the use of float for the benefit of the project.

Early Completion

An early completion schedule is one that anticipates completion of all or a specified part of the work ahead of the corresponding contract time. Since Contract Float belongs to the project, the Company shall not be entitled to any extension in contract time or recovery for any delay incurred because of extensions of an early completion date until all Contract Float is used or consumed and performance or completion of the work extends beyond the contract time.

Pacing

If the Work is delayed on the Critical Path due to a delay caused by JEA, thereby creating additional float on any other path, then use of such float shall be construed as a concurrent delay to any delay caused by JEA. The Company shall maintain its original schedule on the other paths and activities not affected by the delay.

Non-Compliance

JEA may refuse to recommend/authorize a progress payment in the event of the Company’s failure, refusal or neglect to provide the required schedule information, since this will preclude the proper evaluation of the Company’s progress. Remedies for the Company’s failure, neglect or refusal to comply with the requirements of this section are in addition, and not limited to, those provided under other sections of the Contract.

Quality Assurance

The Company shall perform the Work covered by this section with personnel having substantial experience in the use of scheduling software on construction projects that required the development and maintenance of the schedule throughout the project duration.

It is the responsibility of the Company to work with each subcontractor and supplier to obtain information pertinent to the planning and updating of their respective activities in the schedule.

Baseline Schedule Preparation and Submittal

In achieving an approved Baseline Schedule there will be no adjustment in the Contract Price. In general, the Baseline Schedule shall demonstrate a complete understanding of the Work, inclusive of all phasing and sequencing considerations and shall include, but not be limited to:

- The order in which the Company intends to prosecute the Work, outlining the intended flow of Work, including submittals, submittal reviews, procurement of equipment and materials, maintenance of traffic, pollution control measures, utility interfaces, right-of-way, and other information as required by the contract;

- All relevant work constraints to performing the Work including, but not limited to, right-of-way access constraints (with clear logical connections to the commencement of various work), accommodation of utility relocations, permitting restrictions, and environmental/seasonal constraints;

- The dates on which the Company plans to start and complete various Work stages, operations, and principle items of Work, including the Contract Milestones; and

- Interfaces with other entities such as Utility Owners, Third Parties, adjacent Companies and other stakeholders;

- The Baseline Schedule will be accompanied by a payment breakdown. This breakdown will identify the costs associated with each schedule activity.

- All schedule submittals shall be in accordance with Section 7: Review, Acceptance and Approval of Project Schedule Submittals.

Completion, Timeliness and Review of Baseline Schedule Submittals

To promote the efficient use of Company and JEA scheduling resources, the submittal requirements have been phased. The Company shall complete and submit schedules in accordance with the submittal deadlines contained in Table 1. For the determination of submittal deadline dates and total contract schedule duration, the date of NTP shall be working day number one.

Baseline schedule submittals will be reviewed for conformity with the Contract and the requirements in this specification. Each submittal required by this section shall reflect the incorporation of all of JEA’s comments on the Baseline Schedule to date. With each submittal, the Company shall provide a written response to each of JEA’s comments to date.

Failure of the Company to provide complete, timely Baseline Schedule submittals as specified, and in the sequence and timeframes specified below, may result in delays or extensions to JEA review periods. Baseline Schedule Submittals may be rejected for incompleteness or failure to meet the specification requirements and re-submittal will be required. The Company may submit information earlier than required in the Baseline Schedule Submittal Schedule in Table 1.

Once approved by JEA, the Baseline Schedule shall be assigned as the Project Baseline in the scheduling software used by the Company. All subsequent printed schedules produced by the Company shall show both the Current Schedule and Baseline Schedule Gantt Chart bars.

Baseline Schedule Submittals

In the course of developing the Baseline Schedule, the Company shall submit the deliverables below for JEA review in accordance with the following schedule:

|  |  | Construction Duration < 6 Months | Construction Duration 6 - 12 Months | Construction Duration > 12 Months |
| --- | --- | --- | --- | --- |
| Step | Description | Submittal Deadline (Working Days after NTP) | Submittal Deadline (Working Days after NTP) | Submittal Deadline (Working Days after NTP) |
| 1 | Interim Schedule Submittal | 10 | 10 | 10 |
| 2 | Proposed Payment Breakdown | 15 | 20 | 20 |
| 3 | Baseline Schedule Submittal | 20 | 30 | 60 |
| 4 | Corrected Baseline Schedule Submittal | 30 | 45 | 80 |

Table 1: Baseline Schedule Submittal Schedule

Step 1 – Interim Schedule Submittal

No later than the deadline specified in table 1, the Company shall submit an Interim Schedule detailing activities that are to be performed within the first 120 calendar days after NTP. JEA will review and may approve an acceptable Interim Schedule within 10 working days of submittal. JEA may require the full Interim Schedule, or parts thereof, to be resubmitted throughout the review period. The Interim Schedule Submittal shall include:

- Narrative Report describing work to be performed during the Interim Schedule period using the Baseline Schedule Narrative format described below.

- Electronic schedule file.

- A proposed payment plan, which upon written approval by JEA, shall be used by the Company for payment purposes during the Interim Schedule period.

APPROVAL OF THE INTERIM SCHEDULE IS A CONDITION PRECEDENT FOR PAYMENT.

Step 2 – Proposed Payment Breakdown Submittal

No later than the deadline specified in table 1, the Company shall submit the proposed Schedule of Values (SOV), which upon approval by JEA, shall be used by the Company for payment application purposes. When preparing the SOV, consideration should be given to Enterprise Asset Management reporting requirements that are required at the end of the contract.

As part of the Proposed Payment Breakdown Submittal, the Company shall also submit a list of all submittals required by the contract.

Step 3 – Baseline Schedule Submittal

No later than the deadline specified in table 1, the Company shall complete the Baseline Schedule submittal for approval representing all Work required by the contract. The Baseline Schedule submittal shall include:

- Baseline Narrative Report;

- Electronic schedule file;

- Contract Payment Breakdown Report – a report forecasting monthly cash flow that details all costs loaded to the schedule;

- Cumulative and monthly total project costs curves reflecting the total contract amount.

APPROVAL OF THE BASELINE SCHEDULE IS A CONDITION PRECEDENT FOR PAYMENT BEYOND THE INTERIM SCHEDULE.

Step 4 – Corrected Baseline Schedule Submittal

In the event the Baseline Schedule submittal (Step 3) is not approved, and no later than the deadline specified in table 1, the Company shall complete the Corrected Baseline Schedule Submittal. The Company shall correct the Baseline Schedule submittal for approval by incorporating all of JEA’s comments on the initial Baseline Schedule submittal. No additional changes shall be made. The corrected Baseline Schedule submittal shall be revised and resubmitted until receipt of JEA approval.

Schedule Requirements

General – For the purpose of enabling both JEA and the Company to readily evaluate the Project Schedule, including derived data and reports, the Project Schedules shall be administered in accordance with the following requirements.

All schedules shall be prepared by the Company and reflect the Company’s plans, means and methods, techniques and sequences for performing the Work.

The schedules shall break down the Work into distinct activities with interdependencies to the extent required to clearly depict the planned approach for completion of the Work and to effectively manage the execution of the Work. The schedules shall:

- Divide the Work into manageable and logical segments and specify the progression from Notice to Proceed (NTP) to Substantial Completion (SC) to Final Completion (FC) within the Contract Time.

- Include, at a minimum, appropriate time allowances for submittals, procurement, coordination with others, construction, start-up/check-out (if applicable), operational and performance testing (if applicable), commissioning (if applicable), and Contract closeout.

- The NTP activity shall be the first activity in the schedule and shall be a Start Milestone with an assigned 7-day, no holiday calendar. The SC and FC activities shall be Finish Milestones with assigned “Finish on or Before” constraints, set to the contract milestone dates, with a 7-day no holiday calendar.

- The NTP, SC and FC milestones may include the contract milestone dates in the activity description for quick reference by all parties.

Schedule Settings and Setup – If the Company will be using Oracle Primavera P6, the settings shall be as follows:

- The Project ID will be the contract number between JEA and the Company. It will be appended as described in the following section titled “Project ID Suffix”. The Project Name shall be as defined in the contract between JEA and the Company.

- The Project WBS will, at a minimum consist of the following:

  - Level 1 – Project

  - Level 2 – Executive Summary

    - Shall be populated with sufficient Level of Effort activities and milestones to provide management an overview of the contract. All Contract Milestones will be included at this level.

  - Level 3 – Submittal Preparation

  - Level 4 – Submittal Review and Acceptance

  - Level 5 – Fabrication & Delivery

  - The WBS for the remaining construction related work is at the discretion of the Company. The Company must ensure that the WBS structure is sufficiently robust to segregate, manage, and present the various work types, phases, segments, elements and locations in a clear logical manner and convey the sequence at which the Company intends to construction the Work.

- Project ID Suffix:

  - Each schedule submittal shall have a unique identifier appended to the Project ID specified in the previous section titled “Project ID/Name”, in the form of:

    - For Baseline Schedules, “-BL”.

    - For Proposed Schedules, “-Pbbb”, where ‘bbb’ is sequential starting at 001.

    - For Revised Baseline Schedules, “-RBLccc”, where ‘ccc’ is sequential starting at 001.

    - For Schedule Progress Updates, “-PUyymm”, where ‘yy’ and ‘mm’ correspond to the year and month of the monthly submittal.

- Activity Codes must be maintained at the Project level.

- Calendars must be maintained at the Project level and account for all work scenarios in the Contract and planned by the Company.

- Duration Type shall be “Fixed Duration & Units”.

- Percent Complete Type shall be “Physical”.

- Make Open Ended Activities Critical should be checked.

- Scheduling method for progressed activities shall be set to “Retained Logic”.

- Total Float Calculations shall be set to “Finish Float = Late Finish – Early Finish”.

- Define Critical Activities as “Longest Path”.

Activity Identification – each activity in the Project Schedules shall have an activity identifier (Activity ID). The Company shall utilize an Activity ID that is simple and allows space between existing activities for the future addition of activities for continuing sort and display capability. The Activity ID of an existing activity shall not be modified or assigned to another activity. The scope of work for an activity shall not be substantially changed once the Baseline Schedule is approved since this would result in re-use of the Activity ID for a different scope of work. If the Contactor opts to use an intelligent Activity ID, the Company must provide a breakdown of what each character of the Activity ID represents.

Activity Description – the activity description shall identify the unique scope of the activity. There shall not be any two activities with the same activity description. It shall not be necessary to investigate activity code assignments or logic relationships to identify the scope of an activity. For example, the description “POUR FOOTINGS” or “INSTALL MANHOLE” will not be acceptable; the description “POUR FOOTINGS OF BIOSOLIDS BUILDING” or “INSTALL MANHOLE – Sta. 112+00” will be acceptable. At the same time, the Activity Description shall be concise enough to not require excessive column width in the Oracle Primavera P6 layout. The terms “Miscellaneous,” “Misc.” or other vague adjectives shall not be used as an activity description. The Company shall standardize the use of terms and their spelling in all activity descriptions. Abbreviations used in activity descriptions shall be consistent with the abbreviations used throughout the Contract and the design drawings. Once the Baseline Schedule is approved, activity descriptions shall not be modified except at the direction or with the consent of JEA.

Activity Duration – unless otherwise specified, construction activities shall have a duration between one (1) and fifteen (15) working days. At the request of JEA, the Company shall substantiate the need for specific activities having shorter or longer durations than stated herein. Certain non-labor activities such as procurement or delivering of materials may have durations in excess of 15 working days. After approval of the Baseline Schedule, changes in activity durations shall be addressed exclusively with the Duration Remaining data field. JEA shall be the final authority regarding the appropriate level of schedule detail for all schedules submitted for approval.

Activity Dates – Early and Late start and finish dates of activities shall be calculated for each activity based upon the schedule data date, actual dates, schedule logic, schedule constraints, calendars, original duration or remaining duration, in accordance with the schedule parameters defined in this specification.

Activity Predecessors and Successors – every activity shall have logically assigned predecessors and successors in conformance with the requirements of this section. The logical predecessors for each activity will be limited to those activities whose scope of work necessarily must be completed in order to perform the current activity. Unless otherwise specified, NTP shall be the only activity in the Project Schedules without predecessors and the Final Completion activity shall be the only activity in the Project Schedules without a successor.

Activity Constraints – Activity Constraints can affect activity float calculations and will not be used unless approved by JEA or allowed by this specification. The imposition of a date constraint on any activity other than the contract completion deadlines will only be permitted when the Company substantiates the need for the constraints to the satisfaction of JEA.

Activity Percent Complete – Activity remaining durations and percent complete shall be entered in the Project Schedules by the Company as appropriate to indicate activity progress and status as of the current Data Date for the update. The Company is to insure that progress is based on a current estimate of remaining duration to complete the Work and not the activity’s percent complete which calculates the remaining duration based on the original estimated duration.

Activity Codes – The Project Schedules shall contain activity code classifications and code values. The coding shall also incorporate the appropriate JEA provided data elements to allow reporting by any individual element or a combination thereof. These activity codes shall be the first codes defined for the activities, followed by any other codes, and shall use the values provided by JEA following award. The Company may add additional codes to satisfy its own requirements. In addition to JEA’s activity codes, the Company shall propose a coding structure for JEA’s review and acceptance. The activity code structure combined with the activity identification number shall provide the capability to organize information by location, road or ramp, structure, work type, subcontractor, discipline, etc.

Activity Calendar - The planning unit for the Work shall be whole working days. The use of other calendars may be used as required with a clear definition within the calendar description and/or the Baseline Schedule Narrative as to what the calendar is intended to be used for and/or what specific non-working periods they include. Level of Effort or WBS Summary activities used to show project durations from NTP to a Contract Milestone shall use a seven-day no holiday calendar. A common calendar base time of eight (8) consecutive hours (e.g., 8 AM to 4 PM) will be used on all calendars unless approved by JEA. To ensure activity start and finish dates are accurately calculated, time will be turned on when performing updates to the Project Schedule. This ensures activity durations are not inadvertently calculated as a partial workday or result in a 1-day duration activity spanning multiple dates.

Cost Loading – Project Schedules shall be cost loaded. All costs necessary to meet the particular requirements of each payment activity will be included in the payment breakdown and that breakdown will total up to the Contract Price. Costs can be loaded as non-labor resources or as expenses if desired.

Change Orders/SWA – New activities will be added to the project schedules upon approval of a Change order or SWA. These new activities will also include the costs associated with the Change Order/SWA. The Activity ID of these new activities should clearly show it represents a Change Order or SWA. For example, an activity with an ID of “CO1-100” indicates that it represents Change Order #1. If multiple activities are to be added under a single Change Order or SWA they shall be sequentially numbered such as CO1-100, CO1-110, CO1-120, etc.

CPM Logic – The Company shall be responsible for developing the CPM logic of the Baseline Schedule and for updating that CPM logic each month to accurately reflect the progress of the Work to date and the Company’s current plan for completion of the work. All paths through the Project Schedules shall proceed in the direction representing the progression of time. Activity lag durations shall not have a negative value. Activity lags shall not be used in lieu of activities. Redundant ties to preceding activities in a sequential series of activities will not be permitted. For example, if activity C is the successor in a Finish-Start relationship to activity B, and activity B is the successor in a Finish-Start relationship to activity A, then activity A shall not have a redundant Finish-Start relationship to activity C. A tie representing a different constraint will not be considered redundant. For example, a logic tie showing that the completion of the work scope of a predecessor is required before the successor can start is different from a logic tie representing a resource limitation and will not be considered redundant.

Timely Completion – Unless otherwise specified, timely completion shall refer to completion on or before a date that supports the Contract Milestones.

Use of Constraints or Float Suppression Techniques – Any use of Start constraints within the schedule shall be documented in the schedule narrative. The only instance where a Late Finish constraint may be used is for the Substantial Completion or Final Completion Milestones. Any other use of constraints is prohibited. The use of negative lags or the use of any other float suppression techniques is also prohibited from use in project schedules.

Resource Leveling – In schedule submittals to JEA, the Company shall not use restraints or constraints to optimize and/or level manpower and equipment requirements. Activities shall be duration and logic driven.

Default Progress Data – Actual Start and Finish dates shall not be automatically updated by default mechanisms that may be included in the CPM scheduling software systems.

Out-of-Sequence Logic – The Company shall correct all incorrect logic relationships in the schedule update to eliminate any out-of-sequence logic. The Company shall make all changes in the logic or other adjustments found to be incorrect by JEA.

Narratives

Baseline Schedule Narrative

The Baseline Schedule narrative shall demonstrate a feasible approach to achieving or improving the planned schedule and contains the following information:

- Identification of the Data Date and schedule file name.

- A description of the planned flow of work, identifying all key or driving resources. Identify key constraints and potential problems influencing the Company’s approach to the work. Describe all construction interfaces with third parties at the Project site. Also identify temporary Company plants, facilities or fixed equipment that the Company or subcontractor plan to use within the right-of-way. Include in this discussion the length of time the plant is to be used, any planned moves, and any potential conflicts that could arise, if the plan is not adhered to.

- A summary of planned labor utilization for the Contract, identifying the average and maximum number of workers on site each month based on the resource loaded Project Schedules. Identify actual and potential labor resource limitations. A summary of planned equipment utilization for the Contract, identifying each type of operated equipment to be used on the Work, the planned quantity of each type of operated equipment utilized each month, and the criteria for mobilizing and demobilizing each piece of equipment to and from the site. Identify actual and potential equipment resource limitations.

- An explanation of how adverse weather conditions have been addressed in the Baseline Schedule. Identify all activities, if any, that contain contingency days for adverse weather conditions and the duration of such contingency included for each.

- An explanation of special calendars that only allow work to take place during a pre-defined window of time.

- The narrative shall address the Company’s material procurement plan and identify the strategy for any long lead item(s). There shall be no fabrication and delivery activities for concrete and asphalt concrete. Fabrication and delivery activities for short lead-time items shall not be included in the project schedules. “Short lead-time" shall be defined as a period of two weeks or less from placement of order to delivery of material to the Project site.

Schedule Progress Update Narrative

All Schedule Progress Update submittals shall include sections containing the following information:

- Header: Identification of the project name, the update period, the Data Date, and the schedule file name.

- Progress Narrative: A summary of the progress key activities including delays and completions.

- Tabular Period Performance Summary: a table of key contract and internal milestone dates showing baseline, prior update and current forecast columns and their variances.

- Period Progress & Impact on Remaining Work: A summary of work completed or not completed, and the effect on remaining work including:

  - A summary of planned labor utilization for the Contract, identifying the average and maximum number of workers on site each month. Identify actual and potential labor resource limitations. A summary of the actual labor utilization used over the past month.

  - A summary of planned equipment utilization for the Project, identifying each type of operated equipment to be used on the Work, the planned quantity of each type of operated equipment utilized each month, and all changes to the criteria for mobilizing and demobilizing each piece of equipment to and from the Project site. Identify actual and potential equipment resource problems. A summary of the actual equipment utilized over the past month.

- Critical & Near Critical Path Performance: Identification of activities with critical or near critical float (within 14 Days of the Critical Path) that were planned to occur during the update period, of which did not occur or occurred later than the scheduled Early Start or Early Finish date, and an explanation of these delays. Provide a listing of all activities that may overrun or have overrun their planned duration by more than 20 percent and any justification for maintaining original planned durations for future activities of like Work.

- Material & Equipment Procurement Issues: Identification of delays occurring to activities taking place off the Project site, e.g., submittal preparation, fabrication, and delivery activities.

- Progress Delays & Schedule Impacts: A summary of current or potential delays occurring in the reporting month and their associated recovery plans and/or time impact analyses.

- Changes from the Previous Update: Revisions to logic or duration(s) by the Company to effectively use labor and resources that have no adverse effect on Completion Deadlines or Contract Price shall be detailed in the update. These revisions shall contain the following information:

  - Identification of the activities changed.

  - A description of the scope of the logic change and identification of the advantages and disadvantages of implementing the change.

  - Identification of all driving resources, if any.

- Identification of key constraints influencing the Company’s approach to the Work.Progress Relative to the Baseline: A comparison of key activities and their current schedule compared to the baseline.

- Other: A summary of other items such as usage of risk register days, usage of weather days, etc.

- Schedules: Following the items above, shall be a pdf of schedules showing layouts to be provided. Those will include schedule by:

  - WBS including the baseline bars/milestones showing on Gantt chart

  - Critical Path

  - Cost Report

Required Submittal and Delivery Activities

Submittal List

The Company shall submit a list of all submittals required by the Contract, as part of Step 2 no later than the deadline identified in Table 1.

The submittal list shall conform to the following format or any other format approved by JEA:

| Submittal List |  |  |
| --- | --- | --- |
| Submittal Reference Number | Description of Submittal | Activity ID |

Table 2 Submittal List Format

3.9.2	Submittal Activities

Submittal activities shall be included in the Project Schedules in a manner consistent with the level of detail shown below:

| Activity | Abbreviation in Activity Description |
| --- | --- |
| Prepare and Submit | P/S |
| Review and Approve | R/A |
| Revise and Re-submit | R/R |
| Fabricate and Deliver (Material or Equipment) | F/D or FAB or DEL |

Table 3 Submittal Activity Detail

Submittals with Multiple Activities

When multiple items are included in a single submittal, that submittal shall be represented in the schedule by an activity in accordance with the following conditions:

- The “Review and Approve" activity for that submittal shall be a predecessor to every activity representing the fabrication and delivery of any of the materials submitted.

- If the submittal is returned and the disposition is sufficient to enable the commencement of a successor activity, then the original submittal activity shall be broken down into multiple activities, as necessary, to accurately reflect the logic of the Company's current plan.

- As part of the monthly update procedure, submittal activities shall be reviewed and modified to ensure that the scope and logic of the activities are consistent with the Company’s current plan.

Delivery Activities

Activities representing the delivery of materials or equipment for more than one installation activity will be permitted in accordance with the following conditions:

- The material delivery activity shall be a predecessor to the first activity representing the installation of that material in each area;

- When partial deliveries are received and those deliveries are adequate to enable the commencement of some, but not all, successor activities, then the original delivery activity shall be broken down into multiple activities, as necessary to accurately reflect the logic of the Company’s current plan;

- As part of the monthly update procedure, a discussion of delivery activities shall be reviewed and modified to ensure that the scope and logic of delivery activities are consistent with the Company’s current plan; and

- There shall be no fabrication and delivery activities for concrete and asphalt concrete. Fabrication and delivery activities for short lead-time items shall not be included in the project Schedules. “Short-lead time" shall be defined as a period of two weeks or less from placement of order to delivery of material to the Project site.

Timely Completion

Unless otherwise specified, timely completion shall refer to completion on or before a date that supports the Completion Deadlines.

Use of Constraints or Float Suppression Techniques

Any use of constraints within the schedule shall be documented in the schedule narrative. The only instance where a constraint may be used is a Finish on or Before constraint on Contract Milestones. Any other use of constraints is prohibited. This includes the following: Start On, Mandatory Start or Finish. The use of negative lags or the use of any other float suppression techniques is also prohibited from use in the project schedules.

Resource Leveling

In schedule submittals to JEA the Company shall not use restraints or constraints to optimize and/or level manpower and equipment requirements. Activities shall be duration and logic driven.

Default Progress Data

Actual Start and Finish dates shall not be automatically updated by default mechanisms that may be included in the CPM scheduling software systems.

Out-of-Sequence Logic

The Company shall correct all incorrect logic relationships in the schedule update to eliminate any out-of-sequence logic. The Company shall make all changes in the logic or other adjustments found to be incorrect by JEA.

Electronic Schedule Naming and Formatting

JEA will provide guidance on schedule name designation to be used. The Company shall not submit any two schedules with the same file name.

Electronic Project Schedule Files

Electronic schedule files shall be in “.xer” format compatible with Oracle Primavera P6. Electronic narrative files shall be in readable PDF format (not scanned).

Printed Project Schedules

PDF or printed schedules shall be no larger than 11”x17” in landscape format and no more than one page wide. PDF or printed schedules should show Activity ID, Activity Name, Original Duration, Remaining Duration, Start, Finish and Total Float columns. The Gantt Chart shall show bars for Actual Work, Remaining Work, Critical Remaining Work, Current Bar Labels, Milestones, Project Baseline and Baseline Milestone. The Data Date line shall also be displayed on the Gantt Chart.

The header of PDF or printed schedules shall contain the project name, the run date and the data date at a minimum. The footer shall contain a Gantt Chart legend, page number, total pages number and active filters at a minimum.

Schedule Progress Updates

The Company shall update the Current Baseline Schedule in the form of a Schedule Progress Update on a monthly basis for the duration of the Contract. This shall not constitute a modification of the Current Baseline Schedule. The purpose of Schedule Progress Updates shall be to accurately document the progress of the Work to-date and to correct the schedule to accurately reflect the Company’s current plan for the timely completion of the Work. Schedule Progress Updates shall be used to record progress for payment purposes and to reflect how the Work is being performed.

Schedule Progress Updates shall never be used as the basis for any adjustment in the Completion Deadlines. Any acceptance of the Schedule Progress Update by JEA, either expressed or implied, shall only apply to the issue of progress and not to any issue of acceptability or accuracy of the Schedule Progress Update for use as a basis for measuring adjustments in Completion Deadlines. The Schedule Progress Update submittal shall be due with Company’s invoice for payment, and shall be a prerequisite to payment by JEA.

Monthly Schedule Progress Update Period

A monthly Schedule Progress Update of the Current Baseline Schedule shall be submitted for each calendar month from the date of the NTP through the date of Final Acceptance. The Data Date of each monthly Schedule Progress Update shall be coordinated with the JEA Project Manager but is typically one of three options:

- The last calendar day of the month, meaning that the progress of the Work to date shall be documented and progressed through the last day of the month; or

- The last day of the pay application billing period so that schedule progress and billing are in alignment; or

- The day of monthly progress meetings where the Company will supply the updated monthly schedule.

Monthly Schedule Progress Update Data

A joint monthly schedule update meeting shall be held in conjunction with the construction progress update meeting. The purpose of this meeting is to review and discuss the contents of the most recent Schedule Progress Update submittal. The JEA review period for the monthly Schedule Progress Update data submittal is 10 working days. The Schedule Progress Update data submittal shall consist of the following submittal components:

- A schedule narrative consistent with Section 3.8.2 above;

- Electronic files with record schedule incorporating all submitted Schedule Update Data (PUXXX);

- The actual progress achieved on each operation and its effect upon the timing of the remaining work;

- All required documentation required under the Contract in support of the invoice;

- A comparison report showing all changes made to the schedule since the last Schedule Update;

- Production curves showing the approved baseline production (planned) values and the actual production values; and

- Should any Work be conducted on a time and materials basis then this update shall contain all necessary data to record progress;

In the event of discrepancies between the submitted data and JEA’s records of progress, JEA’s records shall govern. JEA’s decision shall be final regarding all Schedule Progress Update data. The submittal of incomplete, illegible, or unchecked data or of reports that do not conform to the requirements of this specification may result in the rejection of Schedule Progress Update data, and as such will require a revision and re-submittal.

SUBMITTAL TO JEA OF THE COMPANY’S MONTHLY SCHEDULE PROGRESS UPDATE IS A CONDITION PRECEDENT FOR PAYMENT TO BE INITIATED.

Acceptance of the Schedule Progress Update shall not relieve the Company of its obligation to make appropriate corrections to all of the Project Schedules.

JEA shall not be liable for delays to the Company’s Work that occur during a time when the Company has failed to provide a Schedule Progress Update in accordance with the requirements of the Contract, when having the Schedule Progress Update at the specified time could have influenced JEA’s decisions or actions.

The Schedule Progress Update submittal shall reflect updated progress to the Data Date, forecasted finish for in-progress activities, and re-forecasted Early Dates and Late Dates for remaining activities. The Company shall submit any changes in activity durations, logic ties or constraints for review and acceptance by JEA prior to inclusion of the change into the current Schedule Progress Update. JEA may also submit changes to the Company for inclusion in the current Schedule Progress Update. These changes should be forwarded to the Company for review prior to the monthly construction progress meeting for discussion in that meeting.

Progress Delays

The Company shall identify and promptly report to JEA as soon as they become aware of any matter that could:

- Increase the project budgeted cost or Contract Price,

- Delay the Substantial Completion Deadline,

- Delay meeting a key date or Interim Contract Milestone (if applicable),

- Impair the performance of the work in progress,

- Affect the work of JEA or third parties.

The Company shall promptly develop a schedule recovery or mitigation plan whenever the Company’s actual physical progress is behind schedule by thirty (30) days when compared to the Current Baseline Schedule or could potentially be delayed by thirty (30) days, or within ten (10) days of a written request by JEA. The Company shall submit a schedule recovery or mitigation plan in the form of a Proposed Schedule, whenever the Project Schedule becomes thirty (30) or more Days late to Substantial Completion. The submission of the recovery or mitigation plan shall be at no cost to JEA and shall be submitted within thirty (30) days of the submittal of the Schedule Progress Update that indicates the Project is thirty (30) or more Days late or at JEA’s request. Failure to submit such a recovery plan within the stated timeframe shall provide a basis for future withholdings for payment, either in whole, or in part, by JEA.

Monthly Progress and Invoice Procedure

On a monthly basis, prior to formal submittal of the monthly invoice, the Company shall confirm with JEA the percent complete of work performed prior to submitting the invoice, including the following:

- Activity percent completes, which are based on physical percent complete estimated by the field personnel relating to a resource and cost loaded schedule activity. To streamline this process, earning rules will be established to detail how various activities are progressed and partially paid. These rules will describe how discrete elements of work are to be measured for the purposes of measuring percent completion and be submitted in conjunction with the resource and cost loaded baseline schedules.

- Incorporation of approved Change Orders as individual activities with proper title, coding by Change Order number, associated logic, duration, as well as cost/resource loading.

- Verification of any unit price or time and material items.

- Backup documentation for cost reimbursable procurement and Change Order schedule activities.

Revised Baseline Schedules

Any proposed changes and/or revisions to the Current Baseline Schedule approved by JEA pursuant to its review of Change Orders shall be incorporated into the Current Baseline Schedule and submitted as a Revised Baseline Schedule Submittal. A Revised Baseline Schedule Submittal shall be due with the invoice for payment following JEA’s approval of the changes and/or revisions, as submitted in executed Change Orders. The Revised Baseline Schedule shall include a cost distribution for added Work and will be submitted for review and approval by JEA.

Revised Baseline Schedule Submittals shall include a comprehensive listing of all activities added to or deleted from the Current Baseline Schedule as well as a complete listing of all logic and activity relationship changes that have been made. All changes in the schedule must be fully described in an accompanying narrative.  No Revised Baseline Schedule Submittal will be approved unless it satisfies the following:

- Any out-of-sequenced logic is corrected or explained to the satisfaction of JEA;

- Start and Finish dates are verified for accuracy; and

- The schedule accurately reflects the Company’s plan for completing the remaining Work.

Once a Revised Baseline Schedule Submittal is approved by JEA it shall become the Current Baseline Schedule of record (and be used for subsequent Schedule Progress Update Submittals), and shall be referred to by its revision number.

Except as otherwise designated by Change Order, no Revised Baseline Schedule that extends performance beyond a Completion Deadline shall qualify as a Current Baseline Schedule, or schedule of record, allowing it to be used to demonstrate entitlement to an extension in a Completion Deadline. In no case shall a Schedule Progress Update be construed as a Revised Baseline Schedule or schedule of record unless it is specifically submitted and approved as such by JEA pursuant to this section.

Short Term Schedule

Short Term Schedules shall be submitted by the Company upon request from JEA and shall be provided for within the Contract Price. JEA will specify the period the Short Term Schedule shall encompass. The Company shall produce the Short Term Schedule electronically and it will include a Gantt Chart and details of the daily work activities, including multiple shift work, that the Company intends to conduct. The daily activities shall correspond to the Current Baseline Schedule activities but shall be at a greater level of detail. The Company shall be prepared to discuss the Short Term Schedules, in detail, with JEA to coordinate field inspection staffing requirements, scheduling of Work affecting any adjacent work by other utilities or Companys.

The Three Week Look Ahead Schedule is an example of a Short Term Schedule. Three Week Look Ahead Schedules are to be submitted weekly by the Company in addition to the Company’s monthly Schedule Progress updates.

Review, Acceptance and Approval of Project Schedule Submittals

Failure to meet any of the following conditions shall result in the non-acceptance of the schedule submittal:

- The project budgeted cost shall equal the Contract Price;

- The schedule submittal shall show the timely completion of each activity, as well as, reflect all contractual access requirements and limitations of operations specified;

- All activity relationships and date constraints shall comply with the requirements of the Contract Documents; and

- The Submittal shall be complete in accordance with the requirements of this Specification.

If the schedule submittal is returned to the Company with comments, the submittal shall not be considered accepted until all of JEA’s comments are incorporated into the schedule to JEA’s satisfaction. If the comments are not satisfactorily incorporated into the schedule by the Company, the submittal shall be deemed unacceptable by JEA.

It is the Company’s responsibility to ensure that all Project Schedule documents comply with the requirements of the Contract. Errors in any Project Schedule document accepted by JEA, including but not limited to activity durations, relationships between activities, resource allocation or other float suppression techniques that do not accurately reflect the Work, may be identified at any time and once identified, shall be corrected by the Company. JEA is not responsible for any erroneous assumptions or information in any Project Schedule document, regardless of origin.

During the review of any Project Schedule document, if any of the following conditions are discovered, the document may be returned by JEA without further review for correction and re-submittal:

- The document is incomplete.

- The document does not comply with the specified format.

- A component of the document has not been prepared in accordance with the requirements of this section.

- The quality of the document indicates that the Company has failed to perform an internal quality control review prior to submission.

- There is an inconsistency between electronic files and printed material.

- The Company has made unauthorized changes to any Project Schedule document.

- The Company has failed to incorporate JEA comments concerning the Project Schedule document.

JEA’s failure to return a submittal shall not be construed to mean that the submittal complies with the requirements of the Contract. JEA may, at its discretion, choose to complete a review even though the submittal fails to meet one or more of the conditions for rejection stated herein. The Company shall be responsible for all delays due to its failure to submit complete Project Schedule submittals in accordance with the requirements of the Contract.

JEA’s acceptance or approval of a Project Schedule document indicates only that the submittal appears to comply with the requirements of the Contract. It is the Company’s responsibility to ensure that each submittal complies with the requirements of the Contract. Inconsistencies or errors in any Project Schedule document, including but not limited to activity durations, relationships between activities, resource allocation or other float suppression techniques that do not accurately reflect the Work, may be identified at any time and once identified, shall be immediately corrected by the Company.

JEA shall review schedule submittals for conformance with the requirements of the Contract. Review comments by JEA may address whether items of Work are omitted, activity durations are reasonable or that the level of labor, materials, and equipment, the means, methods, timing and sequencing of the Work are practical. The planning, scheduling or execution of the Work and the accuracy of any Project Schedule shall remain the sole responsibility of the Company.

Notwithstanding any review, review comments, approval, acceptance, scheduling assistance or direction to change and/or revise any Project Schedule by JEA the Project Schedules shall at all times be the Company’s schedule for performing the Work and not be considered as any JEA direction constituting a change. The Company shall not be relieved from completing the Work within the Completion Deadlines due to the failure of the Company to submit acceptable Project Schedule documents.

Requirements for Demonstrating Entitlement to an Adjustment in the Contract Time or Obtaining Approval of a Plan to Recover Delay

Schedule Analysis Requirements

The Company shall develop and submit a time impact analysis and a Proposed Schedule when one or more of the following conditions occur:

- The Company’s plan for the Work as reflected in the Current Baseline Schedule is materially changed;

- JEA has approved a Change Order that affects the Critical Path of the Work necessitating an adjustment in a Completion Deadline;

- The Company’s progress on the Work is behind the Substantial Completion date by thirty (30) days or more;

- In JEA's opinion, the Current Baseline Schedule no longer accurately reflects the Company’s plan for performing the Work;

- The Company is required by the Contract or chooses to submit a time impact analysis demonstrating entitlement to an adjustment to a Completion Deadline or to submit a plan demonstrating how the Company intends to recover delay; or

- Any allowable change has occurred according to the Contract.

The Company shall use AACEi Recommended Practice 52R-06 Time Impact Analysis – As Applied to Construction when preparing a time impact analysis.

The Company shall submit a time impact analysis and a Proposed Schedule within fourteen (14) days following a request by JEA. This required fourteen (14) day period may be extended as necessary subject to the approval of JEA. The Proposed Schedule shall be developed using duplicate electronic files of the Current Baseline Schedule and shall include all status’ to reflect current progress using information from agreed to Schedule Progress Updates, but shall not allocate costs to any proposed activities. Multiple delays will be analyzed chronologically in the order of occurrence. Costs may be allocated to activities only when the Change Order Proposal has been approved by JEA. Under no circumstances shall a time impact analysis based on Schedule Progress Update(s) be acceptable as a basis for an adjustment to a Completion Deadline.

Proposed Schedules shall be used by the Company to:

- Request revisions to logic ties and activities in the Current Baseline Schedule,

- Propose changes in the Current Baseline Schedule required to implement schedule recovery plans,

- To negotiate the schedule impact of a Change Order Proposal with JEA, or

- To propose changes for any other reason in the Current Baseline Schedule.

Proposed Schedules shall code affected and added activities to each Change Order Proposal or schedule recovery plan. Furthermore, Proposed Schedules shall accurately reflect all revisions and/or adjustments made to activities, logic ties and restraints that are necessary to reflect the Company’s current approach for Work remaining. At a minimum, Proposed Schedules shall:

- Incorporate all proposed activities and logic ties required to implement any proposed revisions,

- Detail all impacts on pre-existing activities and logic ties,

- Include a narrative describing the causes of any delay and actions planned to recover the schedule to meet Contract Deadlines.

Each Proposed Schedule shall include a subnet demonstrating how the Company plans to incorporate a Change Order Proposal or other change and/or revision into the Current Baseline Schedule. A subnet is defined as a sequence of new or revised activities that are proposed to be added to the Current Baseline Schedule.

Notwithstanding any other provision or provisions to the contrary, the Company shall have no claim for damages of any kind, or extension or increase to a Completion Deadline, or adjustment of Contract Price, on account of any delay, interruption or suspension of the Work or any portion thereof (herein after collectively referred to as “Delay"), due to whatever cause, unless in addition to all other requirements of the Contract Documents the prerequisites of this section are strictly complied with.

If the Company does not submit a time impact analysis for a specific change order or delay within the specified period, the Company shall be deemed to have irrevocably waived any rights to additional time and cost.

Mitigation of Delays

The Company shall be responsible to develop mitigation measures for all delays, regardless of responsibility for the delays, and to identify all time and cost impacts to the Work associated with those mitigation measures. Unless circumstances otherwise require, the Company shall not pursue mitigation action for which it expects JEA to be liable, prior to notifying JEA and receiving JEA authorization to proceed with the mitigation action.

All Company proposals for mitigation action, including proposed revisions for timely completion, shall confirm that the Company has verified the accuracy of all critical paths to the Substantial Completion Deadline.

Whenever it is possible for the Company to mitigate delay without added cost, the Company shall do so.   The Company shall mitigate all delays as efficiently and economically as possible, with the objective of minimizing both the time and cost impact of the delay, regardless of responsibility for the delay. JEA will not be liable for damages that the Company could have avoided by reasonable means, such as prudent scheduling of the Work and judicious handling of forces, equipment, or materials.