## Ckt 690
Schedule of Values for Ckt 690
Scope | # | ITEM DESCRIPTION | UOM | Quantity | Unit Price | Extended Price
Mob / Demob / Bond | 1 | 1.1 MOBILIZATION | Lump Sum | 1 |  | 0
| 2 | 1.2 DEMOBILIZATION | Lump Sum | 1 |  | 0
| 3 | 1.3 BID BOND | Lump Sum | 1 |  | 0
Site Preparation | 4 | 2.1 SURVEYING - LAYOUT PROPOSED BORE PATH | Lump Sum | 1 |  | 0
| 5 | 2.2 SURVEYING - STAKE EXTENTS OF EXCAVATION | Lump Sum | 1 |  | 0
| 6 | 2.3 SURVEYING - STAKE BOUNDARIES OF PERMANENT AND TEMPORARY EASEMENTS | Lump Sum | 1 |  | 0
Transmission Structures, Cable and Ductbank Installation / removal | 7 | 3.1 TRANSPORTATION OF JEA PLATING MATERIALS TO JOB SITE | Lump Sum | 1 |  | 0
| 8 | 3.2 RETURN UNUSED JEA MATERIALS | Lump Sum | 1 |  | 0
| 9 | 3.3 RECEIVE, UNLOAD AND SPOT STRUCTURES AND ASSOCIATED HARDWARE | Lump Sum | 1 |  | 0
| 10 | 3.4 INSTALLATION OF GROUND ROD ADD GROUND WIRE ON POLE | Lump Sum | 1 |  | 0
| 11 | 3.5 HORIZONTAL DIRECTIONAL DRILL OF (4) 6" AND (1) 2" CONDUITS | Lump Sum | 1 |  | 0
| 12 | 3.6 TRENCH INSTALLATION OF (4) 6" AND (1) 2" CONDUITS | Lump Sum | 1 |  | 0
| 13 | 3.7 DEMOLITION OF EXISTING CONCRETE CAP AND CABLES | Lump Sum | 1 |  | 0
| 14 | 3.8 MATERIAL COST OF 2000KCMIL CABLE PLUS SHIPPING TO SITE | Lump Sum | 1200 |  | 0
| 15 | 3.9 INSTALLATION OF 2000KCMIL CABLE AND GROUND CONTINUITY CABLE | Lump Sum | 1 |  | 0
| 16 | 3.10 FRAME POLE RISER INCLUDING INSTALLATION TERMINATORS AND ARRASTORS | Lump Sum | 1 |  | 0
| 17 | 3.11 FRAME SUBSTATION RISER INCLUDING INSTALLATION TERMINATORS AND ARRASTORS | Lump Sum | 1 |  | 0
| 18 | 3.12 BUILD JUMPERS | Lump Sum | 1 |  | 0
| 19 | 3.13 PROVIDE AND INSTALL CABLE GUARD | Lump Sum | 1 |  | 0
| 20 | 3.14 DEWATERING | Lump Sum | 1 |  | 0
| 21 | 3.15 CABLE VLF TESTING | Lump Sum | 1 |  | 0
| 22 | 3.16 MATERIAL COST OF TERMINATORS | Lump Sum | 1 |  | 0
Miscellaneous | 23 | 4.1 RESTORATION | Lump Sum | 1 |  | 0
| 24 | 4.2 AS-BUILT DRAWINGS | Lump Sum | 1 |  | 0
| 25 | 4.3 SILT FENCE, EROSION AND SEDIMENT CONTROL ASSEMBLY, INSTALLATION, AND REMOVAL | Lump Sum | 1 |  | 0
| 26 | 4.4 ADDITIONAL GROUND RODS (FOR EACH ADDITIONAL GROUND ROD, REQUIRED OVER THE BASE SCOPE OF THREE (3)) | Per Rod | 5 |  | 0
| 27 | 4.5 MOT TO BE USED FOR ALL MOT ON ALL ROADS | Lump Sum | 1 |  | 0
Subtotal Line 1 - 27 Above | [5 empty] | 0
SWA (10% of Subtotal) | [5 empty] | 0
Total Bid Price (Enter this amount on line 1 of the Bid Form) | [5 empty] | 0

## Ckt 693
Schedule of Values for Ckt 693
Scope | # | ITEM DESCRIPTION | UOM | Quantity | Unit Price | Extended Price
Mob / Demob / Bond | 1 | 1.1 MOBILIZATION | Lump Sum | 1 |  | 0
| 2 | 1.2 DEMOBILIZATION | Lump Sum | 1 |  | 0
| 3 | 1.3 BID BOND | Lump Sum | 1 |  | 0
Site Preparation | 4 | 2.1 SURVEYING - LAYOUT PROPOSED BORE PATH | Lump Sum | 1 |  | 0
| 5 | 2.2 SURVEYING - STAKE EXTENTS OF EXCAVATION | Lump Sum | 1 |  | 0
| 6 | 2.3 SURVEYING - STAKE BOUNDARIES OF PERMANENT AND TEMPORARY EASEMENTS | Lump Sum | 1 |  | 0
Transmission Structures, Cable and Ductbank Installation / removal | 7 | 3.1 TRANSPORTATION OF JEA PLATING MATERIALS TO JOB SITE | Lump Sum | 1 |  | 0
| 8 | 3.2 RETURN UNUSED JEA MATERIALS | Lump Sum | 1 |  | 0
| 9 | 3.3 RECEIVE, UNLOAD AND SPOT STRUCTURES AND ASSOCIATED HARDWARE | Lump Sum | 1 |  | 0
| 10 | 3.4 INSTALLATION OF GROUND ROD ADD GROUND WIRE ON POLE | Lump Sum | 1 |  | 0
| 11 | 3.5 HORIZONTAL DIRECTIONAL DRILL OF (4) 6" AND (1) 2" CONDUITS | Lump Sum | 1 |  | 0
| 12 | 3.6 TRENCH INSTALLATION OF (4) 6" AND (1) 2" CONDUITS | Lump Sum | 1 |  | 0
| 13 | 3.7 DEMOLITION OF EXISTING CONCRETE CAP AND CABLES | Lump Sum | 1 |  | 0
| 14 | 3.8 MATERIAL COST OF 2000KCMIL CABLE PLUS SHIPPING TO SITE | Lump Sum | 1800 |  | 0
| 15 | 3.9 INSTALLATION OF 2000KCMIL CABLE AND GROUND CONTINUITY CABLE | Lump Sum | 1 |  | 0
| 16 | 3.10 FRAME POLE RISER INCLUDING INSTALLATION TERMINATORS AND ARRASTORS | Lump Sum | 1 |  | 0
| 17 | 3.11 FRAME SUBSTATION RISER INCLUDING INSTALLATION TERMINATORS AND ARRASTORS | Lump Sum | 1 |  | 0
| 18 | 3.12 BUILD JUMPERS | Lump Sum | 1 |  | 0
| 19 | 3.13 PROVIDE AND INSTALL CABLE GUARD | Lump Sum | 1 |  | 0
| 20 | 3.14 DEWATERING | Lump Sum | 1 |  | 0
| 21 | 3.15 CABLE VLF TESTING | Lump Sum | 1 |  | 0
| 22 | 3.16 MATERIAL COST OF TERMINATORS | Lump Sum | 1 |  | 0
Miscellaneous | 23 | 4.1 RESTORATION | Lump Sum | 1 |  | 0
| 24 | 4.2 AS-BUILT DRAWINGS | Lump Sum | 1 |  | 0
| 25 | 4.3 SILT FENCE, EROSION AND SEDIMENT CONTROL ASSEMBLY, INSTALLATION, AND REMOVAL | Lump Sum | 1 |  | 0
| 26 | 4.4 ADDITIONAL GROUND RODS (FOR EACH ADDITIONAL GROUND ROD, REQUIRED OVER THE BASE SCOPE OF three (3)) | Per Rod | 5 |  | 0
| 27 | 4.5 MOT TO BE USED FOR ALL MOT ON ALL ROADS | Lump Sum | 1 |  | 0
Subtotal Line 1 - 27 Above | [5 empty] | 0
SWA (10% of Subtotal) | [5 empty] | 0
Total Bid Price (Enter this amount on line 1 of the Bid Form) | [5 empty] | 0