## SOV
MILLER SUBSTATION - SCHEDULE OF VALUES
|  | Schedule |  | % Complete |  | Amount Earned to Date |  |  | Previously | Due This
Item | Description | Labor | Material | Labor | Material | Labor | Material | Total | Billed | Period
1 | Mobilization / Administration
1.1 | Project Administration |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
1.2 | Performance and Payment Bond |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
1.3 | Mobilization / Field Trailer Setup |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
1.4 | Temporary Services (e.g. Electrical) |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
1.5 | Survey / Establish Baselines |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
1.6 | As-Builts |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2 | Civil Site Work
Grading & Site Development
2.1 | Mirafi 140-N |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.2 | Herbicide |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
Foundations
2.3 | 230kV Bus & Equipment Drilled Shafts |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.4 | 230kV A-Frame Drilled Shafts |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.5 | 230kV Breaker Slabs |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.6 | Control Enclosure Foundation |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.7 | Padmount Transformers (Precast JEA furnish) |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
Testing
2.8 | Concrete |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
Yard Improvements
2.9 | Blue/Gray #5 Limestone Yard Gravel |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.1 | White #5 Limestone Roadway Gravel |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.11 | Base Cellular Confinement Material, Tensar BX-1100 |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.12 | Substation Perimeter Fence and Gates |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
2.13 | Signs on Fence/Gates |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
3 | Raceway
3.1 | Cable Trench System (Pedestrian and Traffic rated) |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
Conduit
3.2 | 1 In. Conduit |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
3.3 | 1.5 In. Conduit |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
3.4 | 2 In. Conduit |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
3.5 | 3 In. Conduit |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
3.6 | 4 In. Conduit |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
3.7 | Flex Conduit |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
4 | General Above Grade
4.1 | Receiving / Off-Loading Substation Packages |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
4.2 | Transportation of Misc. Material and Equipment |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
5 | Structure Erection
5.1 | 230kV Yard Structures |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
5.2 | Probe Poles |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
5.3 | Bollards (PVC) |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
5.4 | Card Reader Supports |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6 | Equipment Installation
230kV Equipment Installation
6.1 | 230kV Insulators, Buswork, Connectors, Fittings, Damper Cable |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.2 | 230kV CCVT's, CT/PT Units, LA's |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.3 | 230kV Switches |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.4 | 230kV Breakers |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.5 | 230kV Cable Jumpers |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.6 | 230kV SSVT's |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
Miscellaneous Yard Equipment
6.7 | Auto Transfer Switch |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.8 | Yard Panels |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.9 | Safety Switches |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.1 | CT Cabinet |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.11 | Meter Socket |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.12 | Yard Receptacles |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.13 | Junction Boxes |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.14 | Handholes |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
Yard Lighting
6.14 | H-Frame Lights |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.15 | Probe Pole Lights |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.16 | Security Pole Lights |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
6.17 | Light Pole Lights |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7 | Power and Control Cable
Cable Install, SEE CABLE SCH. FOR DETAILS
7.1 | 21C#10 Type BS |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.2 | 8C#10 Type BS |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.3 | 4C#10 Type BS |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.4 | 3C#10 Type C |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.5 | 2C#10 Type C |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.6 | 4C#4 Type C |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.7 | 3C#4 Type C |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.8 | 3C#6 Type C |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.9 | 300/350 Type C |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
Cable Terminations
7.1 | Terminate AC Cabling |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.11 | Terminate DC Cabling |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
7.12 | Terminate Control Cabling, Instrument Cable & misc. |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8 | Grounding
8.1 | 19#8 Copperweld Main Grid |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.2 | 7#5 Copperweld Taps |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.3 | Cadweld Connections |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.4 | Ground Rods |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.5 | Fence and Gate Grounding |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.6 | Cable Trench Grounding |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.7 | Control Enclosure Grounding |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.8 | 230kV Equipment Grounding |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.9 | Switch Grounding Mats |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.1 | Bollard/Card Reader Stand Grounding |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
8.11 | Cabinet/J.Box Grounding |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
9 | Fiber Optic Ductbank
9.1 | Fiber Optic Conduit, Innerduct & Manholes |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
9.2 | Misc. Fiber Materials (Markers, tape, etc.) |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
10 | Facility Security Infrastructure
10.1 | Security Poles |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
10.2 | Conduit & Handholes |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
10.3 | Security Cabinets |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
10.4 | Receptacles |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
10.5 | Junction Boxes |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
11 | Testing
11.1 | Ground Rod Measurements |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
12 | Miscellaneous (Contractor to Add/Specify as needed)
|  |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
|  |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
|  |  |  | 0% | 0% | 0 | 0 | 0 | 0 | 0
| Totals: | 0 | 0 | 0% | 0% | 0 | 0 | 0 | 0 | 0