ENGINEERING, PROCUREMENT AND CONSTRUCTION AGREEMENT

BETWEEN

JEA

AND

[CONTRACTOR]

FOR THE

ST. Johns River Power Park (SJRPP)

UNIT 3 COMBINED CYCLE PROJECT

TABLE OF CONTENTS

Article 1 Definitions and Interpretation	1

1.1	Defined Terms.	1

1.2	Standards of Interpretation.	13

Article 2 Contractor’s Work and Other Obligations	13

2.1	Commencement of the Work.	13

2.2.	Work to be Performed.	14

2.2	Baseline Project Schedule, Progress Reports and Meetings; Recovery Plan.	38

2.3	Standards of Performance.	39

2.4	Transfer of Title/Risk of Loss.	40

2.5	Site Conditions.	41

2.6	Nature of the Work.	43

2.7	Subcontractors.	43

2.8	Insurance.	45

2.9	Provision of Information; Cooperation.	46

2.10	Storm Water Pollution Prevention Plan.	46

Article 3 JEA Obligations	47

3.1	Facility Real Estate Rights and Access to Facility Site.	47

3.2	JEA Permits.	47

3.3	JEA Furnished Equipment.	48

3.4	JEA’s Insurance.	48

3.5	Florida Sales and Use Taxes.	48

3.6	Construction Utilities; Backfeed Power; Fuel.	48

3.7	JEA Operators.	48

3.8	JEA’s Engineer.	48

3.9	Other Obligations.	49

Article 4 JEA’s Right To Inspect, Stop and Re-Perform Work	49

4.1	Inspection and Re-Performance.	49

4.2	Right to Stop Work for Cause.	49

4.3	Uncovering Construction Work.	49

4.4	Right to Suspend Work for Convenience.	50

Article 5 Price and Payment	50

5.1	Contract Price.	50

5.2	Milestone Payments.	50

5.3	Application for Payment; Payment of Invoices.	50

5.4	Conditions of Payments; Withholdings, Set-Offs, Retention.	52

5.5	Right to Audit and Financial Reporting.	54

5.6	Payment or Use Not Acceptance.	55

5.7	Cost-Savings Plan.	55

Article 6 STAGES OF Completion of the Work	55

6.1	Ready for First Fire; Ready for Full Steam Admission.	55

6.2	Mechanical Completion.	57

6.3	Substantial Completion.	59

6.4	Creation of Punch-List.	61

6.5	Transfer of Responsibility to JEA.	62

6.6	Final Completion.	62

Article 7 Performance TESTING and Guarantees	64

7.1	Notices and Preparations for Commencement of Testing.	64

7.2	BOP Performance Testing.	64

7.3	Re-Setting of Equipment.	65

7.4	Power Island Equipment Testing.	65

7.5	Reliability Testing.	66

7.6	Pre-Substantial Completion Remedial Plan.	66

7.7	Output During Testing.	66

7.8	BOP Performance Guarantees; Performance Liquidated Damages.	66

Article 8 Contractor’s Warranties	68

8.1	Warranties.	68

8.2	Warranty Period.	68

8.3	Repair of Defects.	68

8.4	Warranty Period Extension.	69

8.5	Warranty of Title.	69

8.6	Limitation on Warranties.	69

8.7	Exclusive Warranties.	69

Article 9 Changes	70

9.1	Changes.	70

9.2	Procedure for Changes.	70

9.3	Permitted Change Orders.	71

9.4	Changes Involving Schedule Extensions.	72

9.5	Changes to the Contract Price.	73

9.6	Continued Performance Pending Resolution of Disputes.	74

9.7	JEA’s Right to Offset Changes.	74

9.8	Final Resolution.	75

Article 10 Force Majeure	75

10.1	Force Majeure Event.	75

10.2	Burden of Proof.	76

10.3	Excused Performance.	76

Article 11 Indemnification	76

11.1	Contractor’s Indemnity.	76

11.2	JEA Indemnification.	77

11.3	Environmental Indemnity.	78

11.4	Indemnification in Design Professional Contracts.	78

11.5	Notice and Legal Defense.	78

11.6	Failure to Defend Action.	79

11.7	Additional Intellectual Property Obligations.	79

11.8	No Waiver of Sovereign Immunity.	79

11.9	Survival.	79

Article 12 Termination and Suspension Rights	80

12.1	JEA Termination for Convenience.	80

12.2	JEA Termination Upon Contractor Event of Default.	81

12.3	Actions Upon Termination.	82

12.4	Consequences of Termination for Contractor Default.	83

12.5	Suspension of Work upon Non-Payment by JEA.	83

12.6	JEA Default.	83

12.7	Consequences of Termination for JEA Default.	84

12.8	Surviving Obligations.	84

Article 13 Securities	84

13.1	Payment Bond.	84

13.2	Performance Bond.	85

Article 14 Representations and Warranties	85

14.1	Representations and Warranties of Contractor.	85

14.2	Representation and Warranties of JEA.	86

Article 15 Limitations of Liability	86

15.1	Aggregate Cap on Liquidated Damages.	86

15.2	Aggregate Limitation.	86

15.3	Consequential Damages.	87

Article 16 Dispute Resolution	87

16.1	Applicability of Resolution Procedures.	87

16.2	Management Discussions.	87

16.3	Choice of Forum.	87

16.4	Obligations Continue.	88

16.5	Injunctive or Equitable Relief.	88

16.6	Survival.	88

Article 17 Non-Disclosure and Non-Use Covenants	88

17.1	Confidential Information.	88

17.2	Restrictions.	88

17.3	Public Records.	90

17.4	Remedies and Interpretation.	92

Article 18 Miscellaneous	92

18.1	Governing Documents.	92

18.2	Project Managers.	92

18.3	Assignment/Delegation.	93

18.4	Reviews, Inspections, Approvals by JEA.	93

18.5	Governing Law.	94

18.6	Severability.	94

18.7	Notices.	94

18.8	Article and Section Headings.	95

18.9	No Waiver of Rights.	95

18.10	Entire Agreement.	95

18.11	Amendments.	95

18.12	No Third-Party Rights.	95

18.13	JEA’s Obligations Non-recourse.	95

18.14	Relationship of the Parties.	95

18.15	Further Assurances.	95

18.16	Counterparts; Facsimile Signatures.	96

List of Exhibits

Exhibit A-1:	Essential Form

Exhibit A-2: 	Technical Specifications

Exhibit B:	Baseline Project Schedule

Exhibit C:	Scheduling Specification

Exhibit D: 	Milestone Payment Schedule

Exhibit E:	Monthly Progress Report

Exhibit F: 	Insurance Requirements

Exhibit G: 	Permits

Exhibit H:	Key Personnel

Exhibit I: 	JEA Contractor Travel Policy

Exhibit J: 	Acceptable Subcontractors

Exhibit K-1:	Form of Certificate of Ready for First Fire

Exhibit K-2:	Form of Certificate of Ready for Full Steam Admission

Exhibit K-3:	Form of Certificate of Mechanical Completion

Exhibit K-4:	Form of Certificate of Substantial Completion

Exhibit K-5:	Form of Certificate of Final Completion

Exhibit L-1:	Facility Site (ALTA Survey)

Exhibit L-2:	Existing Conditions

Exhibit M: 	Form of Change Order

Exhibit N-1: 	Form of Conditional Lien Release Upon Progress Payment

Exhibit N-2: 	Form of Unconditional Lien Release Upon Final Payment

Exhibit O: 	Contractor Rate Sheet

Exhibit P:	Human Trafficking Affidavit

Exhibit Q-1:	Form of Payment Bond

Exhibit Q-2: 	Form of Performance Bond

Exhibit R:	Care of JEA Customers

Exhibit S:	Required Federal Contract Clauses

Exhibit T:	PIE Purchase Agreement

Exhibit U: 	GSU Transformer Purchase Agreement1

Exhibit V: 	UAT Transformer Purchase Agreement1

ENGINEERING, PROCUREMENT AND CONSTRUCTION AGREEMENT

THIS ENGINEERING, PROCUREMENT AND CONSTRUCTION AGREEMENT (this “Agreement”) is entered into as of [   ] (the “Effective Date”), by and between JEA, a body politic and corporate and corporate existing under the laws of the State of Florida, having its principal offices at 225 North Pearl Street, Jacksonville, Florida 32202 (“JEA”) and [CONTRACTOR], a [_____], having its principal offices at [_____] (“Contractor”).  JEA and Contractor are sometimes individually referred to herein as a “Party” and collectively as the “Parties.”

W I T N E S S E T H:

WHEREAS, JEA is developing a an approximately 640 MW net dual fuel power generation facility (as further described and defined herein as the “Facility”) at Saint Johns River Power Park, Jacksonville, Florida, and desires to purchase from Contractor certain engineering, design, procurement, construction, assembly, installation, commissioning, start-up, performance testing, and related services in connection with the same;

WHEREAS, Contractor is willing to provide such engineering, design, procurement, construction, assembly, installation, commissioning, start-up, performance testing, and related services upon the terms and subject to the conditions set forth in this Agreement; and

WHEREAS, JEA has entered into the PIE Purchase Agreement with the PIE Supplier, pursuant to which the PIE Supplier will supply and deliver the Power Island Equipment.

NOW, THEREFORE, in consideration of the premises and the mutual covenants and agreements contained herein, and other good and valuable consideration, the receipt and sufficiency of which are hereby acknowledged, the Parties covenant and agree as follows:

Definitions and Interpretation

Defined Terms.

As used in this Agreement, the following terms shall have the following meanings (such meanings as necessary to be equally applicable to both the singular and plural forms of the terms defined unless the context otherwise requires):

“Affected Party” has the meaning set forth in Section 10.1.

“Affiliate” means, with respect to a party or entity, any other entity that controls, is controlled by or is under common control with, such party or entity.  For the purposes of this definition, “control” shall mean the possession, directly or indirectly, of the power to direct or cause the direction of the management and policies of the controlled entity, whether through the ownership of voting securities or partnership or other ownership interests or by Agreement or otherwise.  The terms “controlled” and “controlling” have correlative meanings.

“Agreement” means this Engineering, Procurement and Construction Agreement, including the Terms and Conditions, Exhibits A through T, and all written amendments hereto and thereto.

“Ancillary Site Infrastructure” means the roads, fences, security systems, buildings, structures, and other permanent improvements to the Facility Site to be engineered, designed, procured, assembled, constructed, installed and completed by Contractor as part of the Work, as further described in Exhibit A, that comprise part of the overall Facility but which are not Balance of Plant.

“Anticipated FNTP Date” has the meaning set forth in Section 2.1.2.

“Applicable Codes and Standards” means all engineering, environmental construction, safety, and electrical generation and other codes and standards applicable to the Work, including: (i) the codes and standards set forth in Exhibit A, (ii) the regulations of the National Fire Protection Association (or other such board as shall perform similar function), and (iii) the NERC-CIP Requirements, as may be in effect and/or amended from time to time.

“Applicable Laws” means all laws (including Environmental Laws), statutes, regulations, rules, treaties, ordinances, judgments, directives, Permits, decrees, approvals, interpretations, injunctions, writs, orders (including executive orders) or other similar legal requirements of any Governmental Authority (and including, without limitation, the requirements of NERC), as may be in effect from time to time and as may be amended during the Term, as may be in effect and/or amended from time to time.

“Applicable Permits” means all Permits required to be obtained or maintained in connection with the construction of the Facility on the Facility Site, the performance of the Work or the operation of the Facility or any component thereof.

“Application for Payment” has the meaning set forth in Section 5.3.1.

“Approved QA/QC Manual” has the meaning set forth in Section 2.2.22.

“Assets” has the meaning set forth in Section 2.2.17.5.

“Auxiliary Load Guarantee” has the meaning set forth in Section 7.9.1.

“Balance of Plant Equipment” means all equipment, materials, supplies, hardware, software and other goods that are required for the completion of, and that will be incorporated into and become a part of, the complete Facility in accordance with this Agreement, other than the Power Island Equipment.

“Baseline Project Schedule” means the schedule for the Work that is set forth in Exhibit B.  The Baseline Project Schedule may otherwise only be adjusted per Section 9.4 and Section 7.6.

“BOP Equipment List” means a list of all Balance of Plant Equipment to be incorporated in the Facility, with appropriate unique identification information for each component, as further described in Exhibit A-2.

“BOP Performance Testing Completion Notice” has the meaning set forth in Section 7.2.

“BOP Performance Guarantees” has the meaning set forth in Section 7.9.1.

“BOP Performance Tests” has the meaning set forth in Section 7.2.

“BOP Reliability Guarantee” has the meaning set forth in Section 7.6.

“Business Day” means any Day, except Saturdays, Sundays and holidays when banks in the State of Florida are closed.

“Certificate of Final Completion” has the meaning set forth in Section 6.7.2.

“Certificate of Mechanical Completion” has the meaning set forth in Section 6.2.2.

“Certificate of Substantial Completion” has the meaning set forth in Section 6.4.2.

“Change” has the meaning set forth in Section 9.1.

“Change Directive” has the meaning set forth in Section 9.5.1.1.

“Change in Applicable Codes and Standards” means any amendment, modification, superseding act, deletion, addition or change in or to Applicable Codes and Standards that occurs and takes effect after the Effective Date (but excluding any such changes that as of the Effective Date were publicly announced in writing (including online) by the entity responsible for promulgating the same as coming into effect after the Effective Date) and establishes requirements that adversely affect Contractor's costs or schedule for performing the Work.

“Change of Law” means the enactment, adoption, imposition, promulgation, cancellation, modification or repeal, in each case after the Effective Date of any Applicable Laws of: (i) the State of Florida (or any city, county, or municipality therein) or (ii) the Federal Government of the United States to the extent such federal law directly affects the Work, which, in any such case (i) or (ii), establishes requirements that adversely affect Contractor’s costs or schedule for performing the Work; provided, however, the following shall not constitute a Change of Law for purposes hereof:  (A) the coming into effect of any Applicable Laws after the Effective Date that were enacted prior to the Effective Date; (B) the enactment, adoption, imposition, promulgation, cancellation, modification or repeal of any Applicable Laws regarding taxes imposed on Contractor’s net income; and (C) any change in Applicable Laws increasing worker’s compensation rates, minimum wage wages or prevailing wage rate.

“Change Order” has the meaning set forth in Section 9.1.

“Change Order Notice” has the meaning set forth in Section 9.2.2(a).

“Change Order Request” has the meaning set forth in Section 9.2.1.

“Claims” has the meaning set forth in Section 11.1.

“Balance of Plant” means those portions of the Balance of Plant Equipment and all civil works and foundations supporting such Balance of Plant Equipment.

“Completed BOP Performance Tests” has the meaning set forth in Section 7.2.

“Concurrent Delay” means a period during which: (a) a delay to the Work attributable to an event entitling Contractor to an extension of time as described in Section 9.3; and (b) a delay to the Work for which Contractor is not entitled to an extension of time as described in Section 9.3, overlap and each would have independently caused or contributed to a delay to the Critical Path but for the other.  Such “overlap” of the foregoing delays need not have the same starting or ending times or the same exact durations, so long as the delays occur at the same time for some period.

“Conditions of the Nature of the Work” has the meaning set forth in Section 2.7.

“Confidential Information” has the meaning set forth in Section 17.1.

“Construction Documents” has the meaning set forth in Section 2.2.1.5.

“Contract Documents” has the meaning set forth in Section 18.1.

“Contractor” has the meaning set forth in the preamble to this Agreement.

“Contractor Indemnitees” has the meaning set forth in Section 11.2.

“Contractor Permits” means all those Applicable Permits required to complete the Work, including those designated in Exhibit G as being Contractor’s responsibility.

“Contractor’s Hourly Rates” means, for Work performed by the personnel of Contractor described in Exhibit O, the applicable rates for such personnel as set forth in Exhibit O.  The Parties acknowledge that such rates already include profit and overhead and thus any “cost plus” markup under this Agreement will not apply to such rates.

“Contractor’s Personnel” means the Personnel of Contractor.

“Contractor Event of Default” has the meaning set forth in Section 12.2.

“Contractor Project Manager” has the meaning set forth in Section 2.2.7.3.

“Contractor’s Taxes” has the meaning set forth in Section 2.2.8.

“Contract Price” has the meaning set forth in Section 5.1.

“Critical Path” means the sequence of activities, as originally depicted in the Baseline Project Schedule, and updated in each Monthly Updated Schedule, for the achievement of a Guaranteed Date that is: (a) the path for the achievement of such Guaranteed Date with the lowest float values; and (b) the path upon which any activity, if delayed, will delay achievement of the applicable Guaranteed Date; and (c) the longest path from the current start point to the date of achievement of the applicable Guaranteed Date.

“Cure Period” has the meaning set forth in Section 7.9.3.

“Data Breach” has the meaning set forth in Section 2.2.17.6.

“Day” means a calendar day.

“Delivery Point” has the meaning set forth in Section 2.2.4.4.

“Design Development Documents” has the meaning set forth in Section 2.2.1.4.

“Direct Costs” means only the actual, reasonable additional costs that are incurred (or, in the context of Section 9.5.1.2, are avoided) and that would not but for the applicable event have been incurred, by Contractor in connection with the Work as a result of the Change or, per Section 9.5.2 or Section 9.5.3, the event giving rise to the Change Order (or, in the context of JEA’s payment of the Termination Payment under Section 12.1.1, as result from such termination, including demobilization as described therein) for the following items: (i) the cost of (only) those personnel of Contractor as described in O who demonstrably spend time performing such Work, charged at Contractor’s Hourly Rates (such time to be recorded in increments of tenths of an hour, with appropriately descriptive narratives of the Work performed) (ii) the cost of materials and permanent equipment; (iii) payments properly made by Contractor to Subcontractors; (iv) rental charges for necessary machinery and equipment (but excluding hand tools) not to exceed the applicable rates as stated in the then-current Rental Rate Blue Book by Equipment Watch used at the Facility Site; (v) permit fees; (vi) reasonable costs of mobilization and/or demobilization; and (vii) delivery charges and any applicable sales and use taxes imposed on the purchase or use of services, materials, permanent materials, construction equipment and supplies.  Notwithstanding the foregoing, “Direct Costs” shall not include: (A) any charges for Contractor personnel who are not listed in Exhibit O, and any charges for personnel of Contractor listed in Exhibit O beyond the rates set forth in Exhibit O; (B) any charges for “back office” costs, home office support, project administration costs (including professional fees incurred in connection with schedule updates, time impact analysis, or documentation of Contractor claims, or other general or administrative charges or overhead; (C) any charges for profit, (D) any replacement, repair or other costs or liabilities arising from any loss of or damage to any equipment, tools or other property owned or used by Contractor or its Subcontractors; (E) costs to correct or reperform any components of such Work as a result of the acts or omissions of Contractor or its Personnel; (F) any fines or penalties assessed against Contractor or its Personnel in connection with such Work as a result of the actions or omissions of Contractor or its Personnel or (G) any costs or expenses other than those specifically set forth above as “Direct Costs.”

“Disclosing Party” has the meaning set forth in Section 17.1.

“Dispute” has the meaning set forth in Section 16.1.

“Dollars,” or “$” means the lawful currency of the United States of America.

“Effective Date” has the meaning set forth in the preamble to this Agreement.

“Environmental Laws” means any and all statutes, laws, Applicable Laws, treaties, decrees, executive orders, rules, regulatory orders, directives, judgments, writs, Permits, approvals, ordinances, policies, regulations, rulings and interpretations or other similar legal requirements as in effect and as may be amended during the Term, of any Governmental Authority with jurisdiction over any Party, the Facility Site or the Work (hereinafter referred to in this paragraph as “laws”), relating or applicable to pollution or protection of the environment, including those laws relating or applicable to the manufacturing, generation, use, processing, treatment, recycling, storage, handling, Release and/or disposal of,  human or natural exposure to, health and safety issues and/or interference with the use of property caused by or resulting from , chemicals, constituents, contaminants, pollutants, materials (including but not limited to petroleum or petroleum products), and wastes and any other carcinogenic, corrosive, ignitable, radioactive, reactive, toxic or otherwise hazardous substances, mixtures (whether solids, liquids, gases), daughter or degradation products.

“Existing Utilities” has the meaning set forth in Section 2.6.3.

“Facility” has the meaning set forth in the Recitals.

“Facility Capability Demonstration Tests” means those demonstration tests for the Facility as set forth in Section 01610.3.5 of Exhibit A.

“Facility Site” means that certain parcel of land on which the Facility will be located, as further described in Exhibit L-1.

“Final Completion” has the meaning set forth in Section 6.7.1.

“First Tier Subcontract” means a Subcontract directly between Contractor and a Subcontractor.

“First Tier Subcontractor” means a Subcontractor that is the counterparty to a First Tier Subcontract with Contractor.

“Florida’s Public Records Law” has the meaning set forth in Section 17.3.

“FNTP Date” has the meaning set forth in Section 2.1.2.

“Force Majeure” has the meaning set forth in Section 10.1.

“Fuel Nomination Protocol” has the meaning set forth in Section 7.1.

“Full Notice to Proceed” or “FNTP” has the meaning set forth in Section 2.1.2.

“Geotechnical Report” means the following documents as set forth in Attachment A-20 to Exhibit A.

“Governmental Authority” means a federal, state, provincial, county, municipal, regional, local, environmental or other governmental body, agency or authority, or of any, instrumentality or agency thereof, or of any other court, arbitrator or other authority or other body having jurisdiction over JEA, Contractor, the Facility, the Facility Site, the performance of the Work or the operation of the Facility or any component thereof.

“Guaranteed Dates” means, the Guaranteed Mechanical Completion Date and the Guaranteed Substantial Completion Date.

“Guaranteed Mechanical Completion Date” has the meaning set forth in Section 6.2.4.

“Guaranteed Substantial Completion Date” has the meaning set forth in Section 6.4.4.1.

“Hazardous Material” means any and all chemicals, constituents, contaminants, pollutants, materials (including, without limitation, petroleum or petroleum products), and wastes, and any other carcinogenic, corrosive, ignitable, radioactive, reactive, toxic, or otherwise hazardous or harmful substances or materials, including mixtures (whether solids, liquids, or gases), daughter or degradation products, or substances of similar character, that are now or at any time hereafter defined as, included in the definition of, or regulated as a “hazardous substance,” “hazardous material,” “hazardous waste,” “solid waste,” “toxic substance,” “extremely hazardous substance,” “pollutant,” “contaminant,” or words of similar import under, or otherwise subject to regulation, control, Remediation, or that could reasonably be expected to give rise to liability under, any applicable Environmental Laws, or that are otherwise considered hazardous or harmful to human health or the environment thereunder. Hazardous Materials include, without limitation, crude oil and any fraction thereof, natural gas, natural gas liquids, liquefied natural gas, synthetic gas usable for fuel (or mixtures of natural gas and such synthetic gas), oil and gas exploration or production wastes, polychlorinated biphenyls, asbestos-containing materials, mercury, lead-based paint, urea formaldehyde insulation, radioactivity, per- and polyfluoroalkyl substances (including PFAS and PFOA), and any substances that are contaminated, polluted, or rendered toxic.

“Indemnified Person” has the meaning set forth in Section 11.3.

“Indemnifying Person” has the meaning set forth in Section 11.3.

“Intellectual Property” means all intellectual property, including: (a) inventions (whether or not patentable or reduced to practice), patents and industrial designs (including utility models, designs, and industrial property) and patent and industrial design applications, and inventions and patent disclosures, together with all renewals, reissues, reexaminations, provisional, divisionals, revisions, continuations, continuations-in-part, and extensions thereof; (b) works of original authorship (whether or not copyrightable), registered and unregistered copyrights, mask works, database rights, and moral rights, together with all applications therefor and renewals thereof; and (c) trade secrets, and confidential or proprietary information.

“JEA” has the meaning set forth in the preamble to this Agreement.

“JEA Delay Event” means any delay in or impacts to Contractor’s performance of the Work to the extent caused by any of the following occurring after the Effective Date (but excluding any delays or impacts to the extent caused by Contractor or its Personnel): (a) a breach by JEA of its obligations under this Agreement; (b) a delay by JEA in performing its obligations under this Agreement beyond the applicable schedule dates therefor in the Baseline Project Schedule (or Monthly Updated Schedule, if later); (c) interference by JEA or its other contractors or suppliers (including the PIE Supplier and Other JEA Equipment Supplier) with the Work; and (d) any other events expressly described as a JEA Delay Event in this Agreement.

“JEA Indemnitees” has the meaning set forth in Section 11.1.

“JEA Permits” means those Applicable Permits to be obtained and maintained by JEA as set forth in Exhibit G.

“JEA Furnished Equipment” means the Power Island Equipment, GSU transformer, unit auxiliary transformer, and switches, to be supplied by JEA for the Facility, as further described in Section 01100.2 of Exhibit A-2.

“JEA’s Engineer” means Black and Veatch Corporation.

“JSEB” means a City of Jacksonville Small and Emerging Business Enterprises as defined in Chapter 126, Part 6 of the City of Jacksonville, Ordinance Code, as may be amended from time to time.

“Key Personnel” has the meaning set forth in Section 2.2.7.3.

“Known Existing Subsurface Man-Made Objects” has the meaning set forth in Section 2.6.3.

“Late Mechanical Completion Liquidated Damages” has the meaning set forth in Section 6.2.4.

“Late Substantial Completion Liquidated Damages” has the meaning set forth in Section 6.4.4.2.

“Limited Notice to Proceed” or “LNTP” means a written notice issued by JEA to Contractor pursuant to Section 2.1.1 directing Contractor to commence and perform a specific, limited scope of Work prior to JEA's issuance of Full Notice to Proceed.

“LNTP Budget” has the meaning set forth in Section 2.1.1.1.

“LNTP Work Scope” has the meaning set forth in Section 2.1.1.1.

“Losses” has the meaning set forth in Section 11.1.

“Major Subcontract” means any Subcontract that either: (a) is a First Tier Subcontract; or (b) involves, either initially or as the result of a subsequent amendment or change order, the provision of goods and/or services with a value of at least Five Hundred Thousand Dollars ($500,000).

“Major Subcontractor” means the Subcontractor that is party to a Major Subcontract.

“Material Safety Data Sheet” means a document prepared and maintained in accordance with applicable Environmental Laws, including OSHA’s Hazard Communication Standard (29 C.F.R. § 1910.1200), describing the properties, hazards, handling, storage, disposal, and emergency response measures applicable to a Hazardous Material.

“Mechanical Completion” has the meaning set forth in Section 6.2.1.

“Milestone Payments” has the meaning set forth in Section 5.2.

“Milestones” means each of the activity milestones that Contractor will successively meet in the course of performing the Work as set forth in Exhibit D.

“Monthly Progress Report” means a progress report containing the information required in Exhibit E.

“Must-Make Maximum Auxiliary Load” has the meaning set forth in Section 7.9.1.

“Monthly Updated Schedule” means, as further described in and in compliance with the requirements of Exhibit C, an updated version of the schedule for the performance of the Work, containing the same schedule logic and durations as are in the Baseline Project Schedule, which shall (a) reflect the actual progress of the Work to date (incorporating, without limitation, all then-present impacts or delays vis-a-vis the Baseline Project Schedule resulting from the fault, actions or omissions of Contractor to date) and (b) forecast the remaining schedule for the completion of the Work.

“MOT” has the meaning set forth in Section 2.2.21.2.

“MOT Items” has the meaning set forth in Section 2.2.21.2.

“MOT Plan” has the meaning set forth in Section 2.2.21.2.

“NERC” means the North American Electric Reliability Corporation.

“Non-Public Data” has the meaning set forth in Section 2.2.17.4.

“Operation and Maintenance Manual” has the meaning set forth in Section 2.2.24.

“Operational Spare Parts” has the meaning set forth in Section 2.2.12.2.

“Other JEA Equipment Vendor” means of supplier of JEA Furnished Equipment, other than the Power Island Equipment.

“Parties” means JEA and Contractor; “Party” means JEA or Contractor, as the case may be.

“Payment Bond” has the meaning set forth in Section 13.3.

“Performance Bond” has the meaning set forth in Section 13.4.

“Performance Liquidated Damages” has the meaning set forth in Section 7.9.2.

“Permits” means all waivers, franchises, variances, permits, authorizations, licenses, approvals, consents, certificates or orders of or from any Governmental Authority having jurisdiction over JEA or Contractor and their respective obligations under this Agreement, or the Facility or any component thereof, the Facility Site, the performance of the Work, or the operation of the Facility or any component thereof, as may be in effect and/or amended or supplemented from time to time.

“Person” means any individual, corporation, partnership, limited liability company, association, joint stock company, trust, unincorporated organization, joint venture, or other entity with legal constitution under applicable laws, or any Governmental Authority or political subdivision or instrumentality or agency thereof.

“Personal Data” has the meaning set forth in Section 2.2.17.4.

“Personnel” means, with respect to a Party or entity, such Party’s or entity’s employees, agents, personnel, representatives, invitees, subcontractors, vendors and any other third party independent contractors with whom such Party or entity has contracted, and its agents’, personnels’, representatives’, invitees’, subcontractors’, vendors’ or third party independent contractors’ respective employees, agents, personnel, representatives, invitees, subcontractors, vendors or third party independent contractors.  For the avoidance of doubt, Contractor (and its Personnel) are not the Personnel of JEA.

“PIE Purchase Agreement” means the agreement by and between JEA and PIE Supplier for the supply of the Power Island Equipment as set forth in Exhibit T.

“PIE Supplier” means GE Vernova Operations LLC.

“Plant Data Books” means the compilation of documents, drawings and information which reflects the Facility design, including the Construction Documents (all as further described in Section Q501 of the Scope of Work), which Contractor will maintain and update, and which JEA will review and approve.

“Power Island Equipment” means the means the 1 x 1 engineered equipment package as supplied by the PIE Supplier under the PIE Purchase Agreement consisting of one (1) GEV 7HA.03 gas turbine and generator package, one (1)  [model] steam turbine and generator package, and one (1) model three pressure drum style duct fired heat recovery steam generator with stacks, and all associated auxiliary equipment, including the Mark VIe distributed control system and all related auxiliary equipment, materials, apparatus, and components, all as further described in Exhibit T.

“Power Island Equipment Installation Guidelines” means the guidelines for assembly and installation of the Power Island Equipment as described in the Power Island Equipment Technical Specifications.

“Power Island Equipment Minimum Performance Guarantees” means the “Minimum Performance Levels” for the Power Island Equipment as defined and described in Exhibit A to Exhibit T.

“Power Island Equipment Performance Tests” has the meaning set forth in Section 7.4.3.

“Power Island Equipment Technical Specifications” means the documentation set forth in Exhibit T.

“Power Island Equipment Testing Procedures” has the meaning set forth in Section 7.4.3.“Pre-Existing Hazardous Materials” has the meaning set forth in Section 2.2.20.3.

“Preliminary Change Order Notice” has the meaning set forth in Section 9.2.1(a).

“Project” means, collectively, the development, financing and completion of the Facility, as further described in Exhibit A.

“Project Manager” means, with respect to each Party, the individual appointed by such Party under Section 18.2 to act on such Party’s behalf with respect to that Party’s duties and responsibilities under this Agreement.

“Project Safety Manual” has the meaning set forth in Section 2.2.17.

“Project Security Plan” has the meaning set forth in Section 2.2.19.

“Prudent Industry Practices” means those practices, methods, procedures and acts as are consistent with the norms of the United States utility power industry at the time in question, which, in the exercise of reasonable judgment and in light of the facts known at the time the decision was made, could have reasonably been expected to accomplish the desired result at a reasonable cost consistent with principles of reliability, safety, Applicable Laws, Applicable Codes and Standards and Applicable Permits.

“Punch-List” has the meaning set forth in Section 6.5.

“Punch-List Withholding Amount” has the meaning set forth in Section 5.4.6.

“Qualified Issuer” means a US office of an insurance company organized under the law of the US or a political subdivision thereof or a foreign bank with a branch office located in the US, and in any case, whose rating with respect to its long-term unsecured, unsubordinated indebtedness is a least “A-” by S&P or Fitch or “A3” by Moody’s or “A” by AM Best that (i) is duly licensed and otherwise authorized in the State of Florida to issue bonds of the kinds and for the limits so required; (ii) is listed in the current issue of the Federal Register Department of the Treasury list; (iii) is in full compliance with the provisions of the Florida Insurance Code; and (iv) has atleast twice the minimum surplus and capital required by the Florida Insurance Code during the Term.

“Ready for First Fire” means  with respect to a Power Island Equipment, the satisfaction of the following requirements:  (i) Contractor has installed the Power Island Equipment; (ii) Contractor has performed the required cold commissioning activities for the Power Island Equipment; (iii) the activities required to achieve Ready For First Fire as set forth in the PIE Supplier-provided Installation Guidelines, Item 230 in the Schedule of Submittals, and Commissioning Book (COMBOOK, Item 231 in the Schedule of Submittals) have been completed by Contractor and approved by JEA or PIE Supplier in writing; (iv) fuel, necessary lubricants, and operating supplies are continuously available for the Power Island Equipment to accomplish ignition of the gas turbine for the first time; and (v) JEA’s trained operators are available for operation of the Power Island Equipment.

“Ready for Full Steam Admission” means  with respect to a Power Island Equipment, the satisfaction of the following requirements: (i) Ready For First Fire has been achieved; (ii) the activities required to achieve Ready for Full Steam Admission as set forth in the PIE Supplier-provided Installation Guidelines, Item 230 in the Schedule of Submittals, and Commissioning Book (COMBOOK, Item 231 in the Schedule of Submittals) have been completed by Contractor and approved by the PIE Supplier in writing; and (iii) steam is successfully generated at one hundred percent (100%) capacity meeting operational steam purity and thermal conditions meeting “Action Level 1” in accordance with GEK 120275.

“Real Estate Rights” means all rights in or to real estate (including title to or other rights to use or access the Facility Site, leases, contracts, Permits, easements, licenses, private rights of way, and utility and railroad crossing rights) required to be obtained or maintained in connection with construction of the Facility on the Facility Site, performance of the Work, or operation of the Facility.

“Receiving Party” has the meaning set forth in Section 17.1.

“Records” has the meaning set forth in Section 18.18.

“Recovery Plan” has the meaning set forth in Section 2.3.2.1.

“Redacted Copy” has the meaning set forth in Section 17.3.2.1.

“Reductive Change Directive” has the meaning set forth in Section 9.5.1.2.

“Release” means spilling, leaking, pumping, pouring, emitting, discharging, injecting, escaping, leaching, dumping, exacerbation, aggravation, abandonment or disposing into or migration within the environment.

“Reliability Test” has the meaning set forth in Section 7.6.

“Reliability Testing” means performing a Reliability Test.

“Remediation” means the investigation, removal, remediation and cleanup of, and other corrective action for, Hazardous Materials and/or damage to the environment caused by Hazardous Materials.

“Responding Party” has the meaning set forth in in Section 5.4.8.2.

“Requesting Party” has the meaning set forth in in Section 5.4.8.2.

“Required Level of Assembly” means, with respect to each component of a Power Island Equipment, the degree and extent of factory assembly, sub-assembly, modularization, and pre-commissioning work to be completed by PIE Supplier prior to delivery of such component to the Delivery Point, as set forth in Exhibit T.

“Retention” has the meaning set forth in Section 5.4.4.

“Scope of Work” means the scope of work set forth in Exhibit A.

“Security Incident” has the meaning set forth in Section 2.2.17.4.

“Surface Conditions” has the meaning set forth in Section 2.6.1.

“Operational Spare Parts” has the meaning set forth in Section 2.2.12.3.

“Subcontract” means a First Tier Subcontract or any contract between Subcontractors, with respect to performing any part of the Work or providing any equipment or materials in connection with the Work.

“Subcontractor” means each and every vendor, supplier, materialmen, subcontractor or contractor of any tier, including such parties’ Personnel, performing any part of the Work or providing any equipment or materials in connection with the Work, directly or indirectly for or to Contractor.

“Substantial Completion” has the meaning set forth in Section 6.4.1.

“Substantial Completion Date” has the meaning set forth in Section 6.4.3.

“SWPPP” has the meaning set forth in Section 2.11.1.

“Takeover Time” has the meaning set forth in Section 6.6.2.

“Tariffs” has the meaning set forth in in Section 5.3.2.

“Term” means the period of time commencing upon the Effective Date and ending upon the last Day of the Warranty Period.

“Termination Payment” has the meaning set forth in Section 12.1.1.

“Terms and Conditions” means the preamble, recitals and Articles 1 through 18 hereof.

“Testing Guidelines” means those testing guidelines as described in and developed in accordance with the procedures described in Section 01610 of Exhibit A-2.

“Testing Start Date Notice” has the meaning set forth in Section 7.4.1.

“Third Party” means, for purposes of each Party’s indemnity obligations under this Article 11, with respect to Contractor’s indemnification obligations, any Person other than JEA Indemnitees but expressly including the employees of the JEA Indemnitees and, with respect to JEA’s indemnification obligations, means any Person other than Contractor Indemnitees, but expressly including the employees of Contractor Indemnitees.

“Transfer Time” has the meaning set forth in Section 6.6.1.

“Travel Policy” means those policies as described in Exhibit I.

“Turnover Package” means, for each Balance of Plant Equipment, the documentation (including drawings, start-up procedures, proposed items for the Punch-List as relate to such system (which shall be subject to the criteria described in Section 6.5), and other items) in content, form and substance acceptable to JEA, submitted by Contractor to JEA which demonstrates that such Balanced of Plant Equipment has been completed in accordance with this Agreement and may be operated safely for its intended purpose.

“Unforeseen Subsurface Conditions” has the meaning set forth in Section 2.6.2.“Warranty” and

“Warranties” have the meanings set forth in Section 8.1.

“Warranty Period” has the meaning set forth in Section 8.2.

“Work” has the meaning set forth in Section 2.2.

Standards of Interpretation.

1.2.1	This Agreement shall not be construed more strongly against either Party, regardless of which Party is responsible for its preparation.

1.2.2	As used in this Agreement, the words “including” or “includes” or “include” shall mean “including without limitation, “includes without limitation,” and “include without limitation.”

1.2.3	Common nouns and pronouns shall be deemed to refer to the masculine, feminine, neuter, singular, and plural, as the identity of the person or persons, firm or corporation may in the context require.

Contractor’s Work and Other Obligations

Commencement of the Work.

Initial LNTP Work; Limited Notice(s) to Proceed.

At any time after the Effective Date, but prior to the issuance of Full Notice to Proceed, JEA may, in its sole discretion, and upon Contractor's consent, issue one or more written Limited Notice(s) to Proceed directing Contractor to commence and perform specific portions of the Work. Each LNTP shall specify the scope, schedule, a lump sum price or maximum agreed upon price (if such Work is to be performed on a time and materials basis), and other details of such Work. Upon receipt of such LNTP, Contractor will promptly commence and diligently perform the LNTP Work Scope.  JEA will pay all undisputed amounts for any Work performed under an LNTP in accordance with and subject to the provisions of Article 5.  All such paid amounts will count toward the Contract Price.

Notwithstanding the foregoing, the Parties acknowledge that the issuance of one or more LNTPs shall not obligate JEA to issue the Full Notice to Proceed. JEA may terminate this Agreement for convenience under Section 12.1 at any time prior to issuance of FNTP in which case JEA’s total liability to Contractor for such termination shall be to pay for any Work performed under any LNTP for which Contractor has not been paid. Payments of the foregoing amounts shall be JEA’s sole liability, and Contractor’s sole and exclusive remedy, in connection with such termination, and JEA will not otherwise be liable to Contractor, any Subcontractor or any other party for any damages or indirect costs resulting from such termination, including prospective profits on Work not performed or other consequential or incidental damages.

All the terms and conditions of this Agreement shall apply to Work performed pursuant to a Limited Notice to Proceed, except to the extent expressly provided otherwise in a Limited Notice to Proceed.

Full Notice to Proceed.  Except for Work performed pursuant to one or more Limited Notices to Proceed, Contractor shall not commence full performance of the Work until JEA issues a written “Full Notice to Proceed” (or “FNTP”), which JEA shall issue when JEA determines it is desirable for Contractor to commence full performance of the Work.  The “FNTP Date” will be the date the Full Notice to Proceed is issued by JEA.

  - Work to be Performed.

Except as otherwise expressly set forth in this Agreement as being the responsibility of JEA or the PIE Supplier or Other JEA Equipment Vendor, Contractor shall, in accordance with this Agreement, perform or cause to be performed all necessary work and services required in connection with the design, engineering, permitting, procurement, construction, assembly, installation, training for operation of, commissioning, start-up, testing and completion of the Facility including without limitation all necessary work and services required in connection with the receipt, unloading, assembly, installation, and integration into the overall Facility, of the Power Island Equipment and other JEA Furnished Equipment (all of the foregoing, collectively, the “Work”) including such work as is further described in the Scope of Work and as required to achieve the requirements of Mechanical Completion, Substantial Completion, and Final Completion.  Company shall perform all Work in accordance with the Contract Documents and the applicable JEA standards manuals, safety manuals, policies, accepted commercial work practices, local, state, and federal, rules regulations and laws which may be amended from time to time. Contractor shall comply with JEA’s standard policies and procedures provided to Contractor after the Effective Date, as such policies and procedures may be amended from time to time. Without limiting the foregoing, as part of the Work, Contractor hereby undertakes the following covenants and agrees to provide the following services:

Engineering/Design Services.

General Contractor Responsibilities.  Contractor represents and warrants that it has thoroughly familiarized itself with the Scope of Work, the specifications of the JEA Furnished Equipment as described in Exhibit U and Exhibit V, and the Power Island Equipment and the PIE Supplier’s scope of supply as described in Exhibit T. Excluding design and engineering of the Power Island Equipment, Contractor will provide all engineering and design services necessary to complete the Facility. Such engineering and design will, without limitation, include such engineering and design of the Balance of Plant as is necessary or appropriate to integrate the JEA Furnished Equipment with the Balance of Plant Equipment, and to cause the Balance of Plant Equipment to interface with the JEA Furnished Equipment, in a manner that results in a Facility that will reliably and safely function and perform as contemplated in this Agreement. Contractor will also be responsible for all engineering and design of the Ancillary Site Infrastructure. All engineering work requiring certification shall be certified by professional engineers licensed and properly qualified to perform such engineering services under Applicable Laws.

Certain Engineering and Design Requirements.  Contractor will engineer and design the Balance of Plant:

(a)	 so that they are in compliance with all Applicable Codes and Standards, Applicable Laws, and Applicable Permits and will be capable of performing in accordance with the BOP Performance Guarantees, the BOP Reliability Guarantee, and other requirements of this Agreement; and

(b)	in a manner that supports and allows for the commissioning, start-up, testing and operation of the Power Island Equipment such that the Power Island Equipment achieves Substantial Completion and can operate without interruption or load restriction, and in this regard such design shall include without limitation such elements of redundancy, isolations, phasing, duplications, safeties, or any other considerations to achieve the same.

Cooperation; Preliminary Designs.  Contractor will cooperate with the engineering efforts of JEA and JEA’s Engineer; provided, however, that Contractor ultimately bears all responsibility for engineering and designing the Balance of Plant, including the incorporation and integration of the JEA Furnished Equipment, and for engineering and designing Ancillary Site Infrastructure so as to meet the requirements of this Agreement. As with respect to any preliminary designs, technical specifications, design bases, or other engineering or design documents or work or information regarding the Balance of Plant that has been provided to Contractor by JEA or JEA’s Engineer in advance of the Effective Date, including any of the same that have in any way been incorporated into the Scope of Work, Contractor represents, warrants and agrees that: (a) it has reviewed the same and understands that the same were and are for informational and conceptual purposes only, and (b) as of the Effective Date, Contractor takes full responsibility for designing and engineering the Balance of Plant in manner that will achieve the BOP Performance Guarantees.

Design Development Documents.  By the date(s) specified in the Baseline Project Schedule, Contractor will prepare, for written approval by JEA, design development documents for the Balance of Plant and the Ancillary Site Infrastructure consisting of drawings, models, specifications, plans and other documents necessary to fix and describe the Balance of Plant and the related Ancillary Site Infrastructure with respect to the civil engineering, structural, instrumentation, control, mechanical, electrical, plumbing, fire protection, acoustical and life safety systems to be incorporated therein (collectively, the “Design Development Documents”). As part of the development of the Design Development Documents, Contractor will propose to JEA, for JEA’s review and approval, the list of systems comprising the Balance of Plant that will be the subject of the Turnover Packages.

Approved Construction Documents.  As further described in the approved Design Development Documents, and any further adjustments in the scope or quality of the Facility authorized in writing by JEA, Contractor will prepare, for written approval by JEA, by the date(s) specified in the Baseline Project Schedule, drawings and specifications setting forth in detail the requirements for the complete construction of the Facility (other than the design of the JEA Furnished Equipment). Such drawings and specifications, as approved by JEA, shall be the “Construction Documents.” Following JEA’s written approval of the applicable Construction Documents pursuant to Section 2.2.1.6, Contractor will proceed with the relevant Work covered thereby, based upon the Scope of Work and Construction Documents.

JEA Review of Documents. With respect to each submittal received from Contractor under Sections 2.2.1.4 or 2.2.1.5, JEA will respond with comments (and approval (or reasoned disapproval), if such approval is required under the Scope of Work) within fifteen (15) Business Days of its receipt thereof, and if JEA does not so respond within this period the submittal will be deemed approved.  Contractor shall, within ten (10) Business Days after Contractor’s receipt of JEA’s comments to the submittals (if any) address such comments by either: (i) adopting such comments and incorporating them into such submittals; (ii) notifying JEA that Contractor believes that the incorporation of such comments would constitute a material change in the Scope of Work and indicate the amount of any additional compensation that Contractor is able to substantiate is required in order to address such comment (in which case, JEA will have the option of directing Contractor to incorporate such comment pursuant to a Change Order in accordance with the provisions of Article 9); or (iii) notifying JEA that Contractor does not agree with such comment, in which case Contractor shall provide to JEA an explanation setting forth its professional reasons for not addressing such JEA comment. Contractor acknowledges that the Baseline Project Schedule takes into account all review and comment periods in respect of the documents to be reviewed by JEA hereunder. JEA’s provision of comments (or lack of provision of comments) to such plans, calculations, specifications and/or drawings shall not relieve Contractor of any of its obligations or liabilities hereunder, and JEA assumes no responsibility for such obligations or liabilities as a result of its provision or lack of provision of comments.

Preparation of Facility Site.

Clearing of Site. Contractor has visited the Facility Site and represents that the Facility Site is sufficient for Contractor to construct the Facility and perform the Work.  Contractor will be responsible for clearance of the Facility Site, including the removal of any obstructions. As part of the Work, Contractor will arrange and pay for disposal of sewage and waste as necessary to enable Contractor to perform the Work.  To the extent not obtained through excavation on the Facility Site, Contractor shall provide for the procurement of any additional soil, gravel, sand, or other fill materials, as required for the performance of the Work.  Subject to Section 2.5.6, with respect to any soil, rock, gravel, sand, minerals, timber or other resources obtained in the clearance or excavation of the Facility Site or the performance by Contractor of the Work, Contractor will only dispose of the same as directed by JEA. Contractor will act in accordance with all Applicable Laws and Applicable Permits to provide adequate treatment of and protection against water runoff resulting from Contractor’s and its Subcontractor’s work, including as required by Applicable Laws and Applicable Permits.  Contractor will provide for the collection, retention, treatment and disposal of groundwater resulting from Contractor’s and its Subcontractor’s work, including in accordance with all Applicable Laws and Applicable Permits.

Surveying. Unless specifically stated in the Contract Documents as being provided by JEA, Contractor shall be responsible for all surveying necessary to commence and perform the Work. Contractor shall employ a land surveyor registered in the State of Florida to reference and restore all property corners and/or monuments that may have been disturbed and to ensure accurate horizontal and vertical control during the construction of this project and for staking locations for new structures. Height and spacing of stakes to be as directed by JEA Engineer.  All Work shall be done to the lines, grades and elevations shown on the drawings. Any Work improperly located may be ordered removed and replaced at the Contractor’s expense. Contractor shall be responsible for making its own determination of water table variations and shall not assume that any water levels shown by the aforesaid boring data will necessarily be maintained at the level indicated. Contractor shall investigate the conditions above or below the surface of the ground as it may deem necessary for the proper and timely performance of its Work including, but not limited to, the making of borings.

Tree Protection. Contractor shall protect all trees, in accordance with applicable city and county laws, from damage by vehicles, equipment and machinery, except those trees designated for removal on the construction drawings and for which Contractor shall be responsible for obtaining all required approvals and permits. Removal of any tree not so designated nor permitted, shall be only upon specific approval by the JEA Engineer. Excavated dirt shall not be piled around the base of any tree not designated for removal. Contractor shall not bury or burn any refuse around or near the trees. Contractor shall proceed with caution when excavating in the vicinity of root structure of any tree. Excavation shall be by hand if necessary. Roots up to 2" in diameter when severed do not require any pruning paint. Roots from 2" to 4" in diameter must be severed with a pruning saw and painted. Roots over 4" shall not be severed except as directed by the JEA Engineer. An ax or similar tool is not acceptable for pruning. The wood shall be treated with asphalt-type pruning paint as soon as possible after pruning. Prior to any Site disturbance, barriers shall be put up around each tree to be protected. These barriers shall be constructed of 2 x 4's or any other practical materials that will discourage disturbance near the tree. To conform to applicable city and county laws and codes, these barriers should be at least 6' away from the trunk of the tree and protect an area that is at least 50% of the unpaved area covered by the crown spread of the tree. When conditions permit, barriers are to be placed in such a manner as to provide the largest undisturbed area possible. Cutting tree roots shall be kept to a minimum and only allowed when absolutely necessary. In such instances Contractor shall ensure that all cuts are made clean with a saw, free of all loose soil, and sealed with pruning paint or shellac. At no time shall roots be pulled, ripped or cut with a blade, backhoe or other mechanical device. Additional fill under the crown spread of trees shall be kept to a minimum. If additional fill is unavoidable, all fill material shall consist of clean, coarse sand or gravel, free of silt and clay to allow for free movement of air and water. Lowering the grade under the crown spread of trees will not be permitted. Should branches require pruning to provide for roadway or other necessary clearance, they shall be cut back to a main stem or crotch of the tree. All cuts shall be made at the bench collar to allow the natural healing process of the tree to occur. To further promote the natural healing process, no pruning paint or other material shall be applied to pruning cuts. If a tree is wounded during construction, all bark surrounding the wound shall be cut away and carefully removed. Care shall be taken to leave as much cambium as possible. Any tree whose root system has been disturbed or damaged must be properly fertilized to aid in its recovery. The hole or punch-bar method shall be used for applying fertilizer. The holes should be approximately 12" to 18" deep, 1" to 2" in diameter, 2' apart, and extend 2' past the drip line of the tree. Contractor shall not apply fertilizer within 1 foot of the trunk of a small tree (up to 6" in diameter) or within 3' of the trunk of a large tree (over 6" in diameter). Injury to the root collar and trunk base may result. The type of fertilizer to be used shall be 25% organic 8-8-8 with minor elements included. Chemical analysis as follows: Total Nitrogen, not less than 8.00%, available Phosphoric Acid, not less than 8.00%, water soluble potash, not less than 8.00%. Fertilizer shall be applied at the following rates and shall be evenly distributed among the holes: (i) Hardwoods up to 6" Dia. 2 lb. per inch of Dia; (ii) Hardwoods over 6" Dia. 4 lb. per inch of Dia; (iii) Evergreens up to 6" Dia. 1 lb. per inch of Dia; and (iv) Evergreens over 6" Dia. 2 lb. per inch of Dia. No separate measurement and payment shall be made for hand digging around trees, tree trimming, and provision of arborist services, but all cost shall be included in the associated item of Work. Hand digging, tree trimming, and arborist services shall include but not be limited to all labor, equipment and supervision required to successfully hand dig or trim tree branches where tree roots or branches may be destroyed or injured due to the Work. Item shall include services of a certified arborist as required by the City landscape architect to ensure minimal or no damage to tree canopy or root system. If the tree canopy or root system is damaged, Contractor, at its own expense, shall repair, restore, or replace the tree at the direction of the arborist. Contractor shall review the drawings and visit the Work area prior to the bid to satisfy itself as to the amount of tree removal and disposal to be performed to complete the Work, and the extent of tree trimming required to perform the work. All tree mitigation costs shall be borne by the City of Jacksonville. Trees identified on the drawings for removal shall not be paid for separately, but all associated cost for removal and disposal and subsequent compacted soil backfill replacement shall be included in the associated item of the Work.

Procurement of Balance of Plant Equipment.  Contractor will procure in Contractor’s name, pay for, receive, transport to the Facility Site, unload, and store, as an independent contractor and not as agent for JEA, all Balance of Plant Equipment. Contractor will procure as necessary all manufacturing and related services (whether on or off the Facility Site) necessary to provide the Balance of Plant Equipment.  Within [●] Days after the Effective Date, Contractor will provide JEA with the BOP Equipment List.  Without JEA’s prior written approval, Contractor will not acquire, furnish, install or permit the installation of any bulk-power system electric equipment (including power transformers, high-voltage circuit breakers, protection and control systems, [SCADA] and related communication equipment) that is manufactured by, supplied by, or otherwise under the ownership, control or direction of any person or entity organized under the laws of, or owned or controlled by the government of, a foreign adversary (as defined by U.S. executive order(s), Department of Energy orders, or other U.S. federal mandates). Contractor will flow this requirement down to all Subcontractors and suppliers. Nothing in this Section limits Contractor’s obligation to comply with all Applicable Laws and governmental restrictions regarding supply chain risk for electric sector facilities. Contractor will also provide all cranes and other construction and installation equipment and machinery necessary to perform the Work, including any equipment and machinery which will not become a part of the Facility but are necessary for Contractor to complete the construction and installation of the Facility.

JEA Furnished Equipment.

Power Island Equipment.

PIE Supplier Scope of Supply. The Parties acknowledge that JEA has entered into the PIE Purchase Agreement with the PIE Supplier.  The PIE Supplier’s scope of supply and related obligations are described in Exhibit T.

Power Island Equipment Drawings.  Contractor acknowledges that the PIE Supplier will be providing JEA with drawings, design interfaces, and other documentation for review as further described in Section 400.5 of Exhibit A-2.  Promptly, but within no more than ten (10) Days after Contractor receives such drawings or documentation from JEA or PIE Supplier, Contractor will provide to JEA comments, if any, on such drawings and documentation.

Inspection/Expediting/Shipment of the Power Island Equipment. As part of the Work, upon request, Contractor will cooperate and work with JEA to perform and will participate in and provide input in connection with, all pre-shipment inspections and expediting of the equipment comprising the Power Island Equipment, as directed by JEA. Contractor will cooperate and work with JEA to perform, and will participate in and provide input in connection with, all pre-shipment inspections of such components of each component of the Power Island Equipment for the purposes of determining: (a) whether the same are complete and ready for shipment; and (b) whether any other components should also, at that time, be ready for shipment, in order to avoid impacts to the scheduled installation, construction and/or first fire of the Power Island Equipment.

Delivery/Unloading of the Power Island Equipment

- (i) JEA will cause the PIE Supplier to deliver the respective components of the Power Island Equipment to the applicable delivery point as set forth in Exhibit T (in each case, the applicable “Delivery Point”) by the applicable dates as set forth in the Baseline Project Schedule, in accordance with and subject to the provisions of the PIE Agreement. For Power Island Equipment components delivered by truck/heavy haul to the Facility Site, upon such arrival, Contractor may, by communication and direction to the transporter, extend the applicable Delivery Point to such location on the Facility Site as Contractor requires, provided that such delivery location must be one to which the truck can reasonably navigate without the need for transloading or extraordinary efforts.

- (ii) Provided that PIE Supplier’s shipments are not delivered earlier than sixty (60) Days prior to the dates set forth in the Baseline Project Schedule for “Major Components” of the Power Island Equipment and ninety (90) Days prior to the dates set forth in the Baseline Project Schedule for “Minor Components” of the Power Island Equipment, if any such components cannot be delivered to the Facility Site when ready due to any cause attributable to Contractor, and PIE Supplier consequently delivers such components to storage in accordance with Section 5(f) of the PIE Purchase Agreement or charges JEA for any storage costs at the PIE Supplier’s facilities, then Contractor will (i) be liable to reimburse JEA for any direct storage costs and related expenses that JEA demonstrably incurs as a result thereof, and (ii) bear all costs and expenses of double-handling of components.

Assembly and Installation of Power Island Equipment.  Without limiting any other provision of this Agreement, Contractor will assemble and install all Power Island Equipment in strict accordance with all specifications, instruction and installation manuals, and instructions, of the PIE Supplier.  Contractor will not alter the Power Island Equipment without the prior written consent of JEA and the PIE Supplier.

Cooperation and Coordination with PIE Supplier.  The Parties acknowledge that cooperation and coordination between Contractor and the PIE Supplier will be critical to the successful and timely completion of the Facility.  In this respect, Contractor will cooperate with the PIE Supplier, and coordinate Contractor’s activities with the PIE Supplier's activities in connection with the Project.  Such efforts will include participation in regular meetings between the Contractor Project Manager, JEA Project Manager, and any key representatives of the PIE Supplier designated by JEA, and any other meetings with PIE Supplier as JEA may request that Contractor attend.  Without limiting the foregoing, Contractor acknowledges that PIE Supplier will be providing technical field representatives who will be obligated to provide direction in connection with the erection, construction, start-up, and testing of the Power Island Equipment.  Contractor will proactively seek the assistance, advice, and input from such representatives where necessary or appropriate, including without limitation clarification of any interfaces between the Power Island Equipment and the Balance of Plant. Contractor will allow PIE Supplier’s representative and personnel reasonable access to the Facility Site as may be necessary to allow PIE Supplier to undertake its obligations with respect to the Power Island Equipment.

Other JEA Furnished Equipment.  [Placeholder for provisions addressing unloading, inspection, storage and installation of JEA Furnished Equipment other than the Power Island Equipment].

Assembly Installation and Construction of Balance of Plant Equipment. Contractor will have sole responsibility for the assembly, installation, and construction of the Balance of Plant Equipment.

Inspection, Component Testing and Expediting.

Testing Responsibilities. Contractor will perform all inspections, component testing, expediting, quality surveillance, and traffic services as necessary for the performance of the Work.  Contractor’s responsibilities under this Section 2.2.6.1 shall include inspecting and testing such materials and equipment as are customarily inspected and/or tested in accordance with Prudent Industry Practices in connection with work of the same nature as the Work, including inspecting all Work in progress at intervals appropriate to the stage of construction, fabrication or shipment on or off the Facility Site as necessary to ensure that such Work is proceeding in accordance with this Agreement and the Baseline Project Schedule and to protect JEA against defects and deficiencies in such Work.

JEA’s Right to be Present. Contractor will notify JEA of any testing to or inspections of any components of the Work: (a) ten (10) Days in advance of such testing or inspection, for any testing or inspection outside the Facility Site; and (b) forty-eight (48) hours in advance of such testing or inspection, for any testing or inspection at the Facility Site. JEA, JEA’s Engineer and the JEA Project Manager shall each have the option of being present at all tests and inspections on or off the Facility Site. No inspection nor observance of any inspection or testing performed or failed to be performed by JEA or JEA’s Engineer or any of their respective representatives hereunder shall be deemed to constitute a waiver of any of Contractor’s obligations under this Agreement or be construed as an approval or acceptance of the Work.

Labor and Personnel.

Provision of Personnel; Licensed Engineers.  As part of the Work, and except as set forth in Section 3.7.1, Contractor shall provide and be solely responsible for all labor and personnel required in connection with the Work, all of whom are full-time employees of Contractor or approved Subcontractors and shall be reasonably competent and properly qualified to perform the portions of the Work assigned to them, including professional engineers who are licensed to perform engineering services in the State in which their work is performed (and in the State where the Facility is located, to the extent required for the relevant Work performed) and qualified to perform the type of engineering services required by Contractor hereunder.  Contractor is responsible for complying with all Applicable Laws regarding engineer licensing, including those that may require the provision of the seal of a professional engineer licensed under the laws of the State of Florida, where required. Upon request, Contractor shall furnish a copy of a technical certification or other proof of qualification. Contractor shall take all actions necessary to ensure that Contractor's Personnel are not considered employees of JEA. Such actions include, but are not limited to, ensuring that Contractor's Personnel receive payment and any legally mandated insurance (e.g., workers' compensation and unemployment compensation) from an employer other than JEA.

Contractor Labor Relations. Contractor shall negotiate and resolve any disputes between the Contractor and its employees, or anyone representing its employees. Contractor shall immediately notify JEA of any actual or potential labor dispute that may affect the Work and shall inform JEA of all actions it is taking to resolve the dispute.

Key Personnel; Contractor’s Project Manager. Contractor’s staff will include the key personnel set forth in Exhibit H, who will be dedicated to the Work through Final Completion (the “Key Personnel”).  Contractor will not remove or replace any of the Key Personnel without the prior written consent of JEA.  Contractor will provide a project manager or other representative who has the experience and authority to administer this Agreement on behalf of Contractor (the “Contractor Project Manager”).  Such Contractor Project Manager will be responsible for furnishing information as requested by JEA, will have the authority to agree upon procedures for coordinating Contractor’s efforts with those of JEA, and shall be present or duly represented at the Facility Site at all times when the Work is being performed. Matters relating to this Agreement or the Work which are within the knowledge, or which ought reasonably to be within the knowledge of the Key Personnel and/or Contractor Project Manager shall be deemed to be within the knowledge of the Contractor. The Contractor Project Manage is designated in Section 18.2.

Language Competencies.  For purposes of safety, efficiency and quality control and assurance, all personnel performing Work at the Facility Site will be capable of understanding, speaking, reading, and writing the English language with sufficient structural accuracy and vocabulary to effectively participate in written and oral conversations that relate to Work assignments and communications concerning safety and security at the Facility Site.

Removal of Personnel.  If at any time during the performance of the Work, any of Contractor’s Personnel becomes, for any reason, unacceptable to JEA, including as a result of such person’s creating an undue risk of a safety hazard at the Facility Site or violating: (i) the Project Safety Manual; or (ii) Project Security Plan, then, upon notice from JEA, Contractor will immediately remove and replace such individual.   If at any time during the performance of the Work the Contractor Project Manager or any of the Key Personnel should no longer be available to perform services in connection with the Work, then Contractor will replace such individual with an individual acceptable to JEA.  Any such removal of Personnel (including Key Personnel) shall, unless JEA approves otherwise, be complied with immediately by the Contractor and shall not constitute cause for claiming additional time, compensation or damages.  Any costs associated with the addition, replacement or renewal of any such Personnel, whether at JEA’s request or otherwise, will be borne by Contractor. Removal of any of Contractor’s Personnel shall not release the Contractor from any of its obligations under this Agreement.  Any Personnel discharged for cause by the Contractor or any Subcontractor may not be re-employed at the Facility Site by another Subcontractor; nor shall the Contractor or any Subcontractor employ at the Facility Site an employee of another contractor or supplier of JEA (or of a subcontractor of such other contractor or supplier) who has similarly been refused admittance to or removed from the Facility Site by JEA.

JEA Contractor Travel Policy. Contractor shall cause all of Contractor’s Personnel to comply with JEA’s Travel Policy as set forth in Exhibit I. To the extent the Contractor's fees include reimbursement for travel and travel-related expenses, only the authorized expenses described in Exhibit I will be reimbursed.

Legal Workforce. Contractor’s employment of unauthorized aliens shall be a violation of Section 274A(e) of the Immigration and Nationality Act and a breach of the provisions of the Agreement. Contractor and all Subcontractors must enroll and participate in the federal E-Verify Program prior the performance of any part of the Work and appropriately screen all individuals performing any part of the Work. Proof of enrollment and participation must be provided to the JEA Representative upon request.

Non-discrimination. Contractor represents that it has adopted and shall maintain throughout the Term a policy of nondiscrimination against employees or applicants for employment on account of race, religion, sex, color, national origin, age or handicap, in all areas of employee relations. Contractor shall, on written request from JEA, allow JEA reasonable access to Contractor’s records of employment, employment advertisement, application forms and other pertinent data and records for the purpose of investigation to ascertain compliance with the nondiscrimination provisions of the Agreement; provided however, Contractor shall not be required to produce, for inspection, records covering periods of time more than one year from the effective date of the Agreement. Contractor shall comply with the following: (i) the provisions of Presidential Order 11246, as amended, and the portions of Executive Orders 11701 and 11758 as applicable to Equal Employment Opportunity; (ii) the provisions of section 503 of the Rehabilitation Act of 1973, as amended, and the Americans with Disabilities Act (ADA); and the provisions of the Employment and Training of Veterans Act, 38 U.S.C. 4212 (formerly 2012). Contractor agrees that if any of the Work of the Agreement will be performed by a Subcontractor, then the provisions of this subsection shall be incorporated into and become a part of the subcontract.

Compliance with JSEB Requirements. To the extent applicable, Contractor shall achieve the JSEB participation requirement of [●]% for the Scope of Work, except as allowed under the good faith efforts exception as defined in the City of Jacksonville Ordinance. In no case shall Contractor make changes to the JSEB firms listed in Exhibit J, revise the JSEB Scope of Work or Dollar Amount of Work as stated in Exhibit J without prior written notice to the JEA Project Manager and JEA Manager Supplier Diversity Programs, and without subsequent receipt of written approval from JEA Project Manager and JEA Manager Supplier Diversity Programs. JSEB firms that qualify for this Agreement are those shown on the current City of Jacksonville JSEB Directory appearing at https://jaxseb.coj.net. Certification of JSEB firms must come from the City of Jacksonville. No other agency or organization is recognized for purposes of this Contract. The City of Jacksonville requirements, as outlined in the City of Jacksonville Ordinance relating to JSEBs, shall apply in their entirety to this Agreement. Where the City of Jacksonville ordinance refers to “Chief”, it shall be construed to mean, for purposes of this Agreement, JEA's Chief Procurement Officer. In a like manner, where it refers to “City”, or “City of Jacksonville”, it shall be construed to mean JEA. Use of brokering, as defined in the City of Jacksonville Ordinance, or other techniques that do not provide a commercially useful function are strictly prohibited as means of achieving the JSEB participation requirements of this Agreement. Only the amount of fees or commissions charged by a JSEB for providing a bona fide service such as professional, technical, consultant, or managerial services, or for providing bonds or insurance specifically required for the performance of a contract shall be counted towards a JSEB participation requirement, provided the fee is reasonable and not excessive as compared with fees customarily charged for similar services. Payment terms for participating JSEB firms shall be the same or better than the payment terms Contractor receives from JEA, except that in all cases JSEB firms shall be allowed to submit invoices to Contractor at least bimonthly, and Contractor shall pay proper invoices no later than three (3) days after its receipt of JEA payment. Contractor shall obtain written approval from the JEA Project Manager and JEA Manager Supplier Diversity Programs prior to withholding any payment from the JSEB firm. Any solicitation award with a JSEB participation requirement may be subject to contract compliance per the details outlined on the List of Subcontractors Form. Contractor will be required to self-report all payments made to the JSEB Subcontractors. Reporting of Diverse Subcontractors (Tier 2 and Tier 3) shall be optional. If Contractor does not comply with the JSEB participation requirement established herein, Contractor must submit documentation as JEA’s request describing in detail its good faith efforts to comply with the JSEB participation requirement set forth in this Section. This documentation shall include at a minimum the following items:

Contractor shall contact the JEA Manager Supplier Diversity Programs for assistance when all independent attempts (emails, phone calls, faxes and letters) to contact qualified JSEB firms have failed and shall do so in adequate time for JSEB firms to be identified and to allow JSEB firms adequate time in which to respond.

A written and signed statement describing the level of effort for each of the requirements listed below, including dates and times, people whom Contractor contacted and phone numbers to enable JEA to confirm good faith efforts.

Emails and copies of written solicitations of participation Contractor sent to qualified JSEB firms, showing adequate response time was provided, defining the scope and nature of the work the JSEB firm is asked to perform, Contractor contact information for questions and follow-up, and an offer to meet to review plans, specifications and scope.

A statement of the Contractor’s efforts to negotiate a suitable agreement with JSEB firms including call logs showing participants, dates, times, topics discussed, and open issues.

A statement of Contractor’s efforts to help qualified firms that may require assistance in obtaining bonding, insurance, financing, technical support, procedural information, or other items necessary to compete for and perform the Work.

For each offer received from a qualified JSEB firm but rejected by Contractor, a statement explaining why such JSEB firm was not utilized by Contractor.

For each qualified JSEB firm contacted but considered unqualified by Contractor to perform a portion of the Work, a statement of the reasons Contractor considered firm to be unqualified.

- Failure by Contractor to contact the JEA Manager Supplier Diversity Programs as required herein will be considered when determining if Contractor has made a good faith effort. Contractor understands and agrees that receipt of a lower bid from a non-JSEB qualified firm, will not in and of itself, be sufficient reason to justify failing to meet the JSEB requirements of this Agreement. The determination as to whether Contractor made a good faith effort in trying to achieve the JSEB participation requirement of this Agreement will be made solely by JEA.

Scheduling. Contractor shall coordinate the scheduling of the Work, including working hours and workdays, with JEA and shall perform the Work in accordance with JEA’s scheduling requirements.

Meetings and Public Hearings. Contractor will, upon request from JEA, attend all meetings and public hearings as directed by JEA.

[Required Federal Contract Clauses. Contractor shall cause all of Contractor’s Personnel to comply with the Required Federal Contract Clauses as set forth in Exhibit S.]

Care of JEA Customers. Contractor shall cause all of Contractor’s Personnel to comply with the policies outlined in Exhibit R for the care of JEA’s customers.

Contractor’s Taxes.  Except as otherwise provided in Section 3.5, as part of the Work, Contractor shall administer and pay, and the Contract Price already includes, all sales, use, gross receipts, excise, income, value-added, withholding and other taxes, and all import, export and other duties and tariffs, and any other similar taxes and duties (including penalties and interest related to such taxes): (a) imposed by any taxing authority on Contractor or its Subcontractors for the purchase, transportation, exportation, importation, or use of materials, supplies, equipment (excluding the JEA Furnished Equipment) to be incorporated in the Facility or provided by Contractor or any Subcontractor in connection with the Work; (b) imposed by any taxing authority upon services or labor provided by Contractor or any Subcontractor in connection with the Work; (c) otherwise imposed by any taxing authority on or in connection with the performance of the Work; and/or (d) imposed by any taxing authority upon or measured by Contractor’s receipts hereunder or by wages earned by employees of Contractor or any Subcontractor (“Contractor’s Taxes”).  Contractor shall furnish to the appropriate taxing authorities all required information and reports in connection with all such Contractor’s Taxes. To the extent JEA is obligated under Applicable Laws to pay any of Contractor’s Taxes, Contractor shall: (i) furnish to JEA all information and reports required to be furnished to the appropriate taxing authorities in connection with all such Contractor’s Taxes; and (ii) reimburse JEA for the full amount of such Contractor’s Taxes paid by JEA.

Permitting.  Unless otherwise specified in the Contract Documents, Contractor shall secure, maintain, post as required, and pay for Contractor Permits, including all building, plumbing, electrical, water, sewer, right-of-way, parking, roadway, railroad, shipping, freight, hazardous materials, and any other permits which may be required for performance of the Work in full compliance with all applicable laws, rules and regulations. Contractor shall perform all actions necessary to identify where permits are to be obtained and properly file for the permits, except as provided in Section 3.2. Contractor shall comply with all conditions of permits issued for the Work, either directly or indirectly, issued by federal, state, or local governmental agencies, which are hereby incorporated as part of these Contract Documents. Contractor shall be solely responsible for resolving any issues and bearing all expenses including any damages suffered by JEA that result from a finding of noncompliance during performance of the Work by any of the respective regulatory agencies including, but not limited to, all costs for delays, litigation, fines, fees of any kind, and other costs. Contractor shall comply with all conditions of permits issued for the Work, either directly or indirectly, issued by federal, state, or local governmental agencies, which are hereby incorporated as part of these Contract Documents. Contractor shall be solely responsible for resolving any issues and bearing all expenses including any damages suffered by JEA that result from a finding of noncompliance during performance of the Work by any of the respective regulatory agencies including, but not limited to, all costs for delays, litigation, fines, fees of any kind, and other costs.

Storage and Related Matters.  Contractor shall comply with all receipt, storage and maintenance provisions specified in the Scope of Work.  During the construction of the Facility, Contractor shall warehouse or otherwise provide appropriate storage, in accordance with manufacturers’ recommendations, for all materials, supplies, and equipment to be incorporated into the Facility, to be utilized as spare parts and/or required for permanent and temporary construction.

Construction Utilities, Chemicals and Consumables.

Construction and Start-up Utilities. As part of the Work, Contractor will be responsible for providing the temporary facilities and utilities necessary for the performance of the Work under this Agreement.  Such facilities shall include temporary office trailers or buildings, workshops, restrooms and warehouses.  As part of the Work, and except as provided in Article 3, Contractor will arrange and pay for all supplies of utilities as may be required by Contractor in connection with the Work, including all sources of water (demineralized, potable or otherwise) and sewer (including sanitary, storm and process).  Subject to JEA’s provision of a source for construction power as described in Section 3.6, Contractor will be responsible for providing, installing and maintaining all equipment, materials and systems to distribute that power to any areas of the Facility Site where the same must be utilized in order to perform the Work.  Contractor will arrange for adequate heating, cooling and ventilation of all enclosed work areas.

Chemicals and Consumables.  As part of the Work, and except as provided in Article 3, Contractor will arrange and pay for all supplies of chemicals and consumables in sufficient quantities to enable Contractor to perform the construction Work and start-up and commissioning of the Facility.  Contractor shall ensure that all such chemicals and consumables are stored in a compliant and safe manner while being used, and that they are removed from the Facility Site and disposed of in a safe and compliant manner once determined to be no longer needed. JEA will be responsible for procuring and providing any chemicals and consumables required for the operation of the Facility after the Transfer Time (or Takeover Time).

Temporary Closure of Roadways.  Contractor shall not close or obstruct any portion of a street, road, or private way without first obtaining permits from the appropriate agency. If any street or private way is rendered unsafe by the Contractor operations, Contractor shall make such repairs or provide such temporary ways and guards necessary for the protection and safety of persons on the Work and the public and for the orderly maintenance of traffic. All costs associated with temporary closure of roadways shall be included in Contract Price. Contractor shall notify the police and fire departments in writing if it will be necessary to close a street. Contractor shall copy JEA on all correspondence relating to street closure. Contractor shall notify the police and fire departments prior to closure of the street. Contractor shall be responsible for maintaining proper coordination with the proper authorities. Temporary closure of business entrances must be approved in writing by and coordinated with JEA.

Spare Parts and Special Tools.

Start-Up Spares.  As part of the Work, Contractor will procure, have available, and use as necessary all spare parts required for completion of the Work on the Balance of Plant Equipment, including all start-up spares required for the start-up, testing and initial operation of any component of the Balance of Plant Equipment.  Contractor shall leave any start-up spares for the Balance of Plant Equipment at the Facility Site after completion of start-up and testing of the Facility and such will be considered to be spare parts supplied to JEA under this Agreement, and title thereto will pass to JEA in accordance with Section 2.5.1.

Operational Spare Parts.  Prior to the date that is one hundred and eighty (180) Days before the then-scheduled date for Mechanical Completion, Contractor will provide JEA with a list of long-term operational spare parts for the Balance of Plant Equipment that are recommended by the vendors of any equipment comprising the Balance of Plant Equipment for the initial two (2) years of operation (“Operational Spare Parts”).  JEA may, in its sole discretion, procure any of such recommended  Operational Spare Parts directly from the vendors thereof or through Contractor pursuant to a Change Order.  JEA will make any such Operational Spare Parts so procured available to Contractor for use during the Work.  If Contractor uses any such Operational Spare Parts provided by JEA hereunder in order to perform the Work, Contractor will replace or order a replacement on an expedited basis as a condition of Substantial Completion and will replace such parts with identical parts prior to Final Completion.  Contractor will coordinate with JEA concerning the delivery and storage of Operational Spare Parts.

Special Tools.  As part of the Work, Contractor will procure, as necessary, all special tools required for completion of the Work for the installation and maintenance of the Balance of Plant Equipment (“Special Tools”).  Contractor will also procure and, as a condition precedent to the achievement of Substantial Completion, deliver such Special Tools to the Facility’s maintenance building or other JEA-designated location, and will as part of such delivery organize and catalogue the same. Special Tools shall include any key or lock opening devices, wrenches or sockets which are not available through a professional tool supplier (such as Snap-on) and fixtures to support disassembly of the relevant Balance of Plant Equipment. Contractor shall be permitted by JEA to utilize such Special Tools as necessary for the erection and installation of the Facility, and for the performance of any Warranty corrections, but Contractor shall be responsible for the risk of loss or damage to such Special Tools during such use and shall promptly replace any Special Tools lost or damaged during such use.

Prohibited Items.  Subject to and in accordance with Applicable Laws: (a) no person working on the Facility Site will possess firearms, weapons of any type, alcohol or illegal drugs or at any time be under the influence of alcohol or illegal drugs; (b) no person working on the Facility Site shall have an expectation of privacy in any area of the Facility, including any desk, filing cabinet, computer, locker, office, room, or closet, or in any personal possession they bring into the Facility, including any briefcase, lunchbox, purse, bag, or backpack; (c) Contractor shall, where reasonable suspicion exists, conduct periodic random searches of on-site Facility areas, including desks, filing cabinets, lockers, offices, rooms and closets, for the illegal presence of firearms, weapons, or the presence of alcohol or illegal drugs; (d) Contractor shall, where reasonable suspicion exists, seek to conduct a search of any personal possession brought into the Facility, including any briefcase, lunchbox, purse, bag, or backpack for illegal presence of firearms, weapons, or other presence of alcohol or illegal drugs; and (e) Contractor shall enforce a strict requirement for the immediate removal of any prohibited items and for the removal and permanent expulsion from the Facility Site of any person that at any time is found in possession of any such items.

Personnel Training.  Commencing as early as necessary in order to support the start-up and testing operations of the Balance of Plant, Contractor shall provide training to JEA’s operating staff in the operation and maintenance of all components equipment comprising the Balance of Plant, as further described in Section 01100.1.2.12 of the Scope of Work. Contractor will provide JEA with at least one hundred eighty (180) Days’ prior written notice of the date on which the Contractor intends to commence such training. All such training must be completed as a condition precedent to achieving Mechanical Completion. Contractor shall provide appropriate training manuals and other written materials to each attendee as part of the training program.  Contractor shall coordinate the training schedule and number of attendees with JEA.  JEA will have the right to video tape Contractor training for future reference and use in retraining of plant personnel.

Start-Up and Initial Operation; Facility Testing.

Start-Up and Initial Operation. The Work shall include management responsibility for the start-up and initial operation of the Balance of Plant, and the calibration of the applicable Balance of Plant Equipment controls through the Transfer Time (or Takeover Time, if applicable). JEA will cause permanent plant staff to be available to Contractor to use in performing such operational services as further described in Section 3.7.1. Contractor will provide and be responsible for all labor and personnel for any repairs, adjustments or other non-operational Work required in connection with such start-up and initial operation.  JEA will have the opportunity to participate in all start-up meetings, including daily meetings. JEA will be permitted to have its own and its designees’ personnel (including personnel of JEA’s Engineer) on the Facility Site to observe and verify all start-up and synchronization activities.  During start-up, Contractor shall manage, control, operate, and maintain the Facility in a manner consistent with Prudent Industry Practices, the Operation and Maintenance Manual, Applicable Permits, and Applicable Laws.

Facility Testing.  The Work shall include the testing responsibilities described in Article 7.  JEA will cause permanent plant staff to be available to Contractor to use in performing such testing as further described in Section 3.7.1.

Clean-Up and Waste Disposal.

During Work’s Progress.  During the performance of the Work, Contractor shall keep the Facility Site and the surrounding area clean and free from accumulations of waste materials, rubbish and other debris resulting from the Work. Contractor shall dispose of such items in accordance with all Applicable Laws and Applicable Permits and shall permit PIE Supplier Personnel to utilize any waste disposal containers provided by Contractor without cost. If Contractor fails to clean the premises as required above, JEA shall notify Contractor and allow for ten (10) Days for Contractor to clean the premises.  If Contractor fails to clean the premises during that ten (10) Day period, JEA may at its discretion (and without relieving Contractor of its obligations) do such cleaning as it may deem necessary or appropriate and charge for the costs of performing such work either directly or by offset against any payment due Contractor under this Agreement.  Prior to Substantial Completion, Contractor will remove all Contractor’s tools, construction equipment, machinery, and surplus materials from the Facility Site, except for those items as will be required by Contractor to complete the Punch-List. Promptly following Substantial Completion, Contractor will remove all Contractor’s tools, construction equipment, machinery and surplus materials from the Facility and the Facility Site, except for those items as will be required by Contractor to achieve Final Completion (which will until then be stored by Contractor in such areas on the Facility Site as directed by JEA when not in use by Contractor).

Prior to Final Completion.  As a condition of Final Completion, Contractor will: (a) remove and dispose of all remaining waste materials, rubbish, and other debris resulting from the Work in accordance with all Applicable Laws and Applicable Permits; (b) remove from the Facility and the Facility Site all of Contractor’s tools, construction equipment, machinery, and surplus materials; and (c) leave the Facility Site in a clean and safe condition.

Safety Precautions.  Contractor shall have a comprehensive safety program that governs all of Contractor’s and its Personnel’s activities at the Facility Site in connection with its performance of the Work. The safety program shall be reflected in writing in the form of a written project safety manual (the “Project Safety Manual”) that shall be submitted to JEA within the earlier of twenty (20) Business Days after the Effective Date or the commencement of any Work at the Facility Site. Contractor’s Project Safety Manual shall, at a minimum: (a) meet or exceed the standard of care for such programs as established by nationally recognized firms which provide goods and services of a similar nature; (b) strictly comply with the requirements set forth in the Scope of Work and all Applicable Laws and Applicable Permits; (c) include a detailed plan that allows for JEA and PIE Supplier Personnel to work on and operate, and to protect the completed installations after the Transfer Time (or Takeover Time, if applicable); (d) include a detailed safety plan as to Contractor’s Personnel performing any Work on the Facility after the Transfer Time (or Takeover Time, if applicable); (e) include provisions for all Contractor’s Personnel to complete JEA’s site orientation program; and (f) include a program to maintain a drug and alcohol-free workplace.  If JEA determines that the Project Safety Manual does not meet the foregoing standards, it shall notify Contractor of such deficiencies in writing and Contractor shall immediately correct such deficiencies in the Project Safety Manual and implement the corrections into the performance of the Work at the Facility Site. Contractor shall submit any revisions to the Project Safety Manual to JEA for review prior to instituting such revisions; it being expressly understood, however, that any review of, comments upon or approval of the Project Safety Manual (or any revisions to said Project Safety Manual) by JEA, or any failure by JEA to object to any matter in the Project Safety Manual, does not relieve Contractor from the sole and entire responsibility for the safety and security of the Work, including its completeness, suitability and appropriateness for all purposes, or impose any liability on JEA the safety and security of the Work. Contractor shall initiate, maintain and supervise all reasonable safety precautions and programs in connection with the performance of the Work in accordance with the Project Safety Manual, Applicable Laws, and Applicable Permits and shall take all reasonable precautions for the protection and safety of, and shall provide all reasonable protection to prevent harm, damage, injury or loss (including ecological harm or nuisance resulting from contamination, noise or other causes arising from the performance of the Work) to: (i) all Persons employed by Contractor or Subcontractors or any other contractors in connection with the Work and all other Persons who may be affected thereby; (ii) all materials and equipment or other personal property on the Facility Site or in the vicinity thereof; and (iii) the real property comprising the Facility Site and any real property in the vicinity thereof. Contractor will have a designated safety and health coordinator present on the Facility Site at all times when Work is being performed thereon. This individual’s primary daily responsibility with respect to the Work will be monitoring and ensuring compliance with the Project Safety Manual and the requirements of this Section 2.2.17. The Project Safety Manual shall be reviewed on an annual basis, and as changes to the planned Work arise, to determine if any improvements or adjustments should be made to the Project Safety Manual, and, if so, Contractor shall submit the necessary improvements or adjustments for JEA’s approval.

Emergencies. In the event of any emergency endangering persons or property, Contractor shall take such action as may be necessary to prevent, avoid or mitigate such injury, damage or loss and shall, as soon as possible, but in no event more than twenty-four (24) hours, report any such incidents, including Contractor’s response, to JEA. Whenever Contractor fails to take precautions for the protection of the public, the Work, or of structures or property on or adjacent to the Facility, Facility Site, JEA may, but shall be under no obligation to, take such action as is reasonably necessary under the circumstances. The taking or provision of any such precautions or protection by JEA or its agents or representative shall be for the account of Contractor and will not relieve Contractor of its obligations under this Agreement and Applicable Laws, and Contractor shall reimburse JEA for the reasonable cost thereof.

System-wide Emergency Events. In the event that a system-wide emergency arises during the Term of the Agreement for which JEA requires assistance from Contractor including, but not limited to, severe storms, large-scale fires, floods, and terrorist attacks, Contractor acknowledges the importance of JEA infrastructure and agrees to support, with all its resources, skills and capabilities, and the maximum extent possible, all restoration efforts of JEA. The JEA Project Manager shall notify Contractor when an emergency event occurs and Contractor agrees to mobilize its full resources immediately. In the event conditions are such that an emergency event is likely in progress, but Contractor has not been notified by the JEA Project Manager, Contractor shall make all efforts to contact the JEA Project Manager to determine if and how it should respond. JEA agrees to reimburse Contractor for its actual costs incurred as a result of supporting JEA during the emergency event, plus overhead and profit, not to exceed twelve percent (12%) of such costs.

Storm Preparedness. 	In the event of a Hurricane Warning, Tropical Storm Warning, or other large storm affecting the Facility Site, Contractor shall secure, or shall remove and store all equipment and materials at the Facility Site including, but not limited to, cones, barricades, lights and signs. Contractor shall begin taking such precautions as necessary to secure the Facility Site upon official issuance of mandatory evacuation of the area of the Facility Site, and no later than twenty-four (24) hours prior to predicted arrival of tropical storm or hurricane force winds, or when notified by the JEA Project Manager to do so. These activities are considered a regular part of the Work, regardless of the frequency they are required.

Background Checks and other Security Policies.

Contractor, at its expense, shall conduct appropriate background checks and screen each individual who will provide services to JEA as a part of the Work or who will have access to JEA’s computer systems, either through on-site or remote access.  The minimum background screening process shall include, but not be limited to, the following checks: (a) Social Security Number (SSN) Trace; (b) Criminal Records (County and State Criminal Felony and Misdemeanor, National Criminal Database, Federal Criminal); (c) Background checks undertaken by JEA for its own employees who have duties similar to the duties of the Contractor’s Personnel; and (d) Background checks which may be required pursuant to applicable background screening policies adopted by JEA from time to time. The background screening must be conducted prior to the employee providing any services or performing any Work for JEA. JEA has the right to require more regular background checks and has the right to require that Contractor provide background check results to JEA. JEA shall have the right to audit Contractor’s background check process to ensure compliance with JEA standards. If, at any time, Contractor discovers that an individual providing services to JEA as a part of the Work has a criminal record that includes a felony or misdemeanor, Contractor shall immediately inform JEA and JEA will assess the circumstances surrounding the conviction, time frame, nature, gravity and relevancy of the conviction to the job duties. JEA, in its sole discretion, shall determine whether the individual will be placed on, or terminated from, a JEA assignment. Additionally, all individuals providing services to JEA shall have the responsibility to self-disclose any misdemeanor or felony conviction that occurs while assigned to JEA within three business days of the conviction. If Contractor learns of any such conviction, Contractor shall notify JEA immediately. Contractor shall comply with all applicable laws and regulations governing the conduct of background checks, including but not limited to the Fair Credit Reporting Act (FCRA).

Onsite law enforcement shall be provided by Contractor as needed to ensure safe working conditions for Site Personnel. Any Work performed at night shall have onsite law enforcement present. Contractor shall submit with each Application for Payment verification of the number of hours of law enforcement utilized during each pay period, including any associated fees. Contractor agrees to invoice JEA for law enforcement at its cost with no markup.

JEA Access Badge. If the Work requires an individual to access JEA’s facilities or properties, the JEA Project Manager or other JEA Representative will determine whether or not such individual must have a JEA access badge prior to accessing JEA facilities or properties.  This determination will be made based upon the business need and in accordance with JEA’s applicable security policies and procedures.  In no event shall individuals share JEA access badges. Individuals issued an access badge must adhere to all of JEA’s security badge usage policies and procedures. Violation of the provisions of this Section or any of JEA’s security policies may result in immediate termination of the Agreement. In particular, JEA shall be notified within 24 hours of a lost or stolen JEA access badge or when an individual leaves the Contractor or any subcontractor. Contractor will bear any costs associated with issuance, and production, of any lost or stolen JEA access badge. Contractor is required to report all badge loss, or termination, notifications to the JEA Representative and JEA Security. JEA Security can be contacted at (904) 665-8200 and security@jea.com. Failure to make the reports required in this section may result in significant regulatory fines and penalties. Contractor shall be responsible for all such costs and JEA shall have the right to immediately terminate the Agreement. The provisions in this Section shall apply to Contractor’s Subcontractors and agents performing any of the Work and shall be included in Contractor’s contracts with its Subcontractors for any part of the Work.

Data Ownership, Protection and Location. JEA shall own all right, title and interest in all data of JEA and JEA's customers that relate to the Work. Contractor shall only access JEA's data and JEA's customers’ accounts and data if (i) required to provide the Work, (ii) required in response to service or technical issues, (iii) required by the express terms of the Agreement, or (iv) at JEA's written request. Protection of personal privacy and data shall be an integral part of the Work to ensure that there is no inappropriate or unauthorized use of data of JEA or JEA's customers at any time. Contractor shall safeguard the confidentiality, integrity, and availability of all data of JEA and its customers and comply with the following:

Contractor shall implement and maintain appropriate administrative, technical and organizational security measures to safeguard against the unauthorized access, disclosure or theft of Personal Data or Non-Public Data. For the purposes of the Agreement, “Personal Data” shall mean data that includes information relating to a person that identifies the person by name and has any of the following personally identifiable information: government-issued identification numbers (e.g., Social Security, driver's license, passport); financial account information including account number, credit or debit card numbers; or protected health information relating to a person. “Non-Public Data” shall mean data, other than Personal Data, that is not subject to distribution to the public as public information and is deemed to be sensitive and confidential because it is exempt by statute, ordinance or administrative rule from access by the general public as public information;

All data obtained by Contractor under the Agreement shall become and remain the property of JEA:

            - (i) 	All Personal Data and Non-Public Data shall be encrypted at rest and in transit with controlled access. Unless otherwise agreed in writing by the Parties, Contractor shall be responsible for encryption of the Personal Data and non-Public Data;

            - (ii) 	At no time shall any Personal Data or Non-Public Data of JEA or its customers be copied, disclosed or retained by Contractor or any party related to Contractor for subsequent use in any transaction that is not a part of the Work;

            - (iii) 	Contractor shall not use any Personal Data, Non-Public Data or any other information collected in connection with the Agreement for any purpose other than providing the Work. Contractor will prevent its employees, other than employees with a need to know, from gaining access to JEA's data and information. Contractor will direct and take all reasonable steps to insure that any Contractor Personnel who encounters any such information during the course of performing Contractor responsibilities under the Agreement shall maintain the confidentiality of such information, which shall not be passed onto other Contractor Personnel. Contractor shall also enforce separation of job duties, require commercially reasonable non-disclosure agreements, and limit staff knowledge of JEA data to that which is absolutely necessary to perform job duties. Contractor shall provide the Work solely from data centers in the United States.  Storage of JEA data at rest shall be located solely in data centers within the United States. Contractor shall not allow its personnel or its subcontractors to store JEA and JEA customer data on portable devices, including personal computers, except for devices that are used and kept only at its data centers in the United States. Contractor shall permit its personnel and subcontractors to access JEA and JEA customer's data remotely only as required to provide technical support. Contractor shall deploy reasonable steps and safeguards as part of a network security program in accordance with accepted industry practices, including but not limited to, Purchasing Card Industry-Data Security Standards (PCI-DSS), to prevent unlawful hacking to gain surreptitious access into JEA's and JEA's customer’s data.

Contractor shall promptly notify JEA within forty-eight (48) hours of any confirmed breaches or issues regarding the security of systems that maintain JEA or JEA's customer data, or within twelve (12) hours in the event of a ransomware incident. However, any such notification by Contractor shall not affect Contractor’s obligations to secure JEA's data as provided under the Agreement. Contractor shall notify JEA within forty-eight (48) hours if it learns that JEA or any of JEA's customers has been, have been, or may have been, the subject of a Security Incident (defined below) of any kind which may compromise data of JEA or its customers, except in the event of a ransomware incident, in which case Contractor shall notify JEA within twelve (12) hours of such incident. In any such event, Contractor shall: (i) investigate the incident(s) and provide a report to JEA within forty-eight (48) hours; (ii) conduct a forensic investigation to determine a cause and what data/systems are implicated; (iii) provide daily updates of its investigation to JEA and permit JEA reasonable access to the investigation; (iv) communicate and cooperate with JEA concerning communication with outside parties such as law enforcement and media; and (v) cooperate with JEA in determining whether and how notice, if any, will be provided to JEA's customers with all applicable laws and regulations.

The term “Security Incident” means the potentially unauthorized access by non-authorized persons to Personal Data or Non-Public Data that Contractor believes could reasonably result in the use, disclosure, or theft of unencrypted Personal Data or Non-Public Data of JEA or its customers within the possession or control of Contractor. If a Data Breach (defined below) with respect to Personal Data or Non-Public data has occurred, Contractor shall promptly implement necessary remedial measures and document responsive actions taken related to the Data Breach, including any post-incident review and actions taken to make changes in business practices in providing the Work, if necessary. If a Data Breach is a result of Contractor’s breach of its obligation to encrypt Personal Data or Non-Public Data or otherwise prevent the release of Personal or Non-Public Data or Contractor’s failure to comply with any of the security requirements provided in this Agreement, Contractor shall bear the costs associated with (i) the investigation and resolution of the Data Breach; (ii) notifications to individuals, regulators or others required by state law; (iii) a credit monitoring service required by state or federal law; (iv) a website or toll-free number and call center for affected individuals required by state law; and (v) completing all corrective actions as reasonably determined by Contractor based on root cause. The term “Data Breach” means the unauthorized access by a non-authorized person or persons that results in the use, disclosure or theft of unencrypted Personal Data, Non-Public Data or JEA's customer information.

In the event of the expiration or early termination of this Agreement, Contractor shall implement an orderly return of JEA's data in a mutually agreeable format at a time agreed to by JEA and Contractor, or upon JEA's request, Contractor shall secure the disposal of all JEA data. During any period of service suspension, Contractor shall not take any action to intentionally erase any JEA data or its customers. In the event of termination of any services or Agreement in its entirety, Contractor shall not take any action intentionally to erase any data of JEA or its customers except as mutually agreed upon in writing by Contractor and JEA. Upon JEA request, Contractor shall securely dispose of all request data in all its forms.

JEA Critical Infrastructure Protection (CIP).

Pursuant to federal regulations, JEA is required to implement Critical Infrastructure Protection (CIP) and comply with NERC/FERC reliability standards for identified assets (collectively the “Assets”). Assets include both physical and cyber Assets that are essential for JEA to maintain the integrity of the bulk electric system. Therefore, Contractor must ensure that all individuals that have access to any Assets meet all requirements of JEA as agreed to by both Parties in this Agreement, including, but not limited to the background screenings required by this Agreement, prior to the individual performing any Services for JEA. The specific Assets an individual will access will determine the specific JEA training and criminal background check that will be required before an employee will be approved to perform Services for JEA. Contractor be responsible for the hourly labor costs of its Personnel associated with completion of the training. The provisions of this Section and the immediately preceding section regarding Data Ownership shall apply to all of the Contractor’s Subcontractors and agents, and shall be included in Contractor’s contracts with its Subcontractors for any part of the Work. JEA reserves the right to modify these terms if the applicable regulations change or additional regulations become applicable. JEA will provide sufficient notice in advance for Contractor to review the new terms and come to an agreement with JEA to comply with JEA’s requirements related to the updated regulations.

If applicable for all or any part of the Work, Contractor must respond to JEA’s supply chain risk questionnaire. Contractor’s response to the questionnaire shall be provided directly to JEA. Contractor will provide supporting documentation but is not obligated to provide internal policy and procedure documents. Contractor shall assist JEA in complying with the requirements of NERC Reliability Standard NERC CIP-013 by satisfying the requirements (i)-(vii) below Contractor shall reasonably coordinate with JEA in JEA’s compliance with any NERC CIP requirements regarding Transient Cyber Assets (non-managed by JEA) used as part of the Work and future vendor remote access requirements as part of CIP-003 effective April 2026. Contractor must have in place appropriate cyber security processes, including, but not limited to, addressing the following:

- Notification by Contractor to JEA, within seventy-two (72) hours or sooner, of any Contractor Personnel who have access to JEA facilities, who have been terminated, retired or ceased working on JEA projects;

- Notification by Contractor of confirmed Contractor-identified incidents that have compromised the cyber security of the products or Services provided to JEA under this Agreement that pose a cyber security risk to JEA;

- Coordination of responses to confirmed Contractor-identified incidents related to the products or Services provided to JEA under this Agreement that pose cyber security risk to JEA;

- Notification by Contractor when remote or onsite access should no longer be granted to Contractor representatives;

- Disclosure by Contractor of known vulnerabilities related to the products or Services provided to the JEA;

- Method for verification of software integrity and authenticity of all software and patches provided by the Contractor for use in JEA’s Bulk Electric System’s Cyber System; and

- Coordination of controls for (i) Contractor-initiated Interactive Remote Access, and (ii) system-to-system remote access with Contractor.

Medical Facilities.  Contractor shall provide and maintain adequate first aid facilities, equipment, and personnel at the Facility Site in accordance with Applicable Laws and Prudent Industry Practice. Such facilities, equipment, and personnel: (a) shall be sufficient to treat on-site injuries or illnesses that may occur during performance of the Work; (b) shall be available to Subcontractor, PIE Supplier, JEA, and any other Personnel at the Facility Site; and (c) shall be available at all times during working hours. Contractor shall ensure that all first aid services are staffed by appropriately qualified personnel and are equipped with necessary supplies and equipment to provide immediate and effective treatment. Contractor shall also prepare, implement, and maintain, as part of the Project Safety Manual, emergency response procedures and protocols, including Facility Site access, high or confined space rescues, and transportation arrangements for injured or ill personnel requiring emergency medical treatment.

Security. Contractor shall be responsible for the security of the Facility Site at all times from Full Notice to Proceed until 12:00:01 AM on the Day after the Day when JEA delivers to Contractor the certificate that the requirements for Substantial Completion have been achieved (or when Substantial Completion has been deemed achieved) as described in Section 6.4.3.  Within ten (10) Days after the Effective Date, Contractor will provide JEA with an initial draft of the project security plan that Contractor intends to implement to secure the Facility during the Work. Contractor’s draft security plan shall, at a minimum: (a) meet or exceed the standard of care for such plans as established by nationally recognized firms which provide goods and services of a similar nature; (b) strictly comply with all requirements of the Scope of Work, Applicable Laws and Applicable Permits; and (c) provide for reasonable access of PIE Supplier Personnel to the Facility Site. Such plan will include a method acceptable to JEA for controlling, identifying and monitoring the employees of Contractor, the Subcontractors, PIE Supplier, and JEA (without additional cost) in all areas in which the Work is to be performed. If JEA determines that the draft security plan does not meet the foregoing standards, it shall notify Contractor of such deficiencies in writing and Contractor shall immediately correct such deficiencies in such plan and implement the corrections into the performance of the Work.  The final, JEA-approved security plan will be the “Project Security Plan.”  Contractor will implement, maintain and at all times cause Contractor’s Personnel to comply with the Project Security Plan. The Project Security Plan shall be reviewed on an annual basis, and as changes to the planned Work arise, to determine if any improvements or adjustments should be made to the Project Security Plan, and, if so, Contractor shall submit the necessary improvements or adjustments for JEA’s approval.

Hazardous Materials.

Preventative Measures; Notice Requirements.  Contractor will take all reasonable measures necessary to prevent the Release of any Hazardous Materials at the Facility Site or adjacent areas in violation of Applicable Laws, including compliant storage and containment facilities. Contractor will submit to JEA a Material Safety Data Sheet at least ten (10) Days prior to the delivery of any Hazardous Materials to the Facility Site and will also maintain additional copies of such Material Safety Data Sheets in a central location at the Facility Site and readily accessible to all Personnel at the Facility Site. Contractor will immediately notify JEA of: (a) any Releases of Hazardous Materials that occur in connection with the performance of the Work; (b) any and all violations and any and all investigations, actions, claims, suits, notices of violation, fines, penalties, orders, and other proceedings related to material violations or alleged material violations of Environmental Laws, including but not limited to Permits issued thereunder, which are asserted against Contractor or any of Contractor’s Personnel in connection with the Work or their activities on or in connection with the Facility Site; (c) Contractor’s discovery of any Hazardous Materials at the Facility Site or adjacent areas; and (d) all developments with respect to Section 2.2.20.1(a), 2.2.20.1(b), and/or 2.2.20.1(c).

Contractor Releases; Removal Obligations.  In the event Contractor or its Personnel Releases any Hazardous Material brought to or generated at the Facility Site by Contractor or its Personnel or negligently Releases any other Hazardous Material at the Facility Site, then Contractor will immediately cease performance of any Work in the area affected and report the condition to JEA in writing.  Contractor will not thereafter resume performance of the Work in the affected area except with the prior written permission of JEA.  Without prejudice to Contractor’s rights under Section 11.2(c), Contractor will at its own expense be responsible for undertaking the activities required to collect (including excavation, if necessary), test (both the ground, groundwater, surface water and removed materials), containerize, remove from the Facility Site and areas adjacent thereto, and properly dispose of, in a manner acceptable to JEA and in compliance with this Agreement, all Applicable Laws and all Applicable Permits, all Hazardous Materials brought to or produced at the Facility Site by Contractor or its Personnel in connection with the performance of the Work.  Contractor shall prepare and provide to JEA copies of any reports, studies, assessments, manifests, or other documentation generated in connection with the actions described above, and Contractor shall not list JEA as the generator of any Hazardous Materials removed from the Facility Site. If Contractor fails to promptly undertake its obligations under this Section, JEA may notify Contractor concerning such failure, and if Contractor thereafter fails to promptly commence and diligently continue such activities, then JEA may undertake and complete the same at Contractor’s expense.

Pre-Existing Hazardous Materials.  In the event Contractor encounters material on the Facility Site that it reasonably believes to be a Hazardous Material that existed prior to the Effective Date or was thereafter brought to the Facility Site by JEA or JEA’s Personnel (“Pre-Existing Hazardous Materials”), then Contractor will immediately cease performance of any Work in the area affected and report the condition to JEA in writing.  Contractor will not thereafter resume performance of the Work in the affected area except with the prior written permission of JEA.  Contractor’s rights to receive a Change Order pursuant to this Section are set forth in Section 9.3.5.

Protection of Property.

Protection of Property, Materials and Equipment. Contractor will take actions reasonably necessary to avoid causing damage to any, or interference with the siting, operation or maintenance of any, all public and private property (including all parallel, converging and intersecting electric lines and poles, telephone or fiber optic lines and poles, roads, highways, waterways, railroads, sewer lines, natural gas pipelines, drainage ditches, culverts, buildings, structures, monuments, vehicles, trees, shrubs, lawns, walks and pavements) on, along, adjacent to or near the Facility Site as may be impacted by the Work.  If any of Contractor’s Personnel directly or indirectly causes any damage to any such property, then Contractor will immediately, at its own expense, repair, rebuild or otherwise restore the same or otherwise make whole such damage in a manner acceptable to the owner thereof.  If Contractor fails to commence the repair of such damage as set forth above, and/or fails to diligently pursue such repair, then JEA, after ten (10) Days’ prior written notice to Contractor, provided Contractor has not commenced such repair during such ten (10) Day period, may elect to repair such damages and to deduct from payments due or to become due to Contractor amounts paid or incurred by JEA in correcting such damage.

Maintenance of Traffic. Contractor, as applicable to specific tasks, when required by the governing agency such as the City of Jacksonville or the Florida Department of Transportation, shall maintain traffic in accordance with an approved Maintenance of Traffic (“MOT”) plan (“MOT Plan”) submitted by Contractor to JEA, for Work performed on streets, roads, private ways, and walks. Contractor shall be responsible for all costs associated with MOT and the MOT Plan. All costs for MOT and the MOT Plan will be subject to JEA review and reimbursable at cost. Contractor shall assume full responsibility for the adequacy and safety of provisions associated with the MOT Plan. Contractor shall be solely responsible for the placement, maintenance and removal of the minimum number of devices required by the MOT Plan, or specified by the Florida Department of Transportation, for the control of traffic at the Facility Site including, but not limited to signs, cones, lights, barricades, concrete barrier walls, police officers, flaggers, etc. (“MOT Items”).

Interference with Railroads. Contractor shall not build across, into, over or under, either temporarily or permanently, any portion of a railway or railway right-of-way without first obtaining all required permits. If Contractor’s operations render any railroad unsafe, Contractor shall immediately notify the JEA Project Manager and the railroad owner and take appropriate actions and such temporary safeguards as required to protect life, limb, and property, and to maintain orderly traffic. Contractor shall procure all railroad permits required for the Work beyond those procured by JEA and the costs for such permits shall be included in the Contract Price. All costs associated with railroad fees for railroad flagmen, watchouts, inspectors, supervisors, any additional training of Contractor’s Personnel that is required by applicable laws, rules and regulations when performing Work in association with railways, any certifications required for successful completion of the Work and all other associated costs shall be included in the Contract Price.

Wetlands; Wildlife. Contractor understands and agrees that the Facility Site may include wetlands or other environmentally sensitive areas. Contractor shall not enter these areas during the performance of its Work, unless specifically authorized by the JEA Project Manager and appropriate state and federal permits have been obtained. Contractor’s Personnel shall not endanger wildlife species or domestic animals of any kind.

QA/QC Manual.  Contractor has sole responsibility for the quality assurance and quality control of the Work, including all work of its Subcontractors. To accomplish this, Contractor shall have in effect at all times a quality assurance program that will ensure that Contractor and its Subcontractors adhere to the requirements of this Agreement, including the standards set forth in Section 2.4.  Contractor shall, within twenty (20) Days after the Effective Date, deliver to JEA the following manuals or plans prepared by Contractor, which will outline Contractor’s proposed quality assurance and quality control programs: (a) a controlled copy of Contractor’s quality assurance and quality control system manual; (b) a controlled copy of Contractor’s quality assurance and quality control procedures applicable to the Work; (c) an integrated project specific construction plan that identifies the process control plans that Contractor and its Subcontractors will apply to their activities at the Facility Site; and (d) a site specific quality control plan that will describe in detail all quality verification activities Contractor intends to perform.  Without limiting the foregoing, the quality assurance and quality control program will include: (i) a defined list of JEA witness, hold and inspection points; (ii) a schedule for the same that is compliant with the Baseline Project Schedule; and (iii) a requirement of prior notice for any on-site or off-site fabrication witness, hold and/or inspection points as set forth in Section 2.2.6.2. In connection with the foregoing, Contractor shall not proceed past an established witness, hold, and/or inspection point prior to the date specified therefor in the advance notice unless JEA has witnessed the activity to its satisfaction or has given its written approval for Contractor to proceed past such point.  When JEA is satisfied with such submittals, JEA will notify Contractor that the same shall constitute, in the aggregate, the “Approved QA/QC Manual.”  Contractor will provide JEA with five (5) copies of the Approved QA/QC Manual.  Contractor will follow the Approved QA/QC Manual throughout its performance of the Work, provided that the provisions of this Agreement shall always control over the provisions of the Approved QA/QC Manual.

Royalties and License Fees.  Contractor shall pay and at all times remain responsible for all royalties and license fees, if any, for materials, methods, processes, software and systems supplied by Contractor as part of the Balance of Plant Equipment.  In performing the Work, Contractor shall not supply or incorporate into the Facility any materials, methods, processes or systems which involve the use of any confidential information, intellectual property or proprietary rights which JEA or Contractor does not have the right to use.  Contractor shall timely notify JEA in writing of any claims that Contractor receives alleging infringement of patents or other proprietary rights that may affect Contractor’s performance of the Work or JEA’s operation of the Project.

Operation and Maintenance Manuals.  Not less than one hundred eighty (180) Days prior to the scheduled Substantial Completion Date (but in any event no later than four (4) weeks prior to the date that personnel training with respect thereto will be conducted in accordance with Section 2.2.14), Contractor will prepare in individually bound volumes and deliver to JEA for JEA’s approval two (2) hard copy sets of, and one (1) electronic copy of, a preliminary manual for the start-up, operation and maintenance of the Facility.  JEA will review this preliminary manual and provide Contractor with comments thereto.  Contractor will make all revisions to such manual as instructed by JEA, and once JEA is satisfied with the contents of such manual, JEA will deem it to be approved (such approved manual, the “Operation and Maintenance Manual”).  As a condition to the achievement of Final Completion, Contractor will prepare in individually bound volumes and deliver to JEA five (5) hard copy sets of, and one (1) electronic copy of, the final form of such Operation and Maintenance Manual.

Turnover Packages, Project Data Books and As-Built Drawings.  Contractor will create, maintain, update and compile Turnover Packages during the course of the Work and will (without duplication) deliver to JEA such Turnover Packages as with respect to Work then completed prior to, and as a precedent condition to, Mechanical Completion.  Turnover Packages will be provided in hard copy (five (5) copies per package) and electronic copy.  Contractor shall maintain the Project Data Books (in both hard copy format and electronic copy format) and shall update and revise the Project Data Books based upon equipment selection and final design of the Balance of Plant.  As a condition to Final Completion, Contractor shall provide five (5) hard copies of (and one (1) electronic copy of) the “as built” Project Data Books to JEA.

Other Work.  As part of the Work (and except as otherwise stated in the Scope of Work, Article 3 or Article 7 as being the responsibility of JEA) Contractor shall provide any other related services or items not specifically described in this Agreement if: (a) it reasonably may be inferred, by reference to other gas-fired power projects in the United States and in accordance with standards employed by leading contractors in the United States electric generation facility construction industry, that the providing of such additional work or item was contemplated as part of this Agreement; or (b) the providing of such additional work or item is necessary to make the Balance of Plant operable and capable of performing as specified in this Agreement.

Substitutions. Whenever materials or equipment are specified or described in the Contract Documents by using the name of a proprietary item or the name of a particular supplier, the naming of the item is intended to establish the type, function and quality required. Materials or equipment of other suppliers may be accepted by JEA’s Engineer if sufficient information is submitted by Contractor to allow JEA’s Engineer to determine that the material or equipment proposed is equivalent or equal to that named. Contractor shall make written application to JEA’s Engineer for acceptance thereof, certifying that the proposed substitute will perform adequately the functions and achieve the results called for by the general design, be similar and of equal substance to that specified and be suited to the same use as that specified. The application shall state that the evaluation and acceptance of the proposed substitute will not prejudice the Contractor’s completion of the Work within the time prescribed by the Agreement, whether or not acceptance of the substitute for use in the Work will require a change in any of the Contract Documents (or in the provisions of any other Agreement directly with JEA for Work on the Agreement) to adapt the design to the proposed substitute and whether or not incorporation or use of the substitute in connection with the Work is subject to payment of any license fees, royalties, permits or any other costs. All variations of the proposed substitute from that specified shall be identified in the application and available maintenance, repair and replacement service shall be indicated. The application shall also contain an itemized estimate of all costs that will result directly or indirectly from acceptance of such substitute, including costs of redesign and claims of other companies affected by the resulting change, all of which shall be considered by JEA’s Engineer in evaluating the proposed substitute. Requests for review of substitute items of material and equipment will not be accepted by JEA’s Engineer from anyone other than Contractor. JEA’s Engineer may require Contractor to furnish, at Contractor’s expense, additional data about the proposed substitute. If a specific means, method, technique, sequence or procedure of construction is indicated in or required by the Agreement, Contractor may furnish or utilize a substitute means, method, sequence, technique or procedure of construction acceptable to JEA’s Engineer, if Contractor submits sufficient information to allow JEA’s Engineer to determine that the substitute proposed is equivalent to that indicated or required by the Agreement. JEA’s Engineer will be allowed a reasonable time within which to evaluate each proposed substitute; such time shall not be deemed justification for an extension of Contractor’s time for completion of the Agreement. The approval or disapproval of any proposed substitute shall be subject to the sole and absolute discretion of JEA’s Engineer. No substitute shall be ordered, installed or utilized without JEA’s Engineer's prior written notice, which shall be evidenced by either a Change Order or an approved shop drawing. JEA may require reimbursement for the costs associated with JEA's evaluation of substitutions. JEA may require Contractor to furnish, at Contractor’s expense, a special performance guarantee bonds or other surety with respect to any substitution.

Delivery of Equipment. Shipping materials and equipment to be installed by Contractor shall be delivered by Contractor to the Facility Site or such other place as may be designated by JEA’s Project Manager.  Insofar as transportation conditions will allow, items shall be shipped complete and ready for installation. Where applicable, Contractor shall be responsible for obtaining any permits required for transportation to the Facility Site. For early shipments, Contractor shall provide written notice to JEA’s Project Manager. Upon approval of JEA’s Project Manager, a limited amount of temporary indoor storage space may be made available, but only for the Equipment that must be protected from the weather.  Equipment for which arrangements have been made for indoor storage, shall be packed separately and the container clearly marked "For Indoor Storage."  For equipment that will be stored indoors and that will require special storage precautions, the storage instructions shall be shown on the outside of each container, or in a durable envelope identified as containing storage instructions and attached to the container. In the event Contractor decides to utilize public or private property as a laydown area, Contractor shall enter into a written agreement with the entity who owns the property. JEA shall have access to all laydown areas. Upon submission of Contractor’s first Application for Payment to JEA, Contractor shall provide to JEA a copy of such signed written agreement. Contractor shall submit to JEA a letter of release from the entity in connection with Contractor’s Final Application for Payment to JEA.

Baseline Project Schedule, Progress Reports and Meetings; Recovery Plan.

Baseline Project Schedule; Monthly Progress Reports; Monthly Updated Schedule. Contractor will perform the Work in accordance with the Baseline Project Schedule.  Contractor will keep, and furnish to JEA; (a) Monthly Progress Reports that contain the information described in Section 01100.1.2.11 of Exhibit A-2; and (b) a Monthly Updated Schedule. Each Monthly Progress Report and Monthly Updated Schedule shall be submitted to JEA on or before the fifth (5th) Day of each month following the Effective Date.  The Monthly Updated Schedule will be provided in compliance with the requirements of Exhibit C.  Contractor will also hold progress meetings for JEA and its invitees on a monthly basis, or more frequently if JEA requires.  Contractor will also abide by the requirements of the schedule management specification set forth in Exhibit C.

Recovery Plan.

If at any time the Critical Path in a Monthly Updated Schedule evidences that Contractor is delayed by more than ten (10) Days in its adherence to the Critical Path progress toward the achievement of Mechanical Completion or Substantial Completion in accordance with the Baseline Project Schedule, then JEA may request in writing from Contractor to prepare a proposed plan that feasibly explains and displays how Contractor will, to the extent practical, regain compliance with the Baseline Project Schedule or, if regaining compliance with the Baseline Project Schedule is not practical, reasonably mitigates the delay (the “Recovery Plan”), and Contractor will participate in such meetings as JEA may require in connection with the production and implementation of such Recovery Plan.  Such Recovery Plan will include an analysis showing the then-current progress of the Work as against the Baseline Project Schedule.

Contractor will submit such proposed Recovery Plan to JEA within five (5) Business Days of receiving notification from JEA of its requirement. Upon receipt of such proposed Recovery Plan, JEA will review and comment upon the same.  Contractor will incorporate all reasonable comments and resubmit, within three (3) Business Days of receiving such comments, the proposed Recovery Plan to JEA for approval.  Contractor will promptly thereafter implement the approved Recovery Plan, and will use commercially reasonable efforts to adhere to such implemented Recovery Plan in order to regain compliance with the Baseline Project Schedule , which efforts may include, at Contractor’s option, the utilization of additional shifts, additional manpower, overtime and re-sequencing of activities.  Subject to and without prejudice to Contractor’s rights under Section 9.3 (which would adjust the Guaranteed Dates in relation to the occurrence of certain events as stated therein), and Section 9.4 (which addresses such schedule adjustment), the implementation of a Recovery Plan hereunder will be at Contractor’s expense.

During the last one hundred twenty (120) Days prior to the Guaranteed Substantial Completion Date, if in JEA’s reasonable opinion (including based upon the Critical Path in a Monthly Updated Schedule evidences the same) Contractor will be delayed by more than ten (10) Days in achieving the Guaranteed Substantial Completion Date, then Contractor will, at JEA’s request, conduct daily scheduling meetings with JEA for the purpose of discussing planning and implementation of all actions necessary to reduce, as much as possible, the effects of any delays.

For the avoidance of doubt, nothing in this Section 2.3.2 is intended to limit the Parties’ rights under Article 9.

Standards of Performance.

Contractor shall be solely responsible for all design, engineering and construction means, methods, techniques, sequences, procedures and safety and security programs in connection with the performance of the Work.  The design standard for the Balance of Plant Equipment shall be based upon the Balance of Plant Equipment having a useful life of, and being capable of maintaining the nominal design rating of the Balance of Plant Equipment (as adjusted from time to time in accordance with manufacturers’ degradation curves) for, at least, thirty (30) years from the Substantial Completion Date; provided, however, the Parties agree that the thirty (30) year design life standard shall not be considered a guarantee, condition, covenant, representation or warranty of any kind and Contractor does not warrant the foregoing thirty (30) year design life standard.  All Balance of Plant Equipment will be new and of a quality consistent with the foregoing design requirement.  Without limiting the foregoing, Contractor shall perform the Work: (a) in accordance with: (i) the plans and specifications and accompanying data set forth in and requirements of the Scope of Work (including without limitation designing of the Balance of Plant in accordance with NERC-CIP Requirements); (ii) all Applicable Laws and Applicable Permits; (iii) Prudent Industry Practices; and (v) all Applicable Codes and Standards; and (b) in a manner that is approved as to form, use and content by public entities authorized under Applicable Laws and Applicable Permits to administer or enforce any building or construction code or standard and whose approval of the final design of the Facility, or any portion thereof, is necessary for the construction, operation or maintenance of the Facility in accordance with the Applicable Laws and Applicable Permits.  Contractor will promptly notify JEA if it becomes aware of any material failure by Contractor or the Work to comply with the requirements of this Section 2.4.

Transfer of Title/Risk of Loss.

Contractor-Supplied Items.  Title to all Balance of Plant Equipment, and title to all Operational Spare Parts and Special Tools and all other materials provided by Contractor to JEA under this Agreement shall vest in JEA upon delivery of the same to the Facility Site. Title to the JEA Furnished Equipment will always remain with JEA.

Risk of Loss.

2.5.2.1	Damages Prior to Transfer Time/Takeover Time. Provided that Contractor is named as an additional insured under the Builder’s All-Risk policy as described in Exhibit F, Contractor will: (a) with respect to the Balance of Plant Equipment, bear the risk of loss, destruction or damage to the same at all times until the Transfer Time (or the Takeover Time, if applicable); and (b) with respect to each component of the JEA Furnished Equipment, bear the risk of loss, destruction and damage to the same at all times from its delivery to the Delivery Point by the PIE Supplier until the Transfer Time (or the Takeover Time, if applicable). Contractor shall promptly notify JEA upon discovery of any loss, destruction, damage, or material discrepancy affecting either the Balance of Plant Equipment or Power Island Equipment and shall take all reasonable steps to protect the affected equipment from further damage. Contractor shall not replace any such damaged equipment without the prior written approval of the JEA Project Manager, except where immediate action is necessary to protect safety, prevent further damage, in which case Contractor shall notify JEA as soon as reasonably practicable. Contractor shall promptly remedy, by repair or replacement, any such loss, destruction or damage as occurs to applicable items during the period when Contractor bears the risk of loss of such items as stated above. Contractor will, without reimbursement, bear all costs of completing such repairs and replacements.

2.5.2.2	Damages After Transfer Time.  After risk of loss of any property has transferred to JEA per Section 2.5.2.1, Contractor will be responsible for any damage to the same to the extent arising from the negligence or willful misconduct of Contractor or its Subcontractors, and shall repair or replace any such damaged structures, materials, or equipment at no additional cost to JEA.

2.5.2.3	Damages to JEA’s Existing Property.  Contractor will be responsible for any damage to JEA’s property existing on adjacent to the Facility Site as of the Effective Date, to the extent arising from the negligence or willful misconduct of Contractor or its Subcontractors, and shall repair or replace any such damaged structures, materials, or equipment at no additional cost to JEA.

Risk of Loss to Contractor Property.  Except for losses caused by the negligence or willful misconduct of JEA or those for whom it is responsible (but excluding plant staff when they are under the direction of Contractor as to the extent described in Section 3.7.1), Contractor shall be responsible for the care, custody, and control of, and shall at all times bear the complete risk of loss, destruction, or damage of its materials, supplies, equipment and machinery.

Title to Drawings, Reports, Documents and Information.  Title to each of the Design Development Documents, Construction Documents, reports, documents and other information prepared or acquired by Contractor in connection with the Work, which (in each case) Contractor is required to provide JEA pursuant to this Agreement, shall vest in JEA upon JEA’s receipt of such reports, documents and other information.

License to Software.  Contractor hereby represents and warrants that it has all rights necessary in order to provide to JEA any software that it is so providing under this Agreement as part of the Work.  Contractor hereby grants to JEA a non-exclusive, irrevocable, royalty-free, perpetual license (or, if Contractor is itself a licensee thereof, then a sublicense that meets the foregoing criteria) to use and configure any and all software provided by Contractor or its Subcontractors to JEA in connection with the Work.

Title to Natural Resources.  Title to soil, rock, gravel, sand, minerals, timber and any other resources obtained in the clearance or excavation of the Facility Site or the performance by Contractor of the Work is hereby expressly vested in and reserved by JEA.  Upon request, Contractor will execute and deliver and cause its employees and agents and all Subcontractors to execute and deliver to JEA any transfers, assignments, documents or other instrument which JEA may deem necessary or appropriate to vest complete right, title, interest and ownership of and to any or all items described herein, exclusively in JEA.

Title to Fossils and Artifacts.  Title to all fossils, coins, articles of value or antiquity, and structures and other remains or things of geological or archaeological interest discovered at the Facility Site shall (as between the Parties) remain with and be the property of JEA.  Contractor shall take reasonable precautions to prevent Contractor’s Personnel from removing or damaging any such articles or items.  Contractor shall, within twenty-four (24) hours upon the discovery of any such article or item, verbally notify the JEA Project Manager, followed as soon as reasonably possible thereafter by a written notice to JEA.

Site Conditions.

Surface Conditions.  Contractor has fully inspected the Facility Site and understands its current surface conditions, topography, existing man-made surface objects and existing natural surface objects (“Surface Conditions”). The Contract Price and Baseline Project Schedule already account for all efforts and requirements to address the same and Contractor expressly assumes the risk of any schedule delays or extra costs related to or resulting from such existing Surface Conditions of the Facility Site.

Geotechnical Report; Unforeseen Subsurface Conditions. For informational purposes only, the Geotechnical Report is set forth in Attachment A-20 to Exhibit A-1. Not more than ninety (90) Days following the later of the Effective Date or JEA providing Contractor access to the Facility Site, Contractor shall make independent inquiries regarding relevant naturally occurring subsurface conditions on and near the Facility Site, including taking additional soil borings, if it so chooses, and shall notify JEA in writing of any material differences between the results of Contractor’s investigation and the information included in the Geotechnical Report. If any additional geotechnical analysis performed by Contractor identifies subsurface conditions materially different from the results of the Geotechnical Report or that could not be reasonably anticipated based on the results of the Geotechnical Report (“Unforeseen Subsurface Conditions”), the Parties will negotiate in good faith to mutually agree upon a Change Order in accordance with the provisions of Article 9 to incorporate any equitable adjustments to the Contract Price and the Approved Project Schedule as may be required in order to address such material differences. If there are no material differences that entitle Contractor to a Change Order, or once the Parties agree upon such Change Order (if required), then, except as provided in Section 2.6.3 below, and in Sections 9.3.5, 9.3.6, and 9.3.7, Contractor expressly assumes the risk of any schedule delays or extra costs related to or resulting from any concealed, unusual or difficult subsurface conditions encountered in the performance of the Work on the Facility Site, including conditions relating to soils, water and/or rock. For the avoidance of doubt, as part of the Work, Contractor will have the full responsibility for performing (and selecting the means and methods for completing) all Site preparation work, and for designing, engineering, constructing and installing all foundations and other elements of the Facility that may be impacted by the natural subsurface conditions of the Site.

Interference with Existing Utilities. Contractor acknowledges and agrees that there is a possibility that existing JEA or other utility facilities, including water, sewer, electric, telephone, gas and cable lines, and other utility services (“Existing Utilities”), may cross and/or lie parallel to excavations in the area where the Work will occur. Although JEA may indicate recorded obstacles on the drawings, it does not warrant that other subsurface obstacles do not exist. Contractor shall be responsible for verifying the data furnished by JEA and for fully investigating and locating additional man-made obstructions including every type below, on or above the ground. Contractor should regard these impediments as normal to construction. All costs for performing such work shall not be paid for separately but shall be included in the Contract Price. Contractor shall comply with all requirements of the Sunshine State One-Call program. In the event Contractor encounters an unidentified utility during performance of the Work, Contractor shall promptly cease Work in the affected area and shall immediately notify the JEA Project Manager in writing. JEA will investigate the area and propose remedial actions in accordance with the provisions stated herein. Contractor shall work in cooperation with JEA and representatives of existing utilities to plan and coordinate putting new Work into service so as not to interfere with the operation of the existing utilities. Such plans shall be adhered to unless deviations therefrom are expressly permitted in writing by the JEA Project Manager. Contractor shall at all times conduct the Work in a manner that interferes as little as possible with the existing utilities. Any cables exposed during construction, whether energized or not, must be handled and protected as if they are energized. Contractor shall so conduct its operations and maintain the Work in such condition that adequate drainage shall be in effect at all times. Contractor shall not obstruct existing gutters, ditches and other runoff facilities. When working in the vicinity of overhead lines, Contractor shall request line rubber protection from JEA at least ten (10) Days in advance of performing the work. Contractor shall be solely responsible for any damages, interferences, and interruptions of service caused to any utility's assets and services including water, sewer, electric, telephone, gas, cable, and other utility services, that result from Contractor's failure to fulfill the above-mentioned requirements. In the event Contractor damages an existing utility, Contractor shall immediately notify the property owner, the owner of the damaged utility and the JEA Project Manager. Should the damage cause an interruption of service, Contractor shall be responsible for restoring service as soon as possible; however, Contractor shall not make repairs, other than any required to restore safe conditions, without the approval of the property owner, or the owner of the damaged utility. Contractor shall be responsible for coordinating any repair effort, and any associated costs should the utility owner or a licensed repair contractor be required to make the repair. JEA reserves the right to deduct any unsettled claim amount from Contractor’s invoices until such time as the claim is satisfactorily resolved.

Subsurface Man-Made Objects and Paleontological Discoveries.  Except for Utilities, which are addressed in Section 2.6.3, if Contractor encounters any unknown, subsurface, man-made object (including any object of archaeological interest) or encounters any unknown, subsurface object of paleontological interest, Contractor shall immediately cease Work in the area of the discovery, verbally notify JEA within twenty-four (24) hours of such encounter, followed as soon as reasonably possible thereafter by a written notice to JEA, and shall not continue Work in that area until so directed by JEA.  When resumed, operations within the area of the discovery shall be as directed by JEA. Examples of discoveries that are covered by the foregoing include discarded items, dwelling sites, man-made structures, stone implements or other artifacts, animal bones, human bones, fossils or any item with cultural significance. Provided Contractor complies with the foregoing, Contractor may seek an extension of time and an increase of the Contract Price in connection therewith as described in Section 9.3.6.

Nature of the Work.

Contractor shall be responsible for having taken and shall take all steps necessary to fully understand the nature of the Work, the general local conditions which can affect the Work, and the cost thereof.  Except as provided in Section 9.3, Contractor expressly assumes the risk of any schedule delays or extra costs related to or resulting from any failure by Contractor to acquaint itself fully with conditions which may affect the Work, including, but not limited to, conditions relating to transportation, handling, storage of materials, Contractor’s Taxes, insurance, availability of labor, water, roads, weather (including storm water management and wind), topographic conditions, applicable provisions of law, requirements to install JEA Furnished Equipment, and the character and availability of equipment and facilities needed preliminary to and during the prosecution of the Work (collectively, “Conditions of the Nature of the Work”).  Subject to Article 10, in no event will the Conditions of the Nature of the Work relieve Contractor of its responsibilities under this Agreement.

Subcontractors.

Acceptable Subcontractors.  Exhibit J includes a list of certain companies that may provide certain goods or services in connection with the Work and that are acceptable to JEA for the categories of Work shown in Exhibit J. Contractor shall be obligated, unless otherwise agreed to by JEA, to select from Exhibit J those Subcontractors who will be executing Subcontracts in connection with the performance of Work in the listed categories.  JEA may by written notice to Contractor make additions or deletions to Exhibit J at any time.  Contractor shall have the right to recommend additions to Exhibit J from time to time.  If a particular supplier is excluded from Exhibit J, Contractor will be responsible for ensuring that all of its Subcontractors exclude such supplier, at every tier.  Any successor or replacement of any Person listed in Exhibit J shall be subject to JEA’s prior written approval (which shall not be unreasonably withheld, conditioned or delayed).

Responsibility for Subcontractors.  Contractor shall be solely responsible for scheduling and coordinating the work of Subcontractors and other persons and organizations performing or furnishing any of the Work under a direct or indirect contract with Contractor.  Contractor shall require all Subcontractors and such other persons and organizations performing or furnishing any of the Work to communicate with JEA through Contractor.  Contractor shall be responsible to JEA for the acts and omissions of, and whenever this Agreement refers to the negligence, fault or omission of Contractor it shall include, the negligence, fault or omission of, Contractor’s employees, Subcontractors and their agents and employees, and other persons performing portions of the Work under a contract with Contractor.  Contractor shall not be relieved of obligations to perform the Work in accordance with this Agreement by tests, inspections or approvals required or performed by persons other than Contractor.  Contractor will be responsible for and shall use commercially reasonable efforts to ensure that all Subcontractors performing Work at the Facility Site have read and understand the Project Safety Manual and Project Security Plan and understand all Facility Site safety procedures and comply with the same.

Prompt Payment to Subcontractors. When Contractor receives payment from JEA for labor, services or materials furnished by Subcontractors and suppliers that are hired by Contractor, Contractor shall remit payment due (less proper retainage) to those Subcontractors and suppliers within ten (10) Days after Contractor’s receipt of payment from JEA. Nothing herein shall prohibit Contractor from disputing, pursuant to the terms of the relevant contract, all or any portion of a payment alleged to be due to its Subcontractors and suppliers. In the event of such dispute, Contractor may withhold the disputed portion of any such payment only after Contractor has provided written notice to JEA and to Subcontractor and supplier whose payment is in dispute, stating the amount in dispute and specifically describing the actions required to cure the dispute. Contractor shall deliver such notice to JEA and to the said Subcontractor or supplier within ten (10) Days following Contractor’s receipt of payment from JEA. Contractor shall pay all undisputed amounts due within the time frames specified herein. JEA shall not be liable for fees incurred by Contractor as a result of late payments made to a subcontractor or supplier. The prompt payment requirements herein shall, in no way, create any contractual relationship or obligation between JEA and any Subcontractor, supplier, JSEB, or any third-party, nor create any JEA liability for Contractor’s failure to make timely payments as required. Contractor’s failure to comply with the prompt payment requirements, however, shall constitute a material breach of its contractual obligations to JEA. As a result of such breach, JEA, without waiving any other available remedy it may have against Contractor, may issue joint checks and charge Contractor a 0.2% daily late payment interest charge or charges as specified within the Florida Statutes, whichever is greater.

No Privity with JEA.  JEA shall not be deemed by virtue of this Agreement or otherwise to have any contractual obligation to or relationship with any Subcontractor.  Contractor shall include a clause to this effect in each First Tier Subcontract with First Tier Subcontractors.  Contractor shall be solely responsible for ensuring that all Subcontractors are duly paid for services, equipment, material or supplies in connection with the Work and the Facility.

Subcontracts.  Contractor shall, at JEA’s request, provide to JEA, and JEA shall have the right to review, unpriced drafts of all Major Subcontracts prior to their execution.  JEA may, within a reasonable time after receipt of such a draft Major Subcontract, elect to give Contractor recommendations (if any) as to the terms and conditions thereof, and Contractor will incorporate the same.  JEA’s review of, and recommendations related to, such documents shall not give rise to any liability on the part of JEA and shall not relieve Contractor of any of its obligations hereunder.  All First Tier Subcontracts must be terminable for convenience, and any related termination fees thereunder must be commercially reasonable in light of the value of the services or materials provided thereunder.  As a condition to Final Completion, Contractor will provide JEA with unpriced copies of all Major Subcontracts, and if so requested by JEA, unpriced copies of any other Subcontracts, purchase orders, material requisitions or other agreements with Subcontractors relating to the Work.

Subcontractor Warranties.  Without limiting Contractor’s obligations herein, Contractor shall use commercially reasonable efforts to procure from all Subcontractors providing materials or equipment comprising the Balance of Plant Equipment or services in connection with the Work, product and service warranties at a minimum equal to the Warranties in Article 8 with respect to such materials, equipment and/or services, which shall endure for a minimum period coinciding with the Warranty Period. Contractor will obtain and maintain all Subcontractor warranties in full force and effect, and Contractor will enforce all Contractor warranties (and any rights relating thereto (e.g., rights to have root cause analyses performed) itself and/or on behalf of JEA.  Effective as of the end of the Warranty Period, Contractor hereby assigns to JEA its rights under any and all Subcontractor warranties that continue past the end of the Warranty Period.  Contractor will secure such assignment from each Subcontractor, and Contractor will deliver to JEA copies of all Subcontracts providing for warranties enforceable by JEA.  Contractor will not, and Contractor will ensure that Contractor’s Personnel do not, take any action which could release, void, impair or waive any Subcontractor warranties.

Assignment of Subcontracts.  Contractor shall ensure that Contractor’s rights and obligations under each First Tier Subcontract may be, without requiring the prior consent of the relevant Subcontractor, in whole or in part, assigned and delegated by Contractor upon notification to the Subcontractor from JEA, that: (a) the Contractor’s right to proceed with the Work has been terminated; and (b) JEA will thereafter be assuming Contractor’s obligations under such First Tier Subcontract as with respect to such terminated Work, then such First Tier Subcontractor shall continue to perform its responsibilities under such First Tier Subcontract for the benefit of JEA and shall recognize JEA as being vested with all the rights of Contractor under such First Tier Subcontract.  Notwithstanding the foregoing, it is specifically understood and agreed (and each First Tier Subcontract shall clarify) that no Subcontractor shall have any right to look to JEA for the performance of Contractor’s obligations under any First Tier Subcontract unless and until such Subcontractor has received such notice from JEA, and in no event will JEA be liable for any non-performance under or breach of the First Tier Subcontract by Contractor.

Subcontractor Insurance.   Contractor shall use commercially reasonable efforts to include a requirement in each First Tier Subcontract and each Subcontract with each Subcontractor (of any tier) performing any portion of the Work on the Facility Site that requires such Subcontractors to obtain, maintain and keep in force throughout the time during which they are engaged by Contractor reasonable levels of insurance coverage commensurate with their work scope and in any event, in accordance with the requirements of Exhibit F as are expressly made applicable to Subcontractors.

Global Sourcing. Notwithstanding anything to the contrary elsewhere in this Section, Contractor shall not obtain, source, subcontract, fabricate and assemble material or equipment and any components, parts and systems thereof from Cuba, Iran, North Korea, Sudan, or Syria. In addition, pursuant to Section 287.135(3)(b), Florida Statutes, in connection with the Work, JEA may terminate this Agreement if Contractor is found to have been placed on the Scrutinized Companies List or Scrutinized Companies that Boycott Israel List or is engaged in a boycott of Israel. Contractor acknowledges that Florida law prohibits the use of forced labor in the production of commodities provided to Florida public agencies. In the event Contractor is placed on the Florida Forced Labor Vendor List maintained in accordance with Section 287.1346, Florida Statutes, JEA shall be entitled to terminate this Agreement at its sole option. Upon execution of this Agreement by both Parties, Contractor shall submit an affidavit in the form of Exhibit P to JEA, executed under penalty of perjury, attesting that Contractor does not use coercion for labor or services as defined in Section 787.06, Florida Statutes.

Insurance.

Contractor has obtained prior to the commencement of Work, and shall hereafter maintain in full force and effect during the Term (or for such longer term as may be required under Exhibit F) insurance in accordance with and meeting the requirements set forth in Exhibit F.  Further obligations of Contractor with respect to insurance are set forth in Exhibit F.  If Contractor fails to purchase or maintain any insurance required under this Section 2.9, and such failure remains unremedied for five (5) Days after written notice thereof from JEA, then JEA may, but will not be obligated to, purchase such insurance on behalf of Contractor and will be entitled to be reimbursed by Contractor promptly upon demand. The foregoing provisions requiring Contractor to carry insurance will not be construed in any manner as waiving, restricting or limiting the liability of Contractor as to any obligations imposed under this Agreement, whether or not same are, or may be, covered by insurance.

Provision of Information; Cooperation.

Upon request by JEA, Contractor shall provide such information as JEA may reasonably require to support its development, permitting, financing, construction, operation, and maintenance of the Facility.  Contractor shall provide such information within a reasonable period following JEA’s request in light of the circumstances at the time of such request.  Contractor will, in cooperation with JEA, coordinate and communicate with the gas supplier as reasonably required in order to facilitate the timely development, construction, start-up and operation of the Facility.

Storm Water Pollution Prevention Plan.

NPDES Permit Conformance. Contractor shall obtain as necessary a Generic Permit for Stormwater Discharge from Large and Small Construction Activities (CGP) and shall develop a Stormwater Pollution Prevention Plan compliant with local, state, and federal rules, laws, and ordinances (the “SWPPP”). Contractor shall be responsible for implementing the SWPPP, installing and maintaining in a functional manner structural and nonstructural best management practices as described therein, evaluating the effectiveness of the best management practices, and employing additional performance based best management practices as may be deemed necessary by JEA. Contractor, at its own expense, shall revise, or include as addendum to the SWPPP measures as maybe required by a local, state, or federal authority to remain compliant with local, state, and federal rules, laws, and ordinances. No additional payments shall be made to Contractor for revisions or addendums to the SWPPP, or for the actual implementation of those revisions on the Facility Site, including those made so as to achieve functional performance based best management practices. Contractor shall obtain all other applicable local, state, and federal permits subsequent to notification of JEA of the need for such authorization(s).  It is unlawful to have any discharges that are not composed entirely of stormwater (except discharges pursuant to a NPDES permit) to the Municipal Separate Stormwater System (MS4).  Only non-contaminated water/non-turbid water shall be transported through the MS4. Groundwater discharge (approved by the FDEP pursuant to 62-621.300(2)) from dewatering activities may be routed into the stormwater system, drainage ditch, creek, river or wetland providing that erosion, and transportation of suspended solids to the system is prevented.  If contaminated soil or contaminated groundwater is encountered, the dewatering activity shall cease immediately, and Contractor shall contact JEA’s Environmental Coordinator, Andrew Sears at (904) 665-7719. Contractor or any Subcontractor conducting land disturbing activities shall have at least one (1) corporate representative that is certified for the Florida Department of Environmental Protection Erosion and Sediment Control Inspector Training Manual. For Projects with greater than one acre of disturbed land, a person certified pursuant to the Florida Department of Environmental Protection’s Erosion and Sediment Control Inspector Training Manual or trained by a certified person shall make the routine inspections shall be maintained and kept on the construction site and made available for inspection during land-disturbing activities. Such inspection shall be made no led that daily and a log of such inspections shall be maintained and kept on the construction site and made available for inspection by City and JEA inspectors throughout the duration of land-disturbing activities. If the inspector is trained by a certified person but not certified themselves, accurate training records must be kept and evidence of annual refresher trainer shall be maintained. Any required erosion and sediment control plans submitted to the City of Jacksonville must conform to the requirements in the FDEP’s Florida Department of Environmental Protection’s Erosion and Sediment Control Inspector Training Manual or the provisions contained in the Land Development Procedures Manual. Upon approval to proceed to do so by JEA, Contractor shall complete a Notice of Termination (NOT) (DEP Doc. No. 62-621.300(6), F.A.C.), to terminate the CGP coverage within one (1) week of final site stabilization. If the above requirements are not followed, Contractor shall be held liable for any fines and/or violations incurred by JEA.

Dewatering. If Contractor encounters groundwater, Contractor shall be responsible for utilizing a dewatering system(s) to remove water from the excavations. Prior to beginning any dewatering, Contractor shall submit a dewatering plan to the JEA Project Manager for review and approval. Contractor shall comply with all sampling requirements listed in Florida Department of Environmental Protection (FDEP) Dewatering Regulations before any dewatering can begin. Once the sampling analysis is complete, the sample(s) results shall be submitted to the JEA Project Manager for review and submittal to FDEP. If the sample analysis fails, no dewatering can proceed without further instruction from the JEA Project Manager. Additionally, prior to any dewatering, Contractor shall apply for a St. Johns River Water Management District (SJRWMD) Generic Permit for Short Term Dewatering, and comply with all SJRWMD requirements. If the above requirements are not followed, Contractor shall be held liable for any fines and/or violations incurred by JEA.

Prevention, Control and Abatement of Erosion and Siltation. Contractor shall take steps and make suitable provisions to minimize siltation and erosion of waterways that may result from its operation during the course of construction. Contractor shall make suitable arrangements, which may require the temporary construction of flumes, boxes, or some other device(s), at the Facility Site for the drainage and disposal of water. Contractor shall be responsible for protecting adjacent property to the Facility Site from damage by water resulting from its operations. The Facility Site shall be returned to its original condition to the satisfaction of JEA. Contractor is cautioned that execution or maintenance that creates turbidity and that directly or indirectly affects the water quality of any waterway into which storm water is discharged in such a manner as to exceed the limitations prescribed in the Florida Administrative Code, is a violation of the water quality standards of the State of Florida. Turbidity shall not exceed 29 NTU's, above background level within 100' of the construction activity. Costs incurred by Contractor for compliance to the restrictions outlined above shall be included in the cost of the items for which the turbidity control is required. Silt barriers shall be used at all waterway crossings or at any time during construction that siltation or erosion may occur. Contractor shall submit to the JEA Project Manager, for written approval prior to construction, the method to be used to control the turbidity. The Project Manger’s approval of the method to be used in no way relieves Contractor of the liability in case of a citation against JEA.

Silt Fence Assembly. Contractor shall furnish and install silt fence assembly (including fabric, stakes, etc.) in accordance with the details shown on the Erosion Control Drawings and as required by the SWPPP. Contractor will be responsible for all costs associated with silt fence assembly.

JEA Obligations

Facility Real Estate Rights and Access to Facility Site.

JEA will secure and maintain at its own expense all Real Estate Rights, and JEA will furnish to Contractor access to the Facility Site as necessary for Contractor to perform the Work and in accordance with the Baseline Project Schedule.

JEA Permits.

JEA will secure and maintain, at its own expense, JEA Permits. Contractor will timely use commercially reasonable efforts to support, and will cooperate with, JEA in connection with JEA’s efforts to obtain, maintain and comply with JEA Permits and PIE Supplier in connection with PIE Supplier’s efforts to obtain any permits required of PIE Supplier.  Contractor will promptly provide all necessary information and reasonable assistance as requested by JEA or PIE Supplier in connection with the foregoing.  Contractor will not be entitled to any schedule relief with respect to any delays to the Work as result from the delayed issuance of a JEA Permit where such delayed issuance is a consequence of Contractor’s failure to abide by its obligations under this Section 3.2.

JEA Furnished Equipment.

JEA shall purchase the JEA Furnished Equipment and arrange and pay for the costs of transporting and delivering the components of the JEA Furnished Equipment to the applicable Delivery Point by the date(s) set forth in the Baseline Project Schedule as further described in Section 2.2.4.

JEA’s Insurance.

JEA will obtain and maintain the insurance coverages as described in Exhibit F.

Florida Sales and Use Taxes.

JEA is a municipally owned utility and is exempt from paying Florida Sales and Use Tax and Manufacturer’s Federal Excise Tax when purchasing tangible personal property for its direct consumption. Additionally, pursuant to Florida Statute 212.08(5)(c)3, if Contractor or Subcontractor is buying materials for JEA’s electric generating stations, other than Northside Unit 3, JEA can issue Contractor or Subcontractor an affidavit that will allow Contractor or Subcontractor to purchase materials tax free on behalf of JEA. JEA will provide such affidavit to Contractor within thirty (30) Days of the Effective Date.

Construction Utilities; Backfeed Power; Fuel.

Utilities. JEA shall provide certain temporary electric, potable water, service water, and sanitary utility service connections at designated terminal points shown in the Site Arrangement drawing set forth in Attachment A-1 to Exhibit A-2. Contractor will have the responsibility for distribution of any such utilities within the Facility Site.

Backfeed Power. Provided that Contractor has provided JEA with prior notice with respect thereto as described in Section 7.1, after Mechanical Completion has been achieved, JEA will provide at its expense a supply of backfeed power as necessary to energize the Facility for all start-up and commissioning activities therefor.

Fuel Supply. JEA shall provide fuel as needed for start-up and testing of the Facility.

JEA Operators.

JEA will cause a normal complement of permanent plant staff to be available to Contractor to use in performing operational services in conjunction with Contractor’s and PIE Supplier’s start-up and testing activities as described in this Agreement, but, only in regard to the operation of the Balance of Plant, such staff personnel will be directed solely by Contractor, and Contractor will remain responsible for the training, actions or omissions of such personnel in connection therewith.  However, notwithstanding the foregoing, Contractor shall not be responsible for the willful misconduct of such personnel.

JEA’s Engineer.

JEA’s Engineer will provide design review and construction oversight, including overseeing and resolving engineering/design issues, conveying JEA's instructions to Contractor and enforcing the faithful performance of the Work. JEA’s Engineer's authority includes interpreting the technical portion of the Contract Documents, deciding on matters relating to the execution and progress of the Work and evaluating Contractor’s performance. JEA’s Engineer may stop the Work when deemed necessary by JEA. JEA’s Engineer will receive and adjudicate any claim of ambiguity or error in the technical portion of the Contract Documents and shall reduce any determination into writing, and the decision shall be final and binding. JEA’s Engineer is not a party to the Agreement. JEA’s Engineer has no authority to approve changes to the Work or Agreement, or to commit JEA to any expenditure of money except as expressly designated in writing by the JEA Project Manager.

Other Obligations.

Without limiting the generality of the foregoing, JEA will perform such other obligations and provide such other items as identified as obligations of JEA in Exhibit A-1 and Exhibit A-2.

JEA’s Right To Inspect, Stop and Re-Perform Work

Inspection and Re-Performance.

Without limiting and subject to Section 2.2.22, JEA and its designees will have the right to have reasonable access to and inspect the Work, wherever located and at any stage of completion. If the progress and quality of the Work are not proceeding in accordance with this Agreement and the Baseline Project Schedule, then JEA shall be entitled to make recommendations to Contractor or any Subcontractor for the purpose of remedying such deficiencies; provided, that no recommendations from JEA shall relieve Contractor of any of its obligations under this Agreement.  JEA may reject any Work that does not comply with the requirements of this Agreement (or JEA-approved components of the Plant Data Books).  If JEA’s inspection reveals any such non-compliance or any other defects in any portion of Work, then Contractor will, promptly upon its receipt of notice from JEA, correct all such defective Work.  If Contractor fails to initiate correction of the defective Work within ten (10) Days of its having received notice thereof from JEA, JEA may, without prejudice to any other remedy JEA may have, correct such defective Work; provided, however, that if such defective Work creates a safety hazard at the Facility then JEA may, without prejudice to any other remedy JEA may have, immediately correct such defective Work.  JEA’s correction of such defective Work will not relieve Contractor of its obligations under this Agreement.  All costs and expenses related to such actions of JEA will be for the account of Contractor, and Contractor will promptly reimburse such amounts to JEA, or JEA may set such costs off as against any amount due from JEA to Contractor under this Agreement.

Right to Stop Work for Cause.

If Contractor fails to correct defective Work, fails to materially comply with the Project Safety Manual, or fails to diligently carry out the Work in accordance with the requirements of this Agreement or if Contractor’s actions otherwise fail to conform to the requirements of this Agreement (or JEA-approved components of the Plant Data Books), then JEA, by a written order signed by the JEA Project Manager, may order Contractor to stop performance of the portion of the Work affected thereby, until the cause of such order has been eliminated; provided, however, that this right of JEA to stop Contractor’s performance will not give rise to any duty on the part of JEA to exercise this right for the benefit of Contractor or any other person or entity.  In addition, JEA, by written order signed by the JEA Project Manager, may order Contractor to stop performance if the activities of Contractor or Contractor’s Personnel appear to JEA to cause or threaten to cause danger to life or damage to JEA’s property.  In the event of such a stop order, Contractor will not be entitled to a Change Order extending the Baseline Project Schedule or adjusting the Contract Price.  JEA’s right to stop Work under this Section 4.2 will be without prejudice to any other right or remedy JEA may have.

Uncovering Construction Work.

Uncovering of Work Requested to be Observed.  If a portion of the Work is covered in advance of an agreed witness, hold and/or inspection point (per Section 2.2.22), or otherwise contrary to JEA’s written advance request, Contractor will, if required in writing by JEA, uncover such Work for JEA’s observation and replace the same without change in the Contract Price or Baseline Project Schedule.

Uncovering of Work Not Requested to be Observed.  If a portion of the Work has been covered which was not the subject of an agreed-upon witness, hold and/or inspection point, and with respect to which JEA had not specifically requested in advance an opportunity to observe such Work prior to its being covered, JEA may direct Contractor to uncover such Work.  If such covered Work is thereafter found to be in accordance with the requirements of this Agreement, then Contractor may request a Change Order under Section 9.3.3.  If such Work is not in accordance with this Agreement, Contractor shall bear such costs as part of the Contract Price, and no change to the Baseline Project Schedule will be granted.

Right to Suspend Work for Convenience.

JEA may at any time and from time to time, by a written order signed by the JEA Project Manager, suspend (and later reinstate) the Work or any portion thereof without terminating this Agreement.  Upon receipt of such order, Contractor will immediately suspend its performance of the Work or portion thereof as is directed by JEA in the written order.  During any such suspension, Contractor will: (a) protect and secure the Work and all materials and equipment; (b) place no further subcontracts or purchase orders for materials, services, work or facilities with respect to those parts of the Work suspended except to the extent expressly requested by JEA; and (c) use commercially reasonable endeavors to suspend on the most favorable terms available to Contractor all purchase orders, subcontracts and rental agreements to the extent affected by such suspension and otherwise minimize the additional costs associated with such suspension.  If JEA suspends the Work pursuant to this Section 4.4, then Contractor’s rights to receive a Change Order shall be as described in Section 9.3.2.

Price and Payment

Contract Price.

As full consideration to Contractor for the complete performance of the Work and Contractor’s other covenants in this Agreement, JEA will, subject to the provisions of this Article 5, pay Contractor [●] Dollars ($[●]) (the “Contract Price”).  The Contract Price is fixed and may be adjusted only pursuant to a Change Order issued by JEA in accordance with the provisions of Article 9.

Milestone Payments.

Subject to the terms and conditions of Section 5.3, the Contract Price shall be paid by JEA to Contractor by way of milestone payments (each, a “Milestone Payment”) for completed Milestones.

Application for Payment; Payment of Invoices.

Applications for Payment.  Contractor will, no more frequently than monthly, invoice JEA for Milestone Payments for Milestones completed during the prior month (and for any payments due under Section 9.5.1.1) (each such invoice, an “Application for Payment”). Each Application for Payment shall be accompanied by such supporting documentation as necessary for JEA’s verification of the Application for Payment and the satisfactory completion of the Milestone(s) for which any Milestone Payment is sought in accordance with the Contract Documents. Applications for Payment and supporting documentation shall be submitted to the following email address:

- ACCTPAYCUSTSRV@JEA.COM.

Tariffs.

Existing Tariffs. The Contractor represents that the Contract Price as of the Effective Date includes an amount equal to [●] Dollars ($[●]) (the “Tariffs Allowance”) to cover all import duties, tariffs, customs and other similar taxes or levies on goods, materials, or equipment to be incorporated into the Facility and imported into the United States (“Tariffs”) which are known and in effect as of the Effective Date of this Agreement. The Contractor shall be responsible for the payment of all Tariffs.

New or Changed Tariffs. In the event that subsequent to the Effective Date of this Agreement, any new Tariffs are imposed, or existing Tariffs are changed (including increases, decreases, or eliminations), by any Governmental Authority, which causes Contractor to incur additional Tariff costs for any goods, materials, or equipment to be incorporated into the Facility, the following provisions shall apply:

- (a) 	Notification. The Contractor shall promptly notify JEA in writing of such new or changed Tariff and its anticipated impact on the Contractor’s costs of importing goods, materials, or equipment to be incorporated into the Facility into the United States. Such notification shall be provided no later than thirty (30) days after the Contractor becomes aware of the new or changed Tariff.

- (b) 	Documentation and Verification. Within thirty (30) days after importing any goods, materials or equipment to which Tariffs apply in to the United States, Contractor shall provide Owner with supporting documentation, as applicable, including a completed CBP Form 7501 (inclusive of any continuation sheets and Form 7501A (Document/Payment Transmittal) and bill of lading from port to port, and such further information as may be reasonably requested by Owner to reasonably substantiate such Tariffs. The Owner shall have the right to reasonably audit such documentation.

- (c) 	Adjustment. If any new or changed Tariffs after the Effective Date causes the amount of Tariffs paid by Contractor to exceed the Tariffs Allowance, Contractor and Owner will enter into a Change Order to increase the Contract Price by the actual and demonstrated Tariff charges in excess of the Tariffs Allowance. Should any Tariffs existing at the Effective Date, or imposed thereafter, be reduced or eliminated, resulting in a demonstrable decrease in the Tariffs charges below the Tariffs Allowance, Contractor and Owner will enter into a Change Order to decrease the Contract Price by the actual and demonstrated Tariff charges below the Tariffs Allowance.

- (d) 	Separate Line Item for Tariffs. Any Tariffs applicable to an Application for Payment shall be listed as a separate line item on that Application for Payment. This separate listing will clearly indicate the amount of the Tariff, the rate of the Tariff and the country of origin. The cost of the goods, materials, equipment, or services shall be listed separately from the Tariff amount

- (e)	Limitations. Any price adjustment under this Section shall not exceed the published tariff contained in the US Government’s Harmonized Tariff Schedule (HTS) assigned to the affected item, unless otherwise mutually agreed in writing. Adjustments shall only apply to Tariffs directly impacting goods, materials, or equipment incorporated into the Work or services provided after the effective date of the new or changed Tariff.

Payment of Invoices.  Subject to this Section 5.3 and 5.4, JEA will pay all undisputed portions of each Application for Payment by ACH (based upon the payment information included in Contractor’s invoice) within twenty (20) Business Days after receipt of such Application for Payment and all required supporting documents, and otherwise in compliance with the provisions of the Florida Local Government Prompt Payment Act (Section 218.70, Florida Statutes, et seq.).

Application for Final Payment. Within sixty (60) days from completion of the Work, Contractor shall submit its final Application for Payment for all Work.

JSEB-Invoicing and Payment. If Contractor utilizes JSEB certified firms, regardless of whether this Agreement requires or encourages the use of such firms, the payment terms for participating JSEB firms shall be the same or better than the payment terms Contractor receives from JEA, except that in all cases JSEB firms shall be allowed to submit invoices to Contractor at least bimonthly, and Contractor shall pay proper invoices no later than three (3) Days after its receipt of JEA payment. Contractor shall obtain written approval from the JEA Project Manager and JEA Manager Supplier Diversity Programs prior to withholding any payment from a JSEB firm. Contractor will be required to self-report all payments made to the JSEB certified firms. The payment data will be entered into the B2Gnow JSEB Compliance & Diversity Outreach System (JCDOS) located at the following website: https://jea.gob2g.com/.  This system tracks contract payments made by Contractor to any Subcontractor (i.e. JSEB or Diverse Business), the timeliness of those payments and the payments JEA makes to Contractor. Contractor is required to submit the monthly payments made to the JSEB certified firms by the audit date of the thirtieth (30th) of each month, and to respond to any requests for information within the B2Gnow JSEB Compliance & Diversity Outreach System (JCDOS). The JCDOS must be checked frequently. Contractor and JSEB certified firms will be provided with access information for the JCDOS post the contract award.  B2Gnow provides vendor training, and additional information can be obtained by contacting JEA’s Manager Supplier Diversity Programs.

Conditions of Payments; Withholdings, Set-Offs, Retention.

Required Submittals.  Notwithstanding Section 5.1 or 5.3, JEA will not be required to make any payment to Contractor if Contractor has not provided the submittals described in this Section 5.4:

      - Progress Reports.  Each Application for Payment submitted by Contractor must be accompanied by a Monthly Progress Report, which shall include the Monthly Updated Schedule.

      - Partial Lien Waivers.  Each Application for Payment submitted by Contractor must be accompanied by conditional, partial lien waivers and releases executed by Contractor and each Subcontractor whose services are included in the Work completed prior to the date of such Application for Payment.

      - Final Lien Release; Final Payment.  Contractor’s Application for Payment for the final payment from JEA under the Agreement must be accompanied by conditional, final lien releases and waivers executed by Contractor and by each Subcontractor. Within thirty (30) Days after receipt of final payment, Contractor will provide an unconditional final lien release and waiver in the form set forth in Exhibit N-2, executed by Contractor and each Subcontractor. Acceptance of the final payment shall constitute a full and final release by Contractor of any and all liens and claims of liens, whether statutory or otherwise, in respect of the Work performed pursuant to this Agreement as against JEA, the Facility or the Facility Site and of any payment related claims against JEA for any act or omission of JEA.

Forms of Lien Waivers. The lien waivers and releases required from Contractor and its Subcontractors under this Section 5.4.1 must be in the applicable form as set forth in Exhibit N-1 and Exhibit N-2, as applicable.

Withholding to Protect JEA from Loss.  Notwithstanding anything in this Article 5 to the contrary, but subject to Sections 5.4.2.1 and 5.4.2.2, JEA may, without prejudice to any other rights JEA may have, withhold all or any portion of any payment to Contractor, to such extent as reasonably necessary in JEA’s reasonable opinion to protect JEA from loss due to: (a) defective Work by Contractor or any of its Subcontractors that has not been rectified pursuant to Section 4.1; (b) Claims filed against any JEA Indemnities by Third Parties and for which Contractor has an unfulfilled indemnification obligation under Section 11.1; (c) failure of Contractor to make undisputed payments to Subcontractors when due (provided that JEA is otherwise current in its required payments under this Agreement); (d) liens filed against either the Facility, the Facility Site or any other property of JEA by any Subcontractor; (e) the violation by Contractor or any of Contractor’s Personnel of any Applicable Laws or Applicable Permits, where such violation is likely to cause liability to JEA; (f) failure by Contractor to maintain the insurance required by this Agreement; (g) amounts claimed by Contractor that are in question and under examination or audit; or (h) Contractor’s material failure to fulfill any of its other obligations under this Agreement.

Removal of Liens.  Subject to the provisions of Section 5.4.2.2 below, in the event any lien is filed by Contractor or any Subcontractor against any property of JEA in connection with this Agreement, Contractor shall, upon written notice from JEA, promptly ensure that such lien is removed. If such lien is not promptly removed after Contractor’s receipt from JEA of written notice to do so, JEA may take the necessary action to remove such lien, and all costs in connection with such removal (including attorney’s fees) shall be deducted from withheld payments or other monies due, or which may become due, to Contractor.

Lien Bonds.  Notwithstanding Section 5.4.2(d), JEA shall release any payments withheld due to any lien if Contractor obtains at its sole expense a lien bond which pursuant to governing law, removes the lien as an encumbrance of record upon the Facility.

Payment after Removal of Cause. When Contractor has remedied the cause for withholding any payment and has furnished evidence of such remedy that is reasonably satisfactory to JEA, JEA will make the payment so withheld to Contractor within thirty (30) Days following JEA’s verification of such evidence. If Contractor, after receipt of written notice from JEA, fails or refuses to remedy the cause for withholding such payment within a reasonable time, then JEA may, without prejudice to any other rights JEA may have, remedy it and deduct the cost and JEA expenses, such as counsel and other legal fees and disbursements, from the compensation payable to Contractor under this Agreement, but such action by JEA will not be or be considered to be a waiver of any default by Contractor under this Agreement.

Retention.  JEA will retain five percent (5%) of each payment made to Contractor after the Effective Date (“Retention”).  Subject to Sections 5.4.5 and 5.4.6, JEA shall release Retention within twenty (20) Business Days after Substantial Completion.

Withholding of Performance Liquidated Damages.  Upon the achievement of Substantial Completion, JEA may withhold from any payment due to Contractor, including the release of Retention, under this Agreement an amount equal to any Performance Liquidated Damages and Substantial Completion Delay Liquidated Damages owing, if any.

Withholding to Ensure Completion of the Punch-List.  Commencing upon the inclusion of any proposed Punch-List items as included in any Turnover Package submitted by Contractor, and, further, upon the creation of the Punch-List in accordance with Section 6.5, JEA may withhold from any payment due to Contractor, including the release of Retention, an amount equal to one hundred fifty percent (150%) of the total projected cost of completing the agreed-upon Punch-List items (such amount, the “Punch-List Withholding Amount”).  This amount will be determined by JEA in consultation with JEA’s Engineer and will, subject to Section 5.4.2, be released to Contractor within thirty (30) Days after Final Completion.

Set Off.  JEA may set off any sums payable by Contractor to JEA under or in connection with this Agreement against any payments due to Contractor under the Agreement including the release of Retention.

Right to Audit and Financial Reporting.

Accounting System. Contractor shall establish and maintain a reasonable accounting system that enables JEA to readily identify Contractor’s assets, expenses, cost of goods, and use of funds.

Audited Financial Statements. Contractor shall provide to JEA audited financial statements for its most recent fiscal year not later than five (5) days after receipt of written request from JEA.

Content and Retention of Records. Contractor’s records shall include, but not be limited to, accounting records; written policies and procedures; subcontract files (including any earlier proposals of bids received by JEA); all paid vouchers including those for out-of-pocket expenses; invoices as support for other reimbursement; ledgers; cancelled checks; deposit slips; bank statements; journals; original estimates; estimating work sheets; contract amendments and change order files; back-charge logs and supporting documentation; insurance documents; payroll documents; timesheets; memoranda; and correspondence. Contractor shall, at all times during the Term and for a period of five (5) years after the completion of the Agreement, maintain such records, together with such supporting or underlying documents and materials.

Inspection/Audit of Records. Upon JEA’s request, Contractor shall allow JEA to audit, to examine, and to make copies of or extracts from its financial and operating records (in whatever form they may be kept, whether written, electronic, or other) kept by Contractor, its employees, agents, assigns, successors, and subcontractors, for the purpose of determining invoice accuracy, or otherwise assessing compliance with the Contract Documents. Contractor shall at any time requested by JEA, whether during or after completion of the Agreement, and at Contractor’s own expense make such records available for inspection and audit (including copies and extracts of records as required) by JEA. Such records shall be made available to JEA during normal business hours at Contractor’s office or place of business in a workspace suitable for the audit on three (3) Days’ prior written notice. In the event that no such location is available, then the financial records, together with the supporting or underlying documents and records, shall be made available for audit at a time and location that is convenient for JEA. Contractor shall have knowledgeable personnel available to answer questions for the auditors during the time they are performing the audit and for a period of two (2) weeks thereafter. Contractor shall ensure JEA has these rights with Contractor’s Personnel, and the obligations of these rights shall be explicitly included in any subcontracts or agreements formed between Contractor and any subcontractors to the extent that those subcontracts or agreements relate to fulfillment of Contractor’s obligations to JEA.

Cost of Audits. If the audit identifies: (i) overpricing or overcharges of any nature by Contractor to JEA in excess of one-half of one percent (.5%) of the total billings under the Agreement at the time of the audit; or (ii) fraud, misrepresentation or non-performance, Contractor shall reimburse JEA for the total costs of the audit.

Billing Adjustments and Recoveries. Contractor shall pay JEA all amounts identified as owing to JEA as a result of any such audit or inspection of Contractor’s invoices and records no later than ninety (90) Days after Contractor’s receipt of JEA’s findings.

City of Jacksonville Office of the City Council Auditor. Contractor providing contractual services purchased by JEA agrees and be deemed to have agreed by virtue of doing business under contract with JEA to be subject to audit upon request by the Office of the City Council Auditor pursuant to Article 5 of the JEA Charter.

Payment or Use Not Acceptance.

No payment or other payment to Contractor or any use of the Facility by JEA shall constitute an acceptance of any of the Work furnished by Contractor or shall relieve Contractor of any of its obligations or liabilities with respect thereto.

Cost-Savings Plan.

During the Term, JEA and Contractor are encouraged to identify ways to reduce the Contract Price to JEA related to the Work provided by Contractor. JEA and Contractor may negotiate Change Orders or amendments that allow such reductions in total costs including, but not limited to, the sharing of savings resulting from implementation of cost-reducing initiatives between JEA and Contractor. The decision to accept any cost savings initiative shall be in the sole discretion of JEA, and JEA shall not be liable to Contractor for any cost that may be alleged to be related to a refusal to accept a cost savings initiative proposed by Contractor.

STAGES OF Completion of the Work

Ready for First Fire; Ready for Full Steam Admission.

Notice of Ready for First Fire. So that JEA may work with PIE Supplier to coordinate its activities, Contractor will give JEA at least five (5) Days’ written notice in advance of the then-scheduled date for the achievement of Ready for First Fire.

Ready for First Fire Walkdown. When Contractor believes the gas turbine of the Power Island Equipment has achieved the criteria for Ready For First Fire, it will promptly notify JEA, who will notify the PIE Supplier. The Parties acknowledge that thereafter the PIE Supplier will then have its representatives perform inspections with respect to the same and work with JEA and Contractor to identify and support efforts to address any issues preventing achievement of the criteria for Ready for First Fire of such gas turbine equipment.  Contractor will promptly remedy any issues with the Work identified as preventing the criteria for Ready for First Fire from being achieved.  This process shall be repeated until JEA and PIE Supplier agree that the criteria for Ready for First Fire have been achieved, which will be documented with a completed Certificate of Ready for First Fire in the form set forth in Exhibit K-1, signed by Contractor, JEA and the PIE Supplier.

Plan of the Day. After the gas turbine of the Power Island Equipment has achieved Ready for First Fire, and at the start of each workday thereafter through the Commissioning Period, Contractor and the PIE Supplier shall meet on a daily basis to conduct a review of each Day’s planned commissioning, start-up and testing activities and develop a plan and operational profile for the Power Island Equipment for such Day’s activities, as well as agree and document in writing as to which party shall be responsible to lead the Power Island Equipment commissioning activities for the Day, and whether and the extent to which the PIE Supplier will require an Access Day (the “Plan of the Day”).

Access Days for PIE Supplier. Following the achievement of Ready for First Fire, Contractor will allow and provide PIE Supplier with a total of eighty-five (85) Access Days during the Commissioning Period. Such Access Days need not be consecutive. Contractor shall cooperate with the PIE Supplier JEA to schedule the allocation of Access Days so that Contractor’s and PIE Supplier’s activities, as well as shutdowns, can be planned in such a manner so that, on Access Days, Contractor and PIE Supplier can work concurrently to the greatest extent reasonably possible. During Access Days within which the Power Island Equipment is experiencing extended downtime, Contractor shall use reasonable efforts to plan its work in order to mitigate adverse impacts to the schedule caused by extended downtime. On all Access Days, Contractor shall reasonably cooperate with the PIE Supplier so as to allow it and its personnel to complete their work. Equipment

Access Day Tracking Form. At the end of each workday during the Commissioning Period, Contractor’s and the PIE Supplier’s respective site teams will meet to annotate on a mutually agreed tracking form (the “Access Day Tracking Form”) key events that happened on that day. Contractor and the PIE Supplier shall sign the Access Day Tracking Form indicating whether the Day was agreed to be an Access Day or is disputed by the PIE Supplier based on the agreed upon Plan of the Day. If the PIE Supplier notifies Contractor that, on any given Day when it was, based upon the Plan of the Day, supposed to have been provided an Access Day, it has not received such Access Day meeting the requirements hereof, then Contractor and the PIE Supplier will notify JEA Project Manager of such belief in writing, detailing the reasons for the same. Contractor, the PIE Supplier and the JEA Project Manager will meet to resolve the discrepancy within three (3) Days. If such representatives cannot reach agreement on the Access Day disagreement in the above timeframe, the dispute will be escalated to senior management for resolution. If based upon the agreed applicable Plan of the Day, Contractor affords the PIE Supplier the access required for an Access Day but, for reasons attributable to the PIE Supplier Company, the PIE Supplier elects not to utilize the same in whole or in part during that Day, such election will not negate such Day as an Access Day. Similarly, if based upon the agreed upon applicable Plan of the Day, the PIE Supplier has not requested access required for an Access Day for such Day, but the PIE Supplier is able to perform commissioning activities on the Power Island Equipment without restricting or impeding Contractor-led planned commissioning work, such Day shall not be considered as an Access Day. Contractor agrees that the Baseline Project Schedule already includes and accounts for eighty-five (85) Access Days for the PIE Supplier during the planned Commissioning Period for the Facility. In this regard, PIE Supplier’s utilization of such allotted Access Days shall in no event serve as the direct or indirect basis for or be the subject of a Change Order claim.  PIE Supplier’s required utilization of more than the allotted Access Days to complete the activities described above may constitute a JEA Delay Event in accordance with the definition thereof.

Notice of Ready for Full Steam Admission. So that JEA may work with PIE Supplier to coordinate its activities, Contractor will give JEA at least five (5) Days’ written notice in advance of the then-scheduled date for the achievement of Ready for Full Steam Admission.

Ready for Full Steam Admission Walkdown. When Contractor believes the Power Island Equipment has achieved the criteria for Ready for Full Steam Admission, it will promptly notify JEA, who will notify the PIE Supplier. The Parties acknowledge that thereafter the PIE Supplier will then have its representatives perform inspections with respect to the same and work with JEA and Contractor to identify and support efforts to address any issues preventing achievement of the criteria for Ready for Full Steam Admission.  Contractor will promptly remedy any issues with the Work identified as preventing the criteria for Ready for Full Steam Admission from being achieved. This process shall be repeated until JEA and PIE Supplier agree that the criteria for Ready for Full Steam Admission have been achieved, which will be documented with a completed Certificate of Ready For Full Steam Admission in the form set forth in Exhibit K-2, signed by Contractor, JEA and the PIE Supplier.

Mechanical Completion.

Criteria.  Subject to Section 6.2.3., “Mechanical Completion” will be achieved when each of the following conditions has been met:

6.2.1.1	Contractor has completed the design, engineering, procurement, permitting, assembly, construction, installation, and commissioning of the Balance of Plant (including without limitation all foundations and related civil work relating thereto), and such Balance of Plant are ready to support the commissioning, start-up and initial operation of the JEA Furnished Equipment;

6.2.1.2	Contractor has completed all assembly, installation and integration of the JEA Furnished Equipment (including without limitation all foundations and related civil work in support thereof), in accordance with the requirements of this Agreement, including: (1) the completion of all civil work and foundations for the JEA Furnished Equipment and the setting of all components of the JEA Furnished Equipment on foundations; (2) the connection of the Balance of Plant Equipment and the JEA Furnished Equipment, to each other as required by way of piping, wiring, controls, and safety systems; and (3) ensuring that:

all Balance of Plant Equipment is individually cleaned, leak checked, lubricated, and checked for alignment, lubrication, rotation, and hydrostatic and pneumatic pressure integrity, appropriately flushed, cleaned and statically tested,

all initial fills have been completed (including for the JEA Furnished Equipment),

all instruments are calibrated,

all relays are set,

all ground checks are made,

all piping is tested and flushed,

all motor rotation checks are complete,

the generator panels have been energized,

all facilities required to accept backfeed power are complete and ready,

all electrical circuits have been point-to-point checked to verify that such equipment and operating systems have been correctly installed and verified to respond to simulated test signals equivalent to actual signals received during operation, and

all Balance of Plant Equipment is ready for initial and continuous operation, and may be so operated, without damage thereto or to any other property and without injury to any person,

6.2.1.3	Contractor has caused the Power Island Equipment to have achieved Ready for First Fire;

6.2.1.4	Contractor has caused the Power Island Equipment to have achieved Ready for Full Steam Admission;

6.2.1.5	Contractor has otherwise completed, in accordance with Applicable Laws, Applicable Permits, and Prudent Industry Practices, all Work as necessary to cause the Balance of Plant to be capable of continually operating safely and in support of the intended commissioning, testing, and operation of the Power Island Equipment;

6.2.1.6	Contractor has completed all training as required under Section 2.2.14;

6.2.1.7	 Contractor has provided JEA with the preliminary copies of the Operation and Maintenance Manual as required under Section 2.2.24; and

6.2.1.8	Contractor has completed all Turnover Packages for Work completed to date, and JEA has approved all such Turnover Packages, as required under Section 2.2.25.

Certificate of Mechanical Completion.  When Contractor believes that it has achieved the requirements set forth above for Mechanical Completion, Contractor shall deliver a written notice of such determination in the form set forth in Exhibit K-3 (“Certificate of Mechanical Completion”) to JEA and JEA’s Engineer. The Certificate of Mechanical Completion shall be accompanied by a report in form acceptable to JEA and with sufficient detail to enable JEA to determine whether Contractor has achieved such requirements.

Achievement of Mechanical Completion. Within ten (10) Days of receipt of a Certificate of Mechanical Completion, JEA will inspect the same and either: (a) countersign the Certificate of Mechanical Completion, confirming that Mechanical Completion has bene achieved; or (b) notify Contractor in writing that such criteria have not been achieved, stating the reasons therefor. If JEA countersigns the Certificate of Mechanical Completion, the date on which JEA received the Certificate of Mechanical Completion shall be deemed the date Mechanical Completion has been achieved. If JEA notifies Contractor that such requirements have not been met, Contractor will promptly undertake such action or work as necessary to achieve such requirements and shall then issue another Certificate of Mechanical Completion to JEA and JEA’s Engineer stating that Contractor believes that such requirements have been achieved.  Such procedures shall be repeated until Mechanical Completion is achieved.  If JEA fails to either provide such certification of achievement or notification of non-achievement to Contractor within the aforesaid fifteen (15) Day period, then this will constitute a JEA Delay Event and Contractor will notify JEA of the delay.

Guaranteed Mechanical Completion Date; Late Mechanical Completion Liquidated Damages. Contractor guarantees that Mechanical Completion shall be achieved on or before the date set forth therefor in the Baseline Project Schedule as the “Guaranteed Mechanical Completion Date” (such date, as the same may be extended pursuant to a Change Order pursuant to Article 9, the “Guaranteed Mechanical Completion Date”). If Mechanical Completion does not occur on or before the Guaranteed Mechanical Completion Date, then Contractor will pay to JEA the applicable amounts as set forth in Exhibit A-1 (the “Late Mechanical Completion Liquidated Damages”) per Day for each Day after the Guaranteed Mechanical Completion Date that Mechanical Completion is not achieved.

Amounts Reasonable. The Parties hereby acknowledge and agree that the terms, conditions and amounts fixed as liquidated damages pursuant to this Section 6.2.4 are reasonable, considering the actual costs and damages that JEA will incur if Mechanical Completion is not achieved by the Guaranteed Mechanical Completion Date.  The amounts of these liquidated damages are agreed upon and fixed hereunder by the Parties because of the difficulty of ascertaining the exact amount of losses and/or costs that will be actually incurred by JEA in such event, and the Parties hereby agree that such amounts are a reasonable estimate of JEA’s probable loss (and are not a penalty) and that such amounts shall be applicable regardless of the amount of such lost revenues and increased costs actually incurred by JEA.  Contractor shall pay the Late Mechanical Completion Liquidated Damages required hereunder to JEA on a weekly basis on the last Business Day of each week during the period after the Guaranteed Mechanical Completion Date through the achievement of Mechanical Completion. Any amounts due hereunder may, at JEA’s option, be deducted from any unpaid amounts owed by JEA to Contractor. Both Parties are precluded from challenging the validity of such liquidated damages. Except as set forth in Section 12.2(e), the receipt of any such liquidated damages shall be JEA’s sole and exclusive remedy and Contractor’s only obligation for Contractor’s failure to achieve Mechanical Completion on or before the Guaranteed Mechanical Completion Date.

Refund of Late Mechanical Completion Liquidated Damages. Notwithstanding anything herein to the contrary, if Substantial Completion occurs on or prior to the Guaranteed Substantial Completion Date, then JEA will refund to Contractor any Late Mechanical Completion Liquidated Damages paid by Contractor hereunder.

Substantial Completion.

Criteria for Substantial Completion. Subject to Section 6.4.3, “Substantial Completion” shall be achieved when each of the following conditions has been met:

Mechanical Completion has been achieved;

Contractor has concluded, and JEA has accepted, a set of Completed BOP Performance Tests in accordance with Section 7.2.1, and either (a) all of the BOP Performance Guarantees have been demonstrated as having been achieved, or (b) all of the Must-Make Guarantees have been demonstrated as having been achieved and Contractor has paid to JEA the Performance Liquidated Damages as are due under Section 7.8.3;

the Facility Capability Demonstration Tests have been achieved;

the PIE Supplier has concluded, and JEA has accepted, a set of Power Island Equipment Performance Tests as described in Section 7.4, during which the Power Island Equipment Minimum Performance Guarantees have been achieved;

the PIE Supplier has completed and JEA has accepted a Reliability Test on the Power Island Equipment as described in Section 7.6 and the BOP Reliability Guarantee has been achieved;

Contractor has obtained all Contractor Permits as are required to be obtained and maintained as of Substantial Completion, and the same remain in full force and effect, except for Contractor Permits that if not in full force and effect do not prevent the normal operation of the Facility by JEA;

the Facility is completed and capable of being operated in the normal course of business in compliance with Applicable Laws and Applicable Permits;

Contractor has delivered, organized and catalogued those Special Tools as described in Section 2.2.12.3;

Contractor has removed all Contractor’s tools, construction equipment, machinery and surplus materials from the Facility and the Facility Site, except for those items as will be required by Contractor to achieve Final Completion, as required pursuant to Section 2.2.16.1;

Contractor has delivered to JEA all Operational Spare Parts ordered by JEA pursuant to Section 2.2.12.2; unless more time is required for such Operational Spare Parts to be delivered based on the manufacturer’s published lead time, and if and to the extent that Contractor has utilized any of JEA’s Operational Spare Parts, Contractor has either replaced such Operational Spare Parts or placed an order for such spare parts (on an expedited basis);

Contractor has delivered to JEA all lien releases and waivers related to the Work as are required under Section 5.4.2.2;

JEA and Contractor have agreed upon the final Punch-List as described in Section 6.5, and Contractor has completed performance of all Work except for any remaining items set forth in the approved Punch-List.

Certificate of Substantial Completion.  When Contractor believes that it has achieved the requirements set forth above for Substantial Completion, Contractor shall deliver a written notice of such determination in the form set forth in Exhibit K-4 (“Certificate of Substantial Completion”) to JEA and JEA’s Engineer. The Certificate of Substantial Completion shall be accompanied by a report in form acceptable to JEA and with sufficient detail to enable JEA to determine whether Contractor has achieved such requirements.

Achievement of Substantial Completion.  Within ten (10) Days of receipt of the Certificate of Substantial Completion, JEA will inspect the same and either: (a) countersign the Certificate of Substantial Completion; or (b) notify Contractor in writing that such criteria have not been achieved, stating the reasons therefor. Subject to Section 6.6.2, if JEA countersigns the Certificate of Substantial Completion, the date on which JEA received the Certificate of Substantial Completion shall be considered, for purposes of this Agreement, the “Substantial Completion Date”.  If JEA notifies Contractor that such requirements have not been met, Contractor will promptly undertake such action or work as necessary to achieve such requirements and shall then issue another Certificate of Substantial Completion to JEA and JEA’s Engineer stating that Contractor believes that such requirements have been achieved. Such procedure shall be repeated until Substantial Completion is achieved. If JEA fails to either provide such certification of achievement or notification of non-achievement to Contractor within the aforesaid ten (10) Day period, then this will constitute and JEA Delay Event and Contractor will notify JEA of such delay.

Guaranteed Substantial Completion Date; Late Substantial Completion Liquidated Damages. Contractor guarantees that Substantial Completion shall be achieved on or before the date set forth therefor in the Baseline Project Schedule as the “Guaranteed Substantial Completion Date” (such date, as the same may be extended pursuant to a Change Order pursuant to Article 9, the “Guaranteed Substantial Completion Date”). If Substantial Completion does not occur on or before the Guaranteed Substantial Completion Date, then Contractor will pay to JEA the applicable amounts as set forth in Exhibit A-1 (the “Late Substantial Completion Liquidated Damages”) per Day for each Day after the Guaranteed Substantial Completion Date that Substantial Completion is not achieved.

Amounts Reasonable. The Parties hereby acknowledge and agree that the terms, conditions and amounts fixed as liquidated damages pursuant to this Section 6.3.4 are reasonable, considering the actual costs and damages that JEA will incur if Substantial Completion is not achieved by the Guaranteed Substantial Completion Date.  The amounts of these liquidated damages are agreed upon and fixed hereunder by the Parties because of the difficulty of ascertaining the exact amount of losses and/or costs that will be actually incurred by JEA in such event, and the Parties hereby agree that such amounts are a reasonable estimate of JEA’s probable loss (and are not a penalty) and that such amounts shall be applicable regardless of the amount of such lost revenues and increased costs actually incurred by JEA. Contractor shall pay the Late Substantial Completion Liquidated Damages required hereunder to JEA on a weekly basis on the last Business Day of each week during the period after the Guaranteed Mechanical Completion Date through the achievement of Substantial Completion. Any amounts due hereunder may, at JEA’s option, be deducted from any unpaid amounts owed by JEA to Contractor. Both Parties are precluded from challenging the validity of such liquidated damages. Except as set forth in Section 12.2(f), the receipt of any such liquidated damages shall be JEA’s sole and exclusive remedy and Contractor’s only obligation for Contractor’s failure to achieve Substantial Completion on or before the Guaranteed Substantial Completion Date.

Creation of Punch-List.

In conjunction with its submission of the Turnover Package for the Balance of Plant, Contractor may propose items to be included on the Punch-List with respect to each such system, provided that such proposed items must comply with the criteria below.  In any event, no later than thirty (30) Days prior to the date that Contractor anticipates achieving Substantial Completion, Contractor will prepare and deliver to JEA a single, written list setting forth all of the items of Work that remain to be performed to complete the Work; provided, that, unless JEA otherwise consents in writing, such items of Work on such list shall only be items that are: (a) minor in nature; (b) not related to the reliable operation of the Facility; (c) not related to the safety of the Facility; (d) not related to the compliance of the Facility with any Applicable Laws or Applicable Permits; and (e) do not require a shutdown of the Facility to perform.  Such list shall also state the proposed time limits within which Contractor will complete each of such remaining Work items.  Upon its receipt of such list, JEA will review the same and notify Contractor of any proposed revisions (including additions) thereto. The JEA Project Manager and the Contractor Project Manager will then meet and consult in good faith to agree upon the definitive, final, single list (including the approved time limits within which Contractor will perform such remaining Work items) (such final list, as agreed to by JEA, the “Punch-List”).  If the Parties cannot agree on the Punchlist, JEA will develop a Punchlist and deliver it to Contractor within thirty-five (35) Days after Substantial Completion. Failure to include corrective work on the Punch-List does not relieve Contractor from its responsibility to complete the Work required by the Agreement. Once the final Punch-List is agreed upon, Contractor will immediately begin performing the items thereon. If Contractor has not completed such Work within the approved time limits set forth in the final Punch-List, then JEA may have such items completed at Contractor’s expense.

Transfer of Responsibility to JEA.

Transfer Time.  Subject to Section 6.5.2, as of 12:00:01 AM on the Day after the Day when JEA delivers to Contractor the Certificate of Substantial Completion confirming that Substantial Completion has been achieved (the “Transfer Time”), JEA shall, then and thereafter, be solely responsible for the operation and maintenance of the Facility. Following that date, and prior to Final Completion, Contractor shall have reasonable access to the Facility and the reasonable cooperation of JEA so as to: (a) complete any Punch-List items, and (b) correct any Work that does not conform to the Warranties; provided, however, that such right of reasonable access to the Facility shall not include the right to require a shutdown or reduction in the operations of the Facility, and (ii) Contractor will also have the access rights described in Section 6.5.2. The achievement of Substantial Completion and/or JEA’s use or operation of the Facility at any time shall not be deemed or construed to imply JEA’s acceptance of any Work that is not in compliance with this Agreement.

JEA’s Right to Commercially Operate. Notwithstanding anything in this Agreement to the contrary, if, at any time after Mechanical Completion but prior to the Substantial Completion Date, JEA desires to take over and operate the Facility, then JEA will notify Contractor of the same, designating in such notice the time at which JEA will take control the Facility for this purpose (the “Takeover Time”).  As of the Takeover Time, (a) JEA shall then and thereafter be solely responsible for the operation and maintenance of the Facility, and (b) notwithstanding anything in this Agreement to the contrary, the “Substantial Completion Date” will be deemed to have occurred on that date for purposes of (and only for purposes of) any accrual of Late Substantial Completion Liquidated Damages, the payment for the achievement of the Substantial Completion Milestone and Section 8.2 (commencement of Warranty Period).  Subject to the following sentences, the foregoing shall not relieve Contractor of its obligation to achieve the requirements of Substantial Completion or Final Completion. Following the Takeover Time, Contractor will still have the testing responsibilities described in Article 7, subject to a testing schedule as directed by JEA; provided, that such testing schedule shall be structured so that the commencement of such tests will occur within one hundred and eighty (180) Days after such Takeover Time (and if JEA does not allow such testing to be completed within such period, then such testing will be deemed successfully completed).  For the avoidance of doubt, but subject to the foregoing, Contractor will remain obligated to pay Performance Liquidated Damages pursuant to Section 7.9.2 based upon the final results of the applicable BOP Performance Test.

Final Completion.

Criteria for Final Completion.  Subject to Section 6.6.3, “Final Completion” shall be achieved when each of the following conditions has been met:

Substantial Completion has been achieved;

Contractor has delivered, organized and catalogued all replacement spare parts as required pursuant to Section 2.2.12.2;

Contractor has completed the Facility Site clean-up work as described in Section 2.2.16.2;

Contractor has completed all Punch-List items in accordance with this Agreement;

Contractor has completed any work required under Article 8 with respect to any claims under the Warranties about which Contractor has been given notice prior to the completion of the last Punch-List item;

Contractor has provided the conformed to construction records Project Data Books to JEA (in both hard and electronic copy), as required under Section 2.2.25;

Contractor has delivered to JEA all such final lien waivers and releases as are required under Section 5.4.2.3;

Contractor has delivered to JEA copies of all Major Subcontracts and other documents as required under Section 2.8.4 and all third-party software warranties as required under Section 8.7; and

Contractor has provided JEA with the final Operation and Maintenance Manuals in accordance with Section 2.2.24.

Certificate of Final Completion. When Contractor believes that it has achieved the requirements set forth above for Final Completion, Contractor shall deliver a written notice of such determination in the form set forth in Exhibit K-5 (“Certificate of Final Completion”) to JEA and JEA’s Engineer.  The Certificate of Final Completion shall be accompanied by a report in a form acceptable to JEA and with sufficient detail to enable JEA to determine the achievement by Contractor of all Work and other work to be performed under this Agreement, including the Punch-List items, and such other information that JEA or JEA’s Engineer may require to determine whether Final Completion has been achieved.

Achievement of Final Completion. JEA will within thirty (30) Days following JEA’s receipt of the Certificate of Final Completion, either: (a) countersign the Certificate of Final Completion; or (b) notify Contractor in writing that such requirements have not been achieved, stating the reasons therefor. If JEA countersigns the Certificate of Final Completion, the date on which JEA received the Certificate of Final Completion shall be deemed the date Final Completion has been achieved.  In the event JEA notifies Contractor that such requirements have not been met, Contractor shall promptly take such action as necessary to achieve such requirements and shall then issue to JEA another Certificate of Final Completion.  Such procedure shall be repeated until Final Completion is achieved.  If JEA fails to either countersign the Certificate of Final Completion or notify Contractor of Contractor’s non-achievement of Final Completion within the aforesaid thirty (30) Day period, then Final Completion shall be deemed achieved as of the date of Contractor’s Certificate of Final Completion; provided, that such deemed achievement will not relieve Contractor of its obligation to achieve the criteria for Final Completion.

Final Completion Deadline.  In the event that Contractor does not achieve Final Completion within (i) one-hundred and eighty (180) Days following the Substantial Completion Date,  JEA shall have the right, but not the obligation, to step-in and arrange for the completion of such items of Work as are required under this Agreement to achieve Final Completion and the reasonable price paid by JEA to others in order to complete such items of Work may be either (a) deducted by JEA from the amounts due to Contractor that JEA is retaining as part of the Punch-List Withholding Amount, or (b) invoiced to Contractor and Contractor shall pay such invoiced amounts within ten (10) Days of receipt of such invoice.

Performance TESTING and Guarantees

Notices and Preparations for Commencement of Testing.

Each Monthly Progress Report will include an estimate of the date on which Contractor intends to achieve Mechanical Completion and the date(s) on which the initial tests on the Facility are expected to commence as described in this Article 7.  At least one hundred eighty (180) Days prior to the then-scheduled date for the first commencement of any such testing, Contractor will provide JEA with (a) a copy of the  proposed testing and checkout procedures (which shall be subject to JEA review, and Contractor will make such revisions thereto as are directed by JEA), and (b) reasonable estimates of the net quantity of energy to be generated by the Facility during such testing.  Contractor will thereafter work with JEA to develop and agree upon a written protocol for week-ahead and Day-ahead nomination of fuel as required for testing (the “Fuel Nomination Protocol”) and will use commercially reasonable efforts to abide by such Fuel Nomination Protocol at all times during start-up and commissioning of the Facility. Contractor will give JEA at least ninety (90) Days’ written notice in advance of the date on which Contractor will require backfeed power to energize the Facility for all start-up and commissioning activities therefor. JEA and JEA’s Engineer will have the right to be present or represented during all tests. Prior to commencing any test, unless directed by JEA to the contrary, Contractor will confirm with JEA that the test energy resulting therefrom has been scheduled by JEA. All tests hereunder are to be conducted in accordance with applicable Testing Guidelines. Any testing that is not performed in accordance therewith shall be invalid.

BOP Performance Testing.

In conjunction with the Power Island Equipment Performance Tests for the Power Island Equipment, Contractor shall undertake such testing and measurements as are necessary to demonstrate that the Balance of Plant meet the BOP Performance Guarantees (the “BOP Performance Tests”). Within no later than five (5) Business Days following completion of any BOP Performance Test, Contractor shall report the BOP Performance Test data to JEA. After Contractor has performed BOP Performance Tests demonstrating compliance with the applicable BOP Performance Guarantees, Contractor may notify JEA in writing (such notice, the “BOP Performance Testing Completion Notice”) that it elects to nominate such BOP Performance Tests as “Completed BOP Performance Tests.”  The BOP Performance Testing Completion Notice will be accompanied by a written report of BOP Performance Test results.  As soon as practicable but in any event within seven (7) Days after JEA’s receipt of the BOP Performance Testing Completion Notice, JEA will give written notice to Contractor either accepting or rejecting the BOP Performance Test report.  If JEA accepts the BOP Performance Test report, then the date JEA received the BOP Performance Testing Completion Notice will be considered the date on which JEA has accepted such nominated BOP Performance Tests as a Completed BOP Performance Tests.  In the event that JEA rejects the BOP Performance Test report (in which event, JEA will inform Contractor of the reason for such rejection), Contractor will undertake such action or work necessary to achieve “Completed BOP Performance Tests” and shall then notify JEA that it wishes to nominate such BOP Performance Tests as “Completed BOP Performance Tests.” Such procedure shall be repeated until JEA accepts a BOP Performance Test report submitted by Contractor.  If JEA fails to notify Contractor that it accepts or rejects a nominated BOP Performance Test within seven (7) Days following JEA’s receipt of a given BOP Performance Testing Completion Notice, then Contractor may notify JEA regarding the delay, and if JEA does not respond within two (2) Days, then such non-response shall a JEA Delay Event and shall entitle Contractor to a Change Order under Section 9.3.3.

Re-Setting of Equipment.

During those periods in which no testing is being performed, Contractor shall (a) perform whatever Work is necessary, including re-setting of Balance of Plant and repairs of damage or modifications to the Facility caused by testing, to return the applicable Balance of Plant Equipment to the best operating control settings and configurations, and (b) verify that the PIE Supplier has re-set all control parameters for normal operating conditions.

Power Island Equipment Testing.

Testing Start Date Notice.  Under the PIE Purchase Agreement, during the Commissioning Period, PIE Supplier will notify JEA in writing once PIE Supplier believes that a Power Island Equipment is ready for the commencement of Power Island Equipment Performance Tests and Reliability Test. JEA will then, in consultation with Contractor, respond to PIE Supplier within three (3) Days after receipt of PIE Supplier’s notice, in writing, with proposed dates for any such testing to occur (the “Testing Start Date Notice” for such Power Island Equipment).  Such proposed dates in the Testing Start Date Notice shall be within a reasonable period of time following JEA’s receipt of the aforesaid notice from PIE Supplier, but not to exceed seven (7) Days after the date of issuance of the Testing Start Date Notice. Contractor will cooperate in connection with the foregoing process. If for reasons attributable to Contractor, the Power Island Equipment Performance Tests are not started within thirty (30) Days of the date stated in the Testing Start Date Notice, Contractor will be liable to JEA for any amounts it must pay to PIE Supplier to cover its documented reasonable additional costs of demobilizing and remobilizing personnel as a result of such delay in Power Island Equipment Performance Testing and Reliability Test.

Power Island Equipment Minimum Performance Guarantees. The Parties acknowledge that under the PIE Purchase Agreement the PIE Supplier has guaranteed to JEA the achievement of the Power Island Equipment Minimum Performance Guarantees for the Power Island Equipment.  Contractor guarantees to JEA that no defect or failure of the Work or the Balance of Plant Equipment nor any other action or omission of Contractor or Contractor’s Personnel, including in connection with the installation of the Power Island Equipment or the interface of the same with any portion of the Balance of Plant Equipment, shall result in the failure of such Power Island Equipment to meet the Power Island Equipment Minimum Performance Guarantees for such Power Island Equipment.  If any defect or failure of the Work or any other action or omission of Contractor or Contractor’s Personnel causes or results in the failure of an Power Island Equipment to meet its Power Island Equipment Minimum Performance Guarantees, then Contractor shall at its own expense promptly take all actions as may be necessary or appropriate in order to cure such defect, failure, act or omission so that it no longer causes the Power Island Equipment to fail to meet its Power Island Equipment Minimum Performance Guarantees.

Power Island Equipment Performance Tests.  Contractor acknowledges that PIE Supplier will work with JEA to develop the testing procedures and protocols for the Power Island Equipment. Contractor will, at JEA’s request, participate in and contribute to such efforts, including reviewing and commenting on any proposed procedures and protocols.  JEA will provide to Contractor the final, agreed-upon testing procedures and protocols for the Power Island Equipment (the “Power Island Equipment Testing Procedures”). After Mechanical Completion has been achieved and Contractor has been provided the Certificate of Ready to Test from the PIE Supplier in accordance with the PIE Purchase Agreement, the PIE Supplier shall, with Contractor’s and JEA’s support, cause to be performed and re-performed if necessary (and as described in Section 6.3, Contractor will allow and provide PIE Supplier access to the Facility in connection with the same), in accordance with the Power Island Equipment Testing Procedures, each of the tests required to demonstrate the compliance or non-compliance of such Power Island Equipment with its Power Island Equipment Minimum Performance Guarantees (the “Power Island Equipment Performance Tests” for such Power Island Equipment).  Contractor will cooperate and coordinate with and support JEA and PIE Supplier in connection with the performance of the Power Island Equipment Performance Tests on the Power Island Equipment at all times until their completion, including taking responsibility for the operation and functionality of all applicable Balance of Plant Equipment during the same.

Reliability Testing.

The Parties acknowledge that the Power Island Equipment Minimum Performance Guarantees for the Power Island Equipment include a guarantee that the Power Island Equipment will achieve one hundred percent (100%) reliability during a 72-consecutive-hour reliability test to be performed by JEA with the support of PIE Supplier as part of the Power Island Equipment Performance Tests, as the same is further described in the Power Island Equipment Technical Specifications (the “Reliability Test”). Without limiting Section 7.4.2, Contractor guarantees to JEA that during the Reliability Test for the Power Island Equipment, the Balance of Plant Equipment will operate at one hundred percent (100%) reliability (with no trips or forced load restrictions) (the “BOP Reliability Guarantee”).

Pre-Substantial Completion Remedial Plan.

If a BOP Performance Test demonstrates that the applicable portions of the Balance of Plant Equipment fail to achieve the applicable BOP Performance Guarantees, or if a Reliability Test demonstrates that the applicable portions of the Balance of Plant Equipment fail to achieve the BOP Reliability Guarantee, then Contractor will promptly provide to JEA a written plan describing the actions Contractor intends to take in order to cure such failure, and Contractor will accept and incorporate all comments from JEA regarding such plan.  Contractor will implement such plan, and Contractor will keep JEA apprised on a daily basis as to the status of its efforts to cure the failure.

Output During Testing.

At all times during start-up, testing, and commissioning of the Facility, JEA may, at no expense to Contractor, arrange for the disposition of the Facility’s output of electricity in such manner as JEA shall determine.  Any output of electricity generated by the Facility at any time, and all proceeds from the sale thereof, shall be the property of JEA.

BOP Performance Guarantees; Performance Liquidated Damages.

BOP Performance Guarantees.  As the “BOP Performance Guarantees,” Contractor guarantees that, as will be demonstrated via each Completed BOP Performance Test, the Balance of Plant will:

- (a) 	be capable of supporting all process operating conditions needed for the Power Island Equipment (operating individually and simultaneously) to operate without interruption or load restriction in accordance with the operating cases as set forth in Exhibit T;  and

(b)	achieve: (i) the BOP Auxiliary Load Guarantee; (ii) the BOP Noise Guarantee; (iii) the ST Back Pressure Guarantee; (iv) the HP Steam Piping Pressure, (v) the Hot Reheat Steam Piping Pressure; (vi) the Cold Reheat Steam Piping Pressure; (vii) the LP Steam Piping Pressure; (viii) the Startup Duration; (ix) the BOP Air Emissions; and (x) the BOP Reliability Guarantee, all as set forth in Exhibit A-1.

Make Good Guarantees. Contractor’s obligation to meet the BOP Noise Guarantee, BOP Air Emissions, BOP Reliability Guarantee, and Startup Duration under Section 7.8.1 constitute absolute and fundamental components of this Agreement (the “Must-Make Guarantees”). In this respect, this Agreement does not provide for the payment of liquidated damages in lieu of achieving the Must-Make Guarantees. Contractor will do all things necessary or appropriate to achieve the Must-Make Guarantees.

BOP Performance Liquidated Damages. Provided that the Balance of Plant Equipment has achieved the Must-Make Guarantees, if Contractor fails to cause the Balance of Plant Equipment to meet the BOP Auxiliary Load Guarantee, ST Back Pressure Guarantee, HP Steam Piping Pressure, Hot Reheat Steam Piping Pressure, Cold Reheat Steam Piping Pressure, and LP Steam Piping Pressure at the time Contractor submits the applicable Certificate of Substantial Completion, then, subject to Section 7.8.4, Contractor shall pay to JEA as liquidated damages the amounts of liquidated damages applicable to each such BOP Performance Guarantee as set forth therefor in as set forth in Exhibit A-1 (the “Performance Liquidated Damages”).

Performance Cure Period.  If at the Substantial Completion Date (or at the time of testing after the Takeover Time as described in Section 6.5.2), a BOP Performance Test demonstrates that the applicable Balance of Plant Equipment have achieved the applicable Must-Make Guarantees but have failed to meet the applicable BOP Performance Guarantees, then, provided that Contractor has paid JEA the applicable Performance Liquidated Damages as described in Section 7.8.3, Contractor will, during the one hundred eighty (180) Day period following the Substantial Completion Date, be granted limited access as provided below, to make, at its own expense, adjustments and corrections to the applicable Balance of Plant Equipment so as to attempt to reach one hundred percent (100%) of the BOP Performance Guarantees (the “Cure Period”). At the end of the Cure Period, if based upon the most recent test performance results Contractor has improved any such performance, JEA will refund to Contractor any Performance Liquidated Damages paid by Contractor (or set off by JEA) as are attributable to the improved performance.  If such demonstrated performance has decreased, Contractor will pay additional Performance Liquidated Damages for such incremental decrease in performance (but in all events the Must-Make Guarantee obligations above will apply). During the Cure Period, JEA will use commercially reasonable efforts to afford Contractor reasonable access to the applicable portions of the applicable Balance of Plant Equipment for purposes of allowing Contractor to undertake its efforts as described above at such times as JEA in its sole discretion deems appropriate but subject always to JEA’s operating requirements and priorities. JEA does not guarantee Contractor any minimum amount of time or access hereunder. If due to JEA’s operating requirements and priorities re-testing of the Facility does not occur during the Cure Period, then unless the Parties agree to extend the Cure Period, Contractor will be relieved of its obligations to attempt any further cure hereunder.

Performance Liquidated Damages Reasonable.  JEA and Contractor hereby acknowledge and agree that the Performance Liquidated Damages fixed as liquidated damages pursuant to this Section 7.8 are reasonable liquidated damages, considering the actual increased costs and reduction in the value of the Facility that JEA will sustain in the event of Contractor’s failure to achieve the Auxiliary Load Guarantees.  The amounts of the Performance Liquidated Damages are agreed upon and fixed hereunder by the Parties as liquidated damages because of the difficulty of ascertaining the exact amount of such increased costs and reduction in value that will actually be sustained by JEA in the event of any such failure by Contractor, and the Parties hereby agree that the Performance Liquidated Damages specified herein are a reasonable estimate of JEA’s probable loss (and not a penalty) and that they shall be applicable and payable regardless of the amount of such reduction in value actually sustained by JEA.  Provided that Contractor achieves the Must-Make Guarantees, payment of the Performance Liquidated Damages will be Contractor’s sole and exclusive liability and JEA’s sole and exclusive remedy for Contractor’s failure to achieve the BOP Performance Guarantees.

Contractor’s Warranties

Warranties.

As the “Warranties,” Contractor warrants that, for the duration of the Warranty Period:

(a)	the Balance of Plant Equipment will be: (i) free from defects in design (based upon prudent industry design standards as of the date of manufacture), workmanship and materials; (ii) provided  in accordance with: (A) this Agreement, the Construction Documents and the plans and specifications and accompanying data set forth in the Scope of Work, and (B) all Applicable Laws, Applicable Permits, Applicable Codes and Standards, and  Prudent Industry Practices; and (iii) fit for the use and purpose specified or referred to in the Contract Documents;

(b)	 the Balance of Plant Equipment will be compatible with the distributed control system (DCS) supplied by the PIE Supplier;

(c)	all engineering and design services provided by Contractor or any of Contractor’s Personnel in connection with the Work will be performed: (i) in accordance with this Agreement; and (ii) with the degree of skill and care utilized by nationally-recognized engineers and designers in the United States as of the date such services were performed; and

(d)	all services other than engineering and design services covered by the warranty as stated in clause (c) above, provided by Contractor or any of Contractor’s Personnel in connection with this Agreement will be: (i) performed in a professional, prudent and workmanlike manner that is free from defects in workmanship; and (ii) in accordance with: (A) this Agreement, the Construction Documents and the plans and specifications and accompanying data set forth in the Scope of Work, and (B) all Applicable Laws, Applicable Permits, Applicable Codes and Standards, and Prudent Industry Practices.

Warranty Period.

Subject to Section 8.4, the Warranties with respect to each item or portion of the Work as described above will remain in full force and effect for a period beginning on the Substantial Completion Date and ending one (1) year thereafter; provided, that with respect to Punch-List items or services that are provided after Substantial Completion, the Warranties therefor will endure until one (1) year after Final Completion (each such period, the “Warranty Period”). The Parties acknowledge that the Warranties are given by Contractor to JEA in addition to any Subcontractor warranties that Contractor assigns to JEA pursuant to Section 2.8.5, and that the expiration of the Warranty Period is only applicable to the Warranties and will have no effect on any assigned Subcontractor warranties that may be of longer duration.

Repair of Defects.

If, during the Warranty Period, JEA discovers that the Work or any part thereof fails to meet the Warranties, JEA will, prior to the expiration of the applicable Warranty Period (or within ten (10) Business Days thereafter, provided JEA can demonstrate that the failure occurred prior to the end of the applicable Warranty Period), notify Contractor of such failure and make available access to that portion of the Facility as necessary for correction of the defect as soon as reasonably practicable. Within no later than five (5) Days after receipt of such notice, Contractor will provide to JEA, for JEA’s approval, a proposed plan for undertaking its obligations under this Section 8.3. Contractor will incorporate any revisions to such plan as are instructed by JEA and will then promptly proceed to undertake its obligations hereunder in accordance with such plan. In connection with any Work that fails to meet the Warranties, Contractor’s obligations hereunder are to: (a) cure such failure to bring the applicable Work into compliance with the Warranties, and (b) perform such tests as JEA may reasonably require to demonstrate the cure of such failure.  Contractor will bear any and all costs and expenses associated with the foregoing.  Contractor will bear all costs of removal and replacement of the nonconforming item, and all costs of transportation and transit and all costs of repairs and replacements. If Contractor fails to commence to undertake its obligations hereunder in accordance with the aforesaid plan, or to complete such obligations within the timeline stated in the plan (unless unanticipated circumstances are encountered that delay the same), JEA may after notice to Contractor and a cure period of five (5) Business Days, cause such obligations to be undertaken, at Contractor’s expense, while using reasonable efforts to mitigate such costs and expenses.

Warranty Period Extension.

Any Work re-performed and any part of the Balance of Plant Equipment that is reworked, repaired or replaced in satisfaction of Contractor’s obligations in connection with the Warranties will be re-warranted by Contractor pursuant to the same Warranties set forth in Section 8.1, and Contractor will have the same obligations in relation thereto as set forth in Section 8.3, for a period expiring upon the later of: (a) one (1) year from the date such re-performance, rework, repair or replacement is completed; or (b) the date that is the end of the original Warranty Period; provided, that in no event will any Warranty extend beyond the date that is two (2) years after the applicable commencement date of such original Warranty Period.

Warranty of Title.

Contractor warrants and guarantees that title to all materials, supplies and equipment provided to JEA by Contractor under this Agreement shall pass to JEA (in accordance with Section 2.5.1) free and clear of all claims, liens, security interests and other encumbrances materials, supplies and equipment shall not be acquired by Contractor subject to any agreement under which a security interest or other lien or encumbrance is retained by any Person.

Limitation on Warranties.

Notwithstanding anything to the contrary in this Agreement, Contractor’s Warranties do not extend or apply to deterioration constituting normal wear and tear, or to damage resulting from (i) failure of JEA to store, operate or maintain the warranted item (once JEA has taken care custody and control thereof) in accordance with written Operation and Maintenance Manuals provided by Contractor to JEA, and in the absence thereof, in accordance with Prudent Industry Practices; (ii) improper repairs or alteration, misuse, neglect or accident by JEA or JEA’s agents; or (iii) an event of Force Majeure.

Exclusive Warranties.

THE WARRANTIES AS SET FORTH IN THIS ARTICLE 8 ARE EXCLUSIVE, AND NO OTHER WARRANTIES OF ANY KIND, WHETHER STATUTORY, EXPRESS, OR IMPLIED (INCLUDING ALL WARRANTIES OF MERCHANTABILITY AND FITNESS FOR A PARTICULAR PURPOSE OR ALL WARRANTIES ARISING FROM COURSE OF DEALING OR USAGE OF TRADE) SHALL APPLY.  PROVIDED THAT CONTRACTOR PERFORMS ITS OBLIGATIONS UNDER THIS ARTICLE 8, AND WITHOUT PREJUDICE TO CONTRACTOR’S OBLIGATION TO ACHIEVE SUBSTANTIAL COMPLETION AND FINAL COMPLETION, JEA’S EXCLUSIVE REMEDIES AND CONTRACTOR’S ONLY OBLIGATIONS ARISING OUT OF OR IN CONNECTION WITH DEFECTIVE WORK AFTER SUBSTANTIAL COMPLETION, WHETHER BASED IN CONTRACT, IN TORT (INCLUDING NEGLIGENCE AND STRICT LIABILITY), OR OTHERWISE, SHALL BE THOSE STATED IN THIS WARRANTY SECTION; PROVIDED, THAT IN NO EVENT SHALL THE FOREGOING LIMIT: (A) CONTRACTOR’S OBLIGATION TO PAY LIQUIDATED DAMAGES AS AND WHEN DUE UNDER THIS AGREEMENT, OR (B) CONTRACTOR’S OBLIGATIONS FOR THIRD PARTY CLAIMS UNDER ARTICLE 11 (INDEMNIFICATION).

Changes

Changes.

Without invalidating this Agreement, JEA may: (a) make certain changes to the Work, including any addition to, deletion from, suspension of or other modification to the quality, function, scope or pace of the Work; (b) to the extent specifically provided for in this Article 9, adjust the Guaranteed Dates, the Baseline Project Schedule and/or the Contract Price and other provisions of this Agreement (all of the foregoing, “Changes”, any of the foregoing, a “Change”). Changes may only be authorized by a written order executed by both Parties (each such order, a “Change Order”), a Change Directive, or a Reductive Change Directive, in each case, in accordance with this Article 9.  The form of Change Order to be used by the Parties is set forth in Exhibit M. The Parties acknowledge that, to the extent any Change Order Request would result in an increase to JEA’s maximum indebtedness for the Project, such Change Order Request shall be subject to prior approval by JEA’s Board of Directors or its designee.

Procedure for Changes.

Change Order Requests Initiated by Contractor.

(a)	Within no later than ten (10) Business Days after Contractor becomes aware of any event or circumstance that (i) has impacted (even if the exact extent of the impact is then unknown) the schedule or cost of performing the Work, and (ii) may entitle Contractor to receive a Change Order under this Agreement, Contractor will notify JEA of the same, providing in such notification all such relevant information as is then available regarding the event or circumstance and its actual and potential impacts on the schedule and costs for performing the Work (such notice, the “Preliminary Change Order Notice”). Within no later than ten (10) Business Days after Contractor issues a Preliminary Change Order Notice with respect to an event or circumstance, if Contractor believes that it is entitled to a Change Order under this Agreement with respect thereto, then Contractor will issue to JEA a “Change Order Request” in respect of such event or circumstance.  A Change Order Request shall include documentation sufficient to enable JEA to determine: (i) the factors allegedly necessitating the required Change Order, to the extent known; (ii) the impacts that the event or circumstance has had and is projected to have on Contractor’s Direct Costs in performing the Work, to the extent known; and (iii) the impact that the event or circumstance has had and is projected to have on the progress of the Work based upon the most recent Monthly Updated Schedule (including each Guaranteed Date), to the extent known.  Contractor will also promptly provide to JEA such additional information as JEA may request in connection with any Preliminary Change Order Notice or Change Order Request.  In the event and to the extent that at the time of submittal of the Change Order Request the impacts on Contractor’s Direct Costs in performing the Work or on the progress of performing the Work cannot be finally known, Contractor will state this in the Change Order Request and will provide written updates on a weekly basis that supplement such Change Order Request with any further information that is known.

(b) 	Contractor will always act in good faith and be attentive to identify any event or circumstance that may require a Change Order under Section 9.3 and promptly evaluate the impacts thereof.  In any event, if Contractor fails to provide JEA with a Preliminary Change Order Notice or Change Order Request (or updates thereto) by the required deadlines set forth above then notwithstanding anything in this Article 9 to the contrary Contractor will be deemed to have waived any right to receive a Change Order as a result of such event.

(c)	Without limiting Contractor’s other obligations under this Section 9.2.1 or under Sections 9.3 and 9.5.2, except in the event of an emergency that renders such prior notice impracticable, Contractor will notify JEA in writing prior to incurring any additional Direct Costs in performing the Work for which Contractor intends to seek Change Order relief under Sections 9.3 and 9.5.2, and in such notice will describe the sources and amounts of such Direct Costs in reasonable detail. In the event of an emergency requiring the expenditure of Direct Costs, Contractor will notify JEA in writing promptly after incurring such Direct Costs.

(d)	Upon its receipt of a Change Order Request, JEA may, but except as provided in Section 9.3 below, shall not be obligated to, issue a Change Order pursuant to a Change Order Request.  Unless otherwise stated by JEA in writing, any work outside the Work described in this Agreement performed by Contractor prior to its having received an executed Change Order from JEA will be considered unauthorized work and will be at Contractor’s sole risk and expense.

Changes Initiated by JEA.  If JEA desires to make a Change described in clause (a) of the definition of “Change,” then JEA will submit a written notice proposing such Change (a “Change Order Notice”) to Contractor.  Contractor will promptly review the Change Order Notice and notify JEA in writing within  ten (10) Business Days of the options for implementing the proposed Change (including, if possible, any option that does not involve an extension of time) and the estimated effect(s), if any, that each such option would have on the Contract Price and the Guaranteed Dates to the extent known.  Based upon such information, JEA and Contractor may mutually agree, but shall not be obligated, to execute a Change Order implementing the Change included in such Change Order Notice. Except as provided in Section 9.5.1.1, Contractor shall not, and shall not be obligated to, proceed with any Change pursuant to this Section 9.2.2 unless the Change Order is mutually agreed to and executed by the Parties

Permitted Change Orders.

Subject to Section 9.2.1, and provided that Contractor has used commercially reasonable efforts to avoid and mitigate any potential delays to the achievement of the Guaranteed Dates and any increased Direct Costs resulting from the following events, Contractor will, to the extent described in and subject to the requirements of Sections 9.4 and 9.5.2, as applicable, be entitled to receive Change Orders for the following events. Change Order(s) issued under this Section 9.3 shall be Contractor's sole and exclusive remedy and compensation for any additional costs and/or delays, as applicable, resulting from any event or circumstance entitling Contractor to a Change Order under this Section.

Force Majeure Event.  If and to the extent that an event of Force Majeure causes Contractor to suffer a delay in its performance of the Work, then Contractor will be entitled to a Change Order extending the applicable Guaranteed Dates as described in Section 9.4.2.

Suspension of Work by JEA.  In the event that JEA suspends the Work pursuant to the provisions of Section 4.4 (and excluding any suspension resulting by reason of any act or omission of Contractor or its Personnel) or a suspension results from Contractor’s exercise of its rights under Section 12.7 then: (a) Contractor will be entitled to a Change Order extending the applicable Guaranteed Dates as described in Section 9.4.2; and (b) to the extent that such suspension results in additional Direct Costs for Contractor to perform the Work, JEA will, via Change Order, increase the Contract Price as described in Section 9.5.2.

JEA Delays. If and to the extent that a JEA Delay Event cause(s) Contractor to suffer a delay in the Critical Path or results in additional Direct Costs to perform the Work, Contractor will be entitled to a Change Order extending the applicable Guaranteed Dates as described in Section 9.4.2 and/or increasing the Contract Price as described in Section 9.5.2. If a JEA Delay Event is a result of a Force Majeure event, this Section 9.3.3 shall not apply and Section 9.3.1 shall apply.

Change of Law; Change in Codes and Standards. If and to the extent that a Change of Law or Change in Applicable Codes and Standards occurs that causes Contractor to suffer a delay in the Critical Path, or results in additional Direct Costs to perform the Work then Contractor will be entitled to a Change Order that increases the Contract Price as described in Section 9.5.2, and/or extends the applicable Guaranteed Dates as described in Section 9.4.2.

Hazardous Materials.

Delays Due to Suspension of Work.  If Contractor encounters material Released on the Facility Site that it reasonably believes to be a Pre-Existing Hazardous Material, and, as required under Section 2.2.20.3, ceases performance of any Work in the area affected and reports the condition to JEA in writing, then, once Contractor has been instructed by JEA to resume performance of the Work, Contractor will be entitled to a Change Order that: (a) extends the applicable Guaranteed Dates as described in Section 9.4.2, and (b) to the extent such cessation of Work results in additional Direct Costs for Contractor to perform the Work, increases the Contract Price as described in Section 9.5.2.

Costs and Delays Due to Removal Activities. If Contractor encounters material Released on the Facility Site that it reasonably believes to be a Pre-Existing Hazardous Material, and, pursuant to Section 2.2.20.3, JEA has instructed Contractor (and Contractor has agreed) to take actions in connection with the removal and/or remediation of such Hazardous Material in order to allow continued performance of the Work, then: (a) to the extent that the taking of such actions causes Contractor to suffer a delay in the Critical Path, JEA will, via Change Order, extend the applicable Guaranteed Dates as described in Section 9.4.2; and (b) increase the Contract Price as described in Section 9.5.2.

Man-Made Objects and Paleontological Discoveries. If Contractor is entitled to a Change Order under Section 2.6.3 for unknown, subsurface, man-made objects or unknown, subsurface object of paleontological interest, then: (a) should such condition cause a delay in the Critical Path, Contractor will be entitled to a Change Order that extends the applicable Guaranteed Dates as described in Section 9.4.2; and (b) to the extent that such conditions result in additional Direct Costs for Contractor to perform the Work, Contractor will be entitled to a Change Order that increases the Contract Price as described in Section 9.5.2.

Changes Involving Schedule Extensions.

    - Changed Work Scope. If the Parties agree to a Change Order as described in Section 9.2.2, then such Change Order will as part of such agreement include any agreed extensions to the Guaranteed Dates. If JEA issues a Change Directive pursuant to Section 9.5.1.1, then to the extent that Contractor demonstrates that the Changes of such Change Directive have delayed the Critical Path despite Contractor’s use of commercially reasonable efforts to mitigate and avoid any such delay, then Contractor will be entitled to a Change Order that extends the Guaranteed Dates by the number of Days of such delay as demonstrated by Contractor as being required solely as a result of the Change. To the extent that a Change constituting a deletion from the Scope of Work, or other modification to the quality, function or scope of the Work, will reduce the time it takes to perform the Work, then the Parties will cause a Change Order to be issued that brings forward the applicable Guaranteed Dates by the number of Days of Work saved or alleviated by such Change.

Changes Resulting from Change Events.  Subject to Section 9.2.1, to the extent that Contractor demonstrates that a Change has delayed the Critical Path despite Contractor’s use of commercially reasonable efforts to mitigate and avoid any such delay, then JEA will cause the Change Order resulting from the Change to extend the Guaranteed Dates by the number of Days of such delay as demonstrated by Contractor as being required solely as a result of the Change.

Schedule Analysis. In connection with any proposed Change Order as described in Sections 9.4.1 and 9.4.2, all adjustments to Guaranteed Dates shall be based upon an analysis, as will initially be presented by Contractor, of the reasonable impact of the applicable event to the Critical Path as it is stated in the most recently provided Monthly Updated Schedule, but subject always to Section 9.4.4; provided that such Monthly Updated Schedule is compliant with the requirements of Exhibit C.

Changes to the Contract Price.

Changes to Scope of Work.

Additional Work Scope.  With respect to any Change Order that JEA seeks to issue pursuant to Sections 9.2.2 that will foreseeably increase Contractor’s Direct Costs in performing the Work, promptly upon JEA’s issuance of the Change Order Notice therefor, the Parties will meet and in good faith negotiate to agree upon a lump sum amount by which the Contract Price will be increased in connection with performing such Change.  If and when such lump sum amount is agreed upon, then the ensuing Change Order will increase the Contract Price by such agreed-upon amounts.  If the Parties fail, despite their good faith negotiations, to agree upon such increased amounts within ten (10) Business Days after JEA’s issuance of the Change Order Notice or to the extent JEA deems expedient, then, JEA may issue a written directive (a “Change Directive”) requiring Contractor to proceed with such Change, and in this event JEA will instead, on a retrospective, monthly basis, reimburse Contractor for its demonstrable, additional Direct Costs incurred by Contractor solely as a result of such Change, plus a mark-up of ten percent (10%) (but such markup will not apply to Contractor’s Hourly Rates).  Contractor will invoice JEA for such Direct Costs (and markup) during any month as part of the ensuing Application for Payment as described in Section 5.4, and JEA will pay the same as described in Section 5.5.

Decreased Work Scope.  With respect to any Change Order that JEA seeks to issue pursuant to Section 9.2.2 that will decrease or otherwise modify the quality, function or scope of the Work so as to foreseeably decrease Contractor’s Direct Costs in performing the Work, promptly upon JEA’s issuance of the Change Order Notice therefor, the Parties will meet and in good faith negotiate to agree upon a lump sum amount by which the Contract Price will be decreased in order to recover the mutually-agreed estimate of the total Direct Costs that will be saved by Contractor in connection with such Change.  Once such lump sum amount is agreed upon, the Parties will enter a Change Order decreasing the Firm Price by an agreed-upon amount (such amount to include a reduction equal to ten percent (10%) of such Direct Costs (other than Direct Costs constituting Contractor’s Hourly Rates)) and adjusting the Milestone Payment Schedule.  If the Parties fail, despite their good faith negotiations, to agree upon such decreased amount within ten (10) Business Days after JEA’s issuance of the Change Order Notice, then, JEA may issue a written directive (a “Reductive Change Directive”) requiring Contractor to proceed with such Change, and JEA will determine, in good faith, the reasonable amount of the corresponding reduction to the Contract Price, which reduction shall be limited to the reasonably foreseeable avoided Direct Costs of the eliminated Work (plus ten percent (10%)), and such determination shall immediately apply for purposes of invoicing and payment, pending final resolution of what shall thereafter be considered a Dispute regarding such adjustment in accordance with Article 16. Contractor shall promptly comply with such Reductive Change Directive and shall not suspend, delay, or otherwise impact the performance of the Work as a result of any Dispute regarding the amount of such price adjustment.

Changes Resulting from Certain Events.

(a)	Subject to Section 9.2.1, with respect to any Change Order required to be issued to increase the Contract Price as a result of a Change (other than a Force Majeure event), such Change Order will, on a retrospective basis, increase the Contract Price by an amount equal to the additional Direct Costs demonstrably incurred by Contractor solely as a result of such Change, plus a mark-up of ten percent (10%) of such Direct Costs (but such markup will not apply to Contractor’s Hourly Rates).

(b)	For any period during which a Concurrent Delay exists, Contractor’s entitlement to a Change Order extending the applicable Guaranteed Dates will remain as set forth in Section 9.4, but Contractor shall not be entitled to recover any Direct Costs incurred by Contractor as a result of the extension, including extended field supervision (e.g., project management, site supervision, and field engineering personnel), extended equipment use or equipment on standby (including owned or rented machinery, cranes, and hoists), continued costs of operation and maintenance of Contractor systems and utilities at the Facility Site (such as field offices, utilities, sanitation, internet, and security), and additional premiums for insurance and bonds during the extended period.

Documentation. All claims for Direct Costs shall be supported by reasonable, contemporaneous written documentation sufficient to substantiate the nature, amount and purpose of such Direct Costs, including applicable time sheets, labor hour logs, equipment usage records, payroll records, invoices, receipts and other customary supporting documentation. JEA shall without limitation be entitled to rely on Contractor’s submitted documentation, including the resource loading set forth in the Baseline Project Schedule, as a basis for delineating between claimed Direct Costs and costs already included in the Contract Price.

Continued Performance Pending Resolution of Disputes.

Notwithstanding and pending resolution of any dispute with respect to a Change, Contractor will continue performing the Work.

JEA’s Right to Offset Changes.

Upon JEA’s written request, Contractor will determine and provide JEA with information as to whether a Change extending the applicable Guaranteed Dates can be offset by the expenditure of additional funds or a Change increasing the Firm Price can be offset by an extension of the applicable Guaranteed Dates.  Based upon such information, and if such information shows that such an offset may be made, JEA may, at its sole discretion and to the extent possible, elect to increase the Firm Price in lieu of the extension to the applicable Guaranteed Dates or extend the applicable Guaranteed Dates in lieu of an increase in the Firm Price, or any combination thereof, as the case may be.

Final Resolution.

Any Change Order executed by the Parties shall constitute the final and complete agreement between the Parties with respect to the Change, any and all related claims, and all events or circumstances giving rise thereto, including without limitation any associated disruption, cumulative impacts, or knock-on effects, and neither Party shall be entitled to assert any further entitlement arising therefrom.

Force Majeure

Force Majeure Event.

A “Force Majeure” event means any event occurring after the Effective Date that: (a) is beyond the reasonable control of the Party claiming the Force Majeure (the “Affected Party”) and its Personnel, (b) prevents, delays or affects the Affected Party’s performance under this Agreement, and (c) is not due to the fault, negligence, willful misconduct or fraud of the Affected Party or its Personnel.  Provided that the foregoing criteria are met, each of the following may, without limitation constitute a Force Majeure event: natural disasters, explosions or fire (excluding explosions and fires that are started as a result of a malfunction or failure of any of equipment supplied by Contractor or the negligence of Contractor or its Personnel), cyberattacks, hurricanes, typhoons, tornadoes, cyclones, landslides, lightning, high velocity wind exceeding crane use safety limits, abnormally and unusually severe weather conditions (except as provided below) affecting the Work, flood, earthquake, and other “acts of God,” epidemics and pandemics, governmental actions or inactions other than a Change of Law, terrorism, strikes or lockouts (except as provided below), insurrections, riots or civil strife, or war (whether or not declared).  In no event will any of the following constitute a Force Majeure event: (i) any strike or lockout or other labor-related disturbance involving only Contractor, its Affiliates, its Subcontractors, or their Personnel that involves direct employees of any of them or their Affiliates, except for strikes or lockouts that are national or regional in scope and not specifically targeted at Contractor or the applicable Subcontractor; (iii) typical weather or climatic conditions, including precipitation (including rain, lightening, ice, sleet, and snow), cold, or heat conditions (other than hurricanes and tornadoes) as would be expected for the geographic area of the site of Contractor’s Subcontractor’s manufacturing facilities or in the geographic area of the Facility Site, where in the case of rainfall or snowfall at the Facility Site, rain or snow during any time period(s) within a calendar month shall be considered “typical” if the total of such precipitation as measured by the National Oceanic and Atmospheric Association station closest to the Facility Site for a given calendar month is equal to or less than the average of the same type of precipitation for that same calendar month for the preceding twenty-five (25) years, according to the records of the same National Oceanic and Atmospheric Association station; (iv) inability or failure of a Party to make payment for any reason; (v) unavailability of labor, equipment, material or other resources, other than equipment, material or resources that are unavailable due to an event that affected Contractor or its Personnel and that, if it had happened to Contractor hereunder, would have constituted Force Majeure; (vi) economic hardship of any entity; (vii) normal time periods for clearing customs; (viii) machinery or equipment breakdown due to inadequate maintenance and not the result  of a separate event constituting a Force Majeure event, (ix) late delivery of materials, supplies or components provided by Contractor or its Subcontractors (except where such late delivery is the result of a Force Majeure event), and (x) price fluctuations with respect to labor or materials, supplies or components of equipment related to items to be supplied by Contractor under this Agreement, and (xi) events constituting a JEA Delay Event.

Burden of Proof.

The burden of proof as to whether a Force Majeure event has occurred shall be upon the Party claiming a Force Majeure event.

Excused Performance.

If the Affected Party is rendered wholly or partly unable to perform its obligations under this Agreement because of a Force Majeure event, such Affected Party will be excused from such non-performance to the extent caused by the Force Majeure event, provided that:

Without prejudice to Section 9.2.1, the Affected Party shall promptly, but not later than ten (10) Business Days after becoming aware of the occurrence of a Force Majeure event that has impacted (even if the exact extent of the impact is then unknown) the performance of its obligations under this Agreement, give the other Party written notice describing the particulars of the occurrence and providing an estimate of its expected duration and probable effect on the performance of the Affected Party’s obligations under this Agreement; provided, that if Contractor is the Affected Party and has provided the Preliminary Change Order Notice as required in Section 9.2.1(a) with respect to a Force Majeure event, then such notice shall satisfy this Section 10.3(a) as with respect to such Force Majeure event;

the suspension of performance resulting from such Force Majeure event shall be of no greater scope and of no longer duration than is reasonably required by the Force Majeure event;

no obligations of either Party which arose before the occurrence causing the suspension of performance are excused as a result of the occurrence, except to the extent directly affected by the Force Majeure event;

the Affected Party must continue to perform its obligations under this Agreement to the extent possible, and the Affected Party must use commercially reasonable efforts to overcome, mitigate and remedy the damages, delays and effects of the Force Majeure and its inability to perform its obligations under this Agreement as a result thereof;

the Affected Party keeps the other Party reasonably informed in writing of all efforts to mitigate and remedy the event of Force Majeure; and

when the Affected Party is able to resume performance of its obligations hereunder, that Party shall give the other Party written notice to that effect and shall promptly resume such performance.

Indemnification

Contractor’s Indemnity.

To the fullest extent permitted by law, Contractor will indemnify, defend and hold harmless JEA, its governing board, its Affiliates and its Affiliates’ respective shareholders, members, partners, managers, employees, representatives and agents, and their respective employees, representatives and agents (collectively, the “JEA Indemnitees”) from and against claims, suits, and actions (“Claims”), and all liability (including any strict liability), costs (including attorneys’ fees), expenses, losses, fines, citations, insurance claims, restoration costs, penalties, assessments, or judgments (collectively, “Losses”) that may be imposed on or incurred by a JEA Indemnitee or asserted against any JEA Indemnitee by a Third Party resulting from:

any bodily injury, death or damage to Third Party tangible property to the extent caused by any negligent, tortious or illegal act or omission (including strict liability) or willful misconduct of Contractor, Subcontractor, any Affiliate or their Personnel;

Contractor’s failure to pay any Contractor’s Taxes;

the Release of any Hazardous Materials on or from the Facility Site or any areas adjacent thereto to the extent that such Release results from the negligence (including strict liability), recklessness, or willful misconduct of Contractor or any of Contractor’s Personnel (it being acknowledged that, as with respect to the initial Release of any subsurface Pre-Existing Hazardous Materials, Contractor cannot be considered to have negligently Released the same if Contractor did not know of the location and extent of the same prior to the initial Release);

the violation by Contractor or any of Contractor’s Personnel of any, or the failure of the Work to comply with or be capable of operating in compliance with, Applicable Laws or Applicable Permits (provided, however, that such indemnification shall be limited to claims by a Governmental Authority for associated fines and penalties);

any claim or allegation that any equipment, materials or information provided by Contractor or any of Contractor’s Personnel in connection with its performance of the Work constitutes an infringement of any Intellectual Property rights of any third party or constitutes the unauthorized disclosure of a third party’s confidential information;

any liens, claims of lien or similar encumbrances arising in connection with the Work (other than as result from JEA’s failure to make undisputed payments when required in accordance with this Agreement); and

any Security Incident or Data Breach caused by Contractor or its Personnel;

any claims with respect to employer’s liability or worker’s compensation filed by any employee of Contractor, Subcontractor, any Affiliate or their Personnel; or any of its Personnel; and

- This indemnity shall survive the expiration or termination of this Agreement for Claims arising from events occurring during the Term. The indemnities set forth herein are separate from and in addition to any other rights or remedies available under this Agreement or applicable law.

JEA Indemnification.

To the fullest extent permitted by law, JEA will defend, indemnify and hold harmless Contractor and its Affiliates and its and its Affiliates’ respective shareholders, members, partners, managers, employees, representatives and agents (collectively, the “Contractor Indemnitees”) from and against all Claims and Losses that may be imposed on or incurred by a Contractor Indemnitee or asserted against any Contractor Indemnitee by a third party (including a Governmental Authority) resulting from:

any bodily injury, death or damage to third party tangible property, in each case, to the extent caused by any negligent, tortious or illegal act or omission of JEA any Affiliate or their Personnel;

JEA’s failure to pay any taxes for which JEA is responsible under this Agreement;

the Release of any Hazardous Materials on or from the Facility Site or any areas adjacent thereto to the extent that such Release results from the negligence (including strict liability) or willful misconduct of JEA, any of its Affiliates, or its Personnel;

any violation by JEA or its Personnel of Applicable Laws or Applicable Permits; provided, however, that such indemnification shall be limited to claims by a Governmental Authority for associated fines and penalties; and

any claims with respect to employer’s liability or worker’s compensation filed by any employee of JEA or any of its Personnel.

Environmental Indemnity.

Contractor will indemnify and hold harmless the JEA Indemnitees and will reimburse the JEA Indemnitees from and against any Claims, and all Losses, including without limitation costs of cleanup, containment, removal, remediation and investigation, arising from or in connection with: (a) Contractor Personnel’s actions or activities that result in a violation of any Environmental Law or that lead to an environmental Claim, citation, or damages arising from Contractor’s activities; (b) any environmental, health and safety liabilities arising out of or relating to the operation or other activities performed in connection with the Work by Contractor or any Contractor Personnel at any time on or after the Effective Date; (c) any bodily injury (including illness, disability and death, regardless of when such bodily injury occurred, was incurred or manifested), personal injury, property damage (including trespass, nuisance, wrongful eviction and deprivation of the use of real property), or other damage to any person arising from or allegedly arising from any hazardous activity conducted by Contractor or any Contractor Personnel; and (d) any Claims by a Governmental Authority relating to environmental conditions or Environmental Law compliance arising from Contractor’s performance of the Work. JEA shall be entitled to control any remedial action and any proceeding relating to an environmental Claim. This indemnity is separate from, and shall not be limited by, any insurance required under this Agreement or otherwise maintained by Contractor.

Indemnification in Design Professional Contracts.

In accordance with the requirements of Section 725.08, Florida Statutes, to the extent that this contract falls within the definition of a design professional contract, the provisions of the indemnification clause of that Section shall not apply to Contractor. Contractor shall indemnify, defend, and hold harmless the agency, and its officers and employees, from liabilities, damages, losses, and costs, including, but not limited to, reasonable attorneys’ fees, to the extent caused by the negligence, recklessness, or intentionally wrongful conduct of the design professional and other persons employed or utilized by the design professional in the performance of this Agreement.

Notice and Legal Defense.

Promptly after receipt by an JEA Indemnitee or Contractor Indemnitee (the “Indemnified Person”) of any claim or notice of the commencement of any action, administrative or legal proceeding, or investigation in connection with an actual or potential claim from a third party (including any Governmental Authority), as to which any indemnity provided for in Article 11 may apply, the Indemnified Person will notify the applicable Party who has the defense obligations with respect thereto in writing of such fact (the “Indemnifying Party”). Any delay in an Indemnified Person’s notifying of any such claim or notice will not excuse the Indemnifying Party’s obligations hereunder; provided that such Indemnifying Party is not prejudiced by such delay.  Subject to the last sentence of Section 11.4, upon the Indemnifying Party’s receipt of such notice, it shall assume on behalf of the Indemnified Person, and conduct with due diligence and in good faith, the defense thereof with counsel reasonably satisfactory to the Indemnified Person; provided, that the Indemnified Person shall have the right to be represented therein by advisory counsel of its own selection (and at its own expense); and provided, further, that if the defendants in any such action include both the Indemnifying Party and the Indemnified Person, and if the Indemnified Person shall have reasonably concluded that there may be legal defenses available to it which are additional to or inconsistent with those available to Indemnifying Party, then the Indemnified Person shall have the right to select separate counsel to participate in the defense of such action on its own behalf, and at its own expense.  In no event shall Contractor as the Indemnifying Person, without JEA’s prior written consent, settle any claim hereunder in a manner that results in any impact to the operations or maintenance of the Facility.  In no event shall an Indemnifying Party, without the prior written consent of the Indemnified Party, settle any claim hereunder in a manner that admits any wrongdoing or fault of the Indemnified Party or that does not result in an unconditional release of the Indemnified Party.

Failure to Defend Action.

If any Third-Party claim arises as to which any indemnity provided for in this Article 11 may apply, and the Indemnified Party has provided the Indemnifying Party with the required notice under Section 11.3, and Indemnifying Party fails to expressly confirm its assumption of the defense of such claim within seven (7) Days after its receipt of such notice (or should thereafter cease efforts to provide such defense), then the Indemnified Party against which the claim is instituted or commenced may, at the Indemnifying Party’s expense, contest or settle such claim; provided, that no such contest need be made, and settlement or full payment of any such claim may be made without the Indemnifying Party’s consent (with the Indemnifying Party remaining obligated to indemnify the Indemnified Party under this Article 11) if, in the written opinion of the Indemnified Party’s counsel, such claim is meritorious.  All costs and expenses incurred by the Indemnified Party in connection with any such contest, settlement or payment shall be reimbursed by the Indemnifying Party to the Indemnified Party promptly following, but not later than thirty (30) Days following, the Indemnified Party’s demand therefor.

Additional Intellectual Property Obligations.

Without limiting the foregoing, if JEA is enjoined from completing the Facility or any part thereof, or from the use, or operation of the Facility or any part thereof, as a result of any claim or allegation that any equipment, materials or information provided by Contractor or any of Contractor’s Personnel in connection with its performance of the Work constitutes an infringement of any patent, trade secret, trademark, copyright or other proprietary rights of any third party or constitutes the unauthorized disclosure of such third party’s confidential information, Contractor shall, in addition to its indemnification obligations hereunder, promptly, but in no event later than thirty (30) Days from the date of notice from JEA, commence action to remove such injunction, and thereafter promptly use its best efforts to remove such injunction, including by: (a) procuring for JEA, or reimbursing JEA for procuring, the right to continue using the infringing item, with substantially the same performance, quality and expected life; (b) replacing the infringing item with a non-infringing item of comparable functionality and quality (and having substantially the same performance, quality and expected life); or (c) modifying the infringing item such that it no longer infringes upon any third party’s intellectual property rights and is comparable in functionality and quality (and having substantially the same performance, quality and expected life).

No Waiver of Sovereign Immunity.

Notwithstanding anything to the contrary herein, JEA’s indemnification obligations shall be subject to, and within the limitations set forth in, Section 768.28, Florida Statutes. Nothing herein shall be construed as a waiver of sovereign immunity on the part of JEA.

Survival.

The provisions of this Article 11 will survive any expiration or termination of this Agreement for Claims arising from events occurring during the Term. The indemnities set forth herein are separate from and in addition to any other rights or remedies available under this Agreement or applicable law.

Termination and Suspension Rights

JEA Termination for Convenience.

JEA shall have the right, in its sole discretion, to terminate this Agreement in its entirety, for its sole convenience (without necessity of reason to Contractor), at any time by giving written notice thereof to Contractor.

Termination Payment.  If JEA terminates this Agreement under this Section 12.1, then, subject to the other provisions of this Section 12.1, and subject to Section 5.4.3, the “Termination Payment” will be calculated as follows:

(a)	as determined strictly in accordance with the Milestone Payment Schedule, all amounts as are earned and payable for all completed Milestones in accordance with this Agreement as of the effective date of such termination; plus

(b) 	Contractor’s Direct Cost for Work properly performed in accordance with this Agreement on uncompleted Milestones, plus a mark-up of ten percent (10%) of such Direct Costs (but such markup will not apply to Contractor’s Hourly Rates); plus

(c)	(i) any demonstrable termination or cancellation payments unavoidably payable by Contractor to First Tier Subcontractors, as a result of a termination of their Subcontracts or lease, plus (ii) Contractor’s demonstrable Direct Cost incurred as necessary to demobilize Contractor’s and its Subcontractors’ personnel and equipment from the Facility Site and to protect and bring the Work to an orderly cessation, in each case, as a result of such partial or full termination (as applicable) of this Agreement, minus

(d) 	the aggregate of all payments previously made by JEA to Contractor under this Agreement.

If the Termination Payment is a positive value, then JEA will be obligated to pay the same to Contractor as described below. If the Termination Payment is a negative value, Contractor will reimburse to JEA the absolute value of the same within fifteen (15) Days of the earlier of (i) such determination; or (ii) written notice. Payment of the Termination Payment (or non-payment as provided in the foregoing sentence) shall be the sole and exclusive liability of JEA, and the sole and exclusive remedy of Contractor, with respect to termination of this Agreement pursuant to this Section 12.1. Except as set forth in this Section 12.1.1, JEA will not be liable to Contractor, any Subcontractor or any other party for any damages or indirect costs resulting from such termination, including prospective profits on Work not performed or other consequential or incidental damages.  The Parties recognize, agree and acknowledge that JEA’s termination right hereunder is a permitted action under this Agreement (and not a breach hereof or a default hereunder), which right carries with it the obligation to make the Termination Payment.

Deductions from Termination Payment.  JEA shall not be required to pay all or any portion of the Termination Payment, or (because of subsequently discovered evidence or subsequent observations) may make a demand for repayment of any portion of the Termination Payment previously made to Contractor, to such extent as may be necessary in JEA’s opinion to protect JEA from loss due to:

estimated costs of remedying defective Work by Contractor or any of its Subcontractors;

damage to JEA or JEA’s property to the extent caused by the negligence of Contractor or any of Contractor’s Personnel for which Contractor has responsibility under Section 2.5.2, but only to the extent of Contractor’s liability pursuant to the terms of this Agreement; and

any Releases of Hazardous Materials at the Facility Site or adjacent areas as the result of the actions or omissions of Contractor or Contractor’s Personnel for which Contractor has responsibility under Section 2.2.20.

Condition Precedent.  The following shall be conditions precedent to JEA’s obligation to pay Contractor the Termination Payment: (a) Contractor’s executing and delivering all such documents and taking all such steps, including the assignment of Contractor’s contractual rights, as JEA may require for the purpose of fully vesting in JEA all rights, title and interests of Contractor in and to all Subcontracts, purchase orders, warranties, guarantees and other agreements pertaining to the Work; (b) Contractor’s executing and delivering (and causing its First-Tier Subcontractors to execute and deliver) to JEA all waivers and releases, in form and substance acceptable to JEA, required to establish that the Facility and the Facility Site, and any and all interests, estates or improvements related thereto, are free from any and all claims, liens, security interests or encumbrances arising out of or in connection with performance by Contractor or any Subcontractor of the Work; and (c) Contractor’s promptly delivering to JEA any other information that is reasonably required for JEA in connection with its ongoing ownership, protection, completion, operation or maintenance of the terminated Work.

Verification of the Termination Payment.  Contractor shall, within sixty (60) Days of any termination of this Agreement pursuant to Section 12.1, invoice JEA for the Termination Payment, such invoice to include documentation as is sufficient to enable JEA to verify the progress of the Work, and the amount described in clauses (b) and (c) of Section 12.1.1. JEA shall pay Contractor the Termination Payment within thirty (30) Days after the later of: (a) JEA’s receipt of the documentation required under this Section 12.1.4 and (b) the satisfaction of the conditions precedent set forth in Section 12.1.3.

JEA Termination Upon Contractor Event of Default.

If a Contractor Event of Default occurs, then JEA may, without prejudice to any other right or remedy JEA may have under this Agreement or at law or equity at any time terminate this Agreement, such termination becoming effective two (2) Business Days after Contractor’s receipt of written notice thereof from JEA.  For purposes hereof, a “Contractor Event of Default” will occur if:

(a)	Contractor has: (i) willfully abandoned the Facility Site, with no apparent indication of any good faith intention to return personnel to perform the Work at the Facility Site, and such reduction has a material impact on the schedule of completion of the Work; or (ii) for any reason that is not otherwise excused under this Agreement, suspended a material portion of its business operations in a manner that materially impairs its ability to perform the Work;

(b)	Contractor is adjudged bankrupt or insolvent, makes a general assignment for the benefit of its creditors, has a trustee or receiver appointed for its property, files a petition to take advantage of any debtor’s act under any Applicable Laws or is the involuntary subject of any petition or action under any debtor’s act under any Applicable Laws and such action or proceeding is not dismissed within sixty (60) Days;

(c)	(i) Contractor fails to submit to JEA a Recovery Plan as and when required under Section 2.3.2, or (ii) having provided the same, Contractor has materially failed to use commercially reasonable efforts to adhere to such Recovery Plan’s requirements and consequently will be unable to achieve Mechanical Completion by more than ninety (90) Days past the Guaranteed Mechanical Completion Date or will be unable to achieve Substantial Completion by more than ninety (90) Days past the Guaranteed Substantial Completion Date;

(d)	without limiting Contractor’s liability for Late Mechanical Completion Liquidated Damages, the date of Mechanical Completion has not occurred within one hundred eighty (180) Days after the Guaranteed Mechanical Completion Date;

(e)	without limiting Contractor’s liability for Late Substantial Completion Liquidated Damages, the Substantial Completion Date has not occurred within one hundred and eighty (180) Days after the Guaranteed Substantial Completion Date;

(f)	Contractor assigns or attempts to assign its rights or obligations under this Agreement or any part thereof to any third party without the prior written consent of JEA;

(g)	pursuant to Section 287.135(3)(b), Florida Statutes, Contractor is found to have been placed on the Scrutinized Companies List or Scrutinized Companies that Boycott Israel List or is engaged in a boycott of Israel;

(h)	Contractor willfully and persistently disregards or violates Applicable Legal Requirements or Applicable Permits resulting in an adverse impact on the Work or the reputation of JEA;

(i) 	JEA is prevented from using the Work or the Facility as a consequence of Contractor or its Subcontractor’s infringement of an intellectual property right;

(j)	Contractor intentionally misrepresents the utilization of funds or misappropriates property belonging to JEA, and Contractor has not corrected such misrepresentation or misappropriation within fifteen (15) Days after notice from JEA;

(k)	Contractor reaches the aggregate cap on liquidated damages in Section 15.1. and does not agree to increase such cap; or

(l)	Contractor fails or refuses to perform any other material obligation under the Agreement not already described above and either: (a) does not commence to cure such failure to JEA’s reasonable satisfaction within ten (10) Days after receipt of notice of the same from JEA, or (b) does not cure such failure within thirty (30) Days after receipt of notice of the same from JEA; provided, that if despite having promptly commenced and diligently and expeditiously pursued the cure, the cure is not capable of being effectuated within such thirty (30) Day period, then Contractor may (prior to the end of such thirty (30) Day period) present to JEA a written cure plan that demonstrates how Contractor intends to cure the failure thereafter, and the additional time required to do so, and, based upon such plan, JEA will not unreasonably withhold its consent to allow an additional period of time as Contractor demonstrates is necessary for Contractor to complete the cure.

Actions Upon Termination.

Upon receipt of written notice from JEA of termination of this Agreement pursuant to either Section 12.1 or Section 12.2, Contractor will: (a) cease operations as directed by JEA in the notice; (b) take all actions necessary, or that JEA may direct, for the protection and preservation of the Facility and all equipment related thereto (in whatever stage of completion); (c) enter into no further subcontracts and purchase orders; (d) at JEA’s instruction, assign its rights under all Subcontracts to JEA or JEA’s designee, (e) deliver to JEA any other documentation relating to the Work as may be reasonably requested by JEA in writing within a reasonable time after Contractor’s receipt of such request, (f) cooperate with transition of any JEA-owner materials and other items to JEA or its replacement contractor, and (g) comply with Contractor’s data obligations pursuant to Section 2.2.17.6 (e).

Consequences of Termination for Contractor Default.

Upon any termination pursuant to Section 12.2, in addition to any other rights or remedies that JEA may have under law or equity, JEA may at its option elect to: (a) assume responsibility for and take title to and possession of the Facility and any or all Work, materials or equipment (other than Contractor’s construction equipment) remaining at the Facility Site and any and all other materials or equipment located outside the Facility Site for which payment in full or in part has been made by JEA; and (b) succeed automatically, without the necessity of any further action by Contractor or prior consent of the relevant Subcontractor, to the interests of Contractor in any or all contracts and Subcontracts entered into by Contractor with respect to the Work, and shall be required to compensate such Subcontractors only for compensation becoming due and payable to such parties under the terms of their Subcontracts with Contractor for work performed from and after the date JEA elects to succeed to the interests of Contractor in such Subcontracts, and (c) finish the Work by whatever method JEA may reasonably deem expedient and, to the extent the costs of completing the Work exceed the Contract Price, Contractor shall (subject to Section 15.2) pay the difference to JEA promptly upon demand.

Suspension of Work upon Non-Payment by JEA.

If JEA fails to pay to Contractor any undisputed payment as required hereunder and such failure continues for thirty (30) Days after written notice of such delinquency has been given to JEA by Contractor, then Contractor may upon five (5) Business Days’ prior written notice suspend the Work until payment of the amount owing has been received; provided, however, that nothing contained herein shall modify or abridge JEA’s right to withhold payments from Contractor pursuant to the terms of Section 5.4 of this Agreement. When payment of the amount owing has been received, Contractor shall recommence the Work, provided that the Parties will thereafter work diligently to execute a Change Order pursuant to Section 9.3.2.

JEA Default.

The occurrence of any of the following events shall constitute an “JEA Event of Default” under this Agreement:

- (a)	JEA fails to make payment of any undisputed amount when due under any invoice duly submitted by Contractor to JEA in accordance with the Agreement and such failure continues beyond the date that is thirty (30) Days after JEA’s receipt of such notice of such delinquent payment; or

- (b)	JEA is adjudged bankrupt or insolvent, makes a general assignment for the benefit of its creditors, has a trustee or receiver appointed for its property, files a petition to take advantage of any debtor’s act under any Applicable Laws or is the involuntary subject of any petition or action under any debtor’s act under any Applicable Laws and such action or proceeding is not dismissed within sixty (60) Days; or

- (c)	JEA fails or refuses to perform any other material obligation under the Agreement not already described above and either: (i) does not commence to cure such failure to Contractor’s reasonable satisfaction within ten (10) Days after receipt of notice of the same from Contractor, or (b) does not cure such failure within thirty (30) Days after receipt of notice of the same from Contractor; provided, that if despite having promptly commenced and diligently and expeditiously pursued the cure, the cure is not capable of being effectuated within such thirty (30) Day period, then JEA may (prior to the end of such thirty (30) Day period) present to Contractor a written cure plan that demonstrates how JEA intends to cure the failure thereafter, and the additional time required to do so, and, based upon such plan, Contractor will not unreasonably withhold its consent to allow an additional period of time as JEA demonstrates is necessary for JEA to complete the cure.

Consequences of Termination for JEA Default.

If a JEA Event of Default occurs, then Contractor may, without prejudice to any other right or remedy Contractor may have under this Agreement, terminate this Agreement, such termination becoming effective two (2) Business Days after JEA’s receipt of written notice thereof from Contractor.  Such a termination will be treated as if JEA had terminated this Agreement under Section 12.1, and the Termination Payment thereunder will be payable as Contractor’s sole and exclusive remedy and JEA’s sole and exclusive liability

Surviving Obligations.

Termination of this Agreement: (a) shall not relieve either Party of any obligation hereunder or waive any rights hereunder which expressly or by implication survives termination hereof, including without limitation Sections 2.2.8, 3.5, 18.1, 18.5, 18.6, 18.7, 18.9, 18.9, 18.10, 18.12, and 18.13, and Articles 8, 11, 12, 15, 16 and 17, and (b) except as otherwise provided in any provision of this Agreement expressly limiting the liability of either Party, shall not relieve either Party of any obligations or liabilities for loss or damage to the other Party arising out of or caused by acts or omissions of such Party prior to the effectiveness of such termination or arising out of such termination, and shall not relieve Contractor of its obligations as to portions of the Work already performed or of obligations assumed by Contractor prior to the date of termination.

Securities

Payment Bond.

By no later than ten (10) Days after the Effective Date, Contractor shall furnish a “Payment Bond” in the form set forth in Exhibit Q-1, in an amount equal to one hundred percent (100%) of the Contract Price, as security for the payment of subcontractors.  Per Florida FL Statute 255.05., if a Payment Bond in one hundred percent (100%) of the Contract Price if not reasonably available, JEA may, in its sole discretion, accept a Payment Bond in an amount less than the Contract Price, but not less than $250,000,000. The Payment Bond shall be issued by a surety that is a Qualified Issuer, duly licensed or authorized in the State of Florida to issue bonds for the limits so required, and that is listed in the current issue of the Federal Register Department of the Treasury list. The surety shall not expose itself to any loss on any one risk in an amount exceeding ten (10) percent of its surplus to policyholders, provided: Any risk or portion of any risk being reinsured shall be deducted in determining the limitation of the risk as prescribed in this section. These minimum requirements shall apply to the reinsuring carrier providing authorization or approval by the State of Florida, Department of Insurance, to conduct business in this state has been met. In the case of surety, in addition to the deduction for reinsurance, the amount assumed by any co-surety, the value of any security deposited, pledged or held subject to the consent of the surety and for the protection of the surety shall be deducted. Contractor shall notify its surety of any changes affecting the general scope of the Work or altering the Contract Price. The amount of the Payment Bond shall be adjusted accordingly, and Contractor shall furnish proof of such adjustment to JEA within ten (10) days of date of any Change Order adjusting the Contract Price. If the surety on the Payment Bond furnished by Contractor is declared bankrupt or becomes insolvent or it no longer meets the requirements of this Section 13.1, Contractor shall within seven (7) Days thereafter substitute another Payment Bond and surety, which must be acceptable to JEA and meet the requirements of this Section 13.1. The fully executed Payment Bond must be recorded with the Clerk of Duval County Court and delivered to JEA before JEA will issue FNTP. JEA will not issue FNTP until the Payment Bond is recorded with the Clerk of Duval County Court and subsequently delivered to the JEA Procurement Department. If Contractor fails or refuses to furnish or record the required Payment Bond in accordance with this Section, JEA will retain the Contractor’s Bid Bond as liquidated damages.

Performance Bond.

By no later than ten (10) Days after the Effective Date, Contractor shall furnish a “Performance Bond” in the form set forth in Exhibit Q-2, in an amount equal to one hundred percent (100%) of the Contract Price, as security for the faithful performance of all Contractor’s obligations under this Agreement. Per Florida FL Statute 255.05., if a Performance Bond in one hundred percent (100%) of the Contract Price if not reasonably available, JEA may, in its sole discretion, accept a Performance Bond in an amount less than the Contract Price (but not less than $250,000,000). The Performance Bond shall be issued by a surety that is a Qualified Issuer, duly licensed or authorized in the State of Florida to issue bonds for the limits so required, and that is listed in the current issue of the Federal Register Department of the Treasury list. The surety shall not expose itself to any loss on any one risk in an amount exceeding ten (10) percent of its surplus to policyholders, provided: Any risk or portion of any risk being reinsured shall be deducted in determining the limitation of the risk as prescribed in this section. These minimum requirements shall apply to the reinsuring carrier providing authorization or approval by the State of Florida, Department of Insurance, to conduct business in this state has been met. In the case of surety, in addition to the deduction for reinsurance, the amount assumed by any co-surety, the value of any security deposited, pledged or held subject to the consent of the surety and for the protection of the surety shall be deducted. Contractor shall notify its surety of any changes affecting the general scope of the Work or altering the Contract Price. The amount of the Performance Bond shall be adjusted accordingly, and Contractor shall furnish proof of such adjustment to JEA within ten (10) days of date of any Change Order adjusting the Contract Price. If the surety on the Performance Bond furnished by Contractor is declared bankrupt or becomes insolvent or it no longer meets the requirements of this Section 13.2, Contractor shall within seven (7) Days thereafter substitute another Performance Bond and surety, which must be acceptable to JEA and meet the requirements of this Section 13.2. The fully executed Performance Bond must be recorded with the Clerk of Duval County Court and delivered to JEA before JEA will issue FNTP. JEA will not issue FNTP until the Performance Bond is recorded with the Clerk of Duval County Court and subsequently delivered to the JEA Procurement Department. If Contractor fails or refuses to furnish or record the required Performance Bond in accordance with this Section, JEA will retain the Contractor’s Bid Bond as liquidated damages.

Representations and Warranties

Representations and Warranties of Contractor.

Contractor hereby represents and warrants to JEA as of the Effective Date as follows:

Due Organization of Contractor.  Contractor is a [entity type] duly organized, validly existing and in good standing under the laws of [insert Contractor’s jurisdiction of organization] and has all requisite power and authority to own and operate its business and properties and to carry on its business as such business is now being conducted and is duly qualified to do business in [insert Contractor’s jurisdiction of organization], the State of Florida, and in any other jurisdiction in which the transaction of its business makes such qualification necessary.

Due Authorization of Contractor; Binding Obligation.  Contractor has full power and authority to execute and deliver this Agreement and to perform its obligations hereunder, and the execution, delivery and performance of this Agreement by Contractor have been duly authorized by all necessary corporate action on the part of Contractor; this Agreement has been duly executed and delivered by Contractor and is the valid and binding obligation of Contractor enforceable in accordance with its terms.

Non-Contravention.  The execution, delivery and performance of this Agreement by Contractor and the consummation of the transactions contemplated hereby do not and will not contravene the certificate of incorporation or by-laws of Contractor and do not and will not conflict with or result in a breach of or default under any indenture, mortgage, lease, agreement, instrument, judgment, decree, order or ruling to which Contractor is a party or by which it or any of its properties is bound or affected.

Regulatory Approvals.  All governmental or other authorizations, approvals, orders or consents required in connection with the execution, delivery and performance of this Agreement by Contractor have been obtained or will be obtained in due course.

Representation and Warranties of JEA.

JEA hereby represents and warrants to Contractor as of the Effective Date as follows:

Due Organization of JEA.  JEA is a body politic and corporate, which is authorized to own, manage and operate for the benefit of the City of Jacksonville, a utilities system within and without the City of Jacksonville.

Due Authorization of JEA; Binding Obligation.  JEA has full power and authority to execute and deliver this Agreement and to perform its obligations hereunder and the execution, delivery and performance of this Agreement by JEA have been duly authorized by all necessary corporate actions on the part of JEA; this Agreement has been duly executed and delivered by JEA and is the valid and binding obligation of JEA enforceable in accordance with its terms.

Non-Contravention.  The execution, delivery and performance of this Agreement by JEA and the consummation of the transactions contemplated hereby do not and will not contravene the articles of incorporation of JEA and do not and will not conflict with or result in a breach of or default under any indenture, mortgage, lease, agreement, instrument, judgment, decree, order or ruling to which JEA is a party or by which it or any of its properties is bound or affected.

Limitations of Liability

Aggregate Cap on Liquidated Damages.

Notwithstanding anything to the contrary in this Agreement, Contractor’s aggregate liability to JEA for all liquidated damages under this Agreement shall not exceed an amount equal to twenty-five (25%) of the Contract Price.

Aggregate Limitation.

Notwithstanding any provision to the contrary in this Agreement, to the fullest extent permitted by law, and except for liability arising out of the gross negligence, fraud or willful misconduct of Contractor or Contractor’s Personnel, the total cumulative liability of Contractor and Contractor’s Personnel to JEA for all claims, losses, damages, and expenses, whether based in contract, tort (including negligence), strict liability, or otherwise, shall be limited to an amount equal to one hundred percent (100%) of the Contract Price (as the same may be adjusted by Change Order). Notwithstanding anything to the contrary herein, the foregoing limitation is not intended to limit Contractor’s liability to JEA or JEA Indemnitees arising out of any claims for which Contractor has an indemnification obligation under Article 11, or Contractor’s liability for claims losses, damages, and expenses arising out of Contractor’s breach of Article 17, or Contractor’s obligation to achieve the Make Good Guarantees, and the amount of any such liability arising from such claims or obligations shall not be counted towards such limit of liability.

Consequential Damages.

Notwithstanding anything to the contrary in this Agreement, and except for liability arising out of the gross negligence, fraud or willful misconduct of a Party or its Personnel, and except for any liability arising in connection with a Party’s breach of its obligations under Article 17, in no event shall either Party be liable to the other Party, in connection with or arising out of such Party’s rights or obligations under this Agreement, for any special, incidental, indirect, exemplary, punitive, or consequential damages of any nature including, without limitation, lost income or profits, loss of use, loss of opportunity, loss of goodwill, cost of substitute facilities, goods or services, increased capital costs, fuel cost and cost of purchased or replacement power or claims of any customers of JEA and regardless of whether such losses, damages or liability arises from breach of contract or warranty, tort (including negligence), strict liability or otherwise.  The foregoing limitation is not intended to limit either Party’s liability to the other arising out of any claims of any Third Party for which a Party has an indemnification obligation Article 11.  In addition, the Parties agree that any liquidated damages payable by Contractor as required under this Agreement shall not be considered “special, incidental, indirect or consequential” damages under this Section 15.3.

Dispute Resolution

Applicability of Resolution Procedures.

Except for matters requiring immediate injunctive relief, all claims, disputes or other matters in question between the Parties arising out of or relating in any way to this Agreement (“Dispute”) will be resolved pursuant to this Article 16.

Management Discussions.

If a Dispute arises, the JEA Project Manager and the Contractor Project Manager will make a diligent, good-faith attempt to resolve such Dispute.  If the JEA Project Manager and the Contractor Project Manager are unable to resolve a Dispute arising under this Agreement within thirty (30) Days after notice from one Party to the other, such Dispute will be submitted promptly to the senior executive officers of the Parties, who will promptly meet in person or by telephone.  In the event that these officers do not resolve the Dispute within thirty (30) Days after the matter is submitted to them, then either Party may proceed to initiate the litigation in the courts described in Section 16.3 with respect to such Dispute.

Choice of Forum.

Subject to Section 16.4,  any legal action or proceeding with respect to this Agreement (e.g., enforcement of agreement to arbitrate, enforcement of arbitral award, seeking of injunctive relief) shall be brought in the State or Federal Courts located exclusively in Jacksonville, Duval County, Florida. Each of the Parties hereby accepts and consents to, generally and unconditionally, the jurisdiction of the aforesaid court (and appellate courts with jurisdiction to hear appeals therefrom).  Each of the Parties hereby irrevocably waives any objection which it may now or hereafter have to the laying of venue of any of the aforesaid actions or proceedings arising out of or in connection with this Agreement brought in the courts referred to above and hereby further irrevocably waives and agrees not to plead or claim in any such court that any such action or proceeding brought in any such court has been brought in an inconvenient forum.

Obligations Continue.

Notwithstanding the existence of any Dispute hereunder, the Parties will continue to perform their respective obligations under this Agreement unless the Parties otherwise mutually agree in writing.  During the pendency of a Dispute, if the Work is in progress, the JEA Project Manager will give such written instructions as, in his or her opinion, are necessary for the proper performance of the Work and to prevent delays thereto, pending settlement of the Dispute.  Contractor will carry out such instructions and will proceed with the execution of the Work, it being understood that Contractor’s performance shall be without prejudice and shall not waive any entitlement to time or cost adjustment under Article 9, whether or not Contractor gives JEA a written notice before carrying out such Work that Contractor is doing so under protest.

Injunctive or Equitable Relief.

Notwithstanding anything in this Agreement to the contrary, nothing in this Agreement is intended to, nor shall it, prevent the Parties from seeking injunctive or equitable relief at any time as may be available under law or in equity.

Survival.

The provisions of this Article 16 will survive the termination of this Agreement.

Non-Disclosure and Non-Use Covenants

Confidential Information.

For purposes of this Article 17, “Confidential Information” means and includes (a) all information (whether oral, written, electronic or otherwise) that is provided by or on behalf of a Party (the “Disclosing Party”) or its Affiliates to the other Party (the “Receiving Party”), before or after the Effective Date, that is designated in writing as “confidential” or “proprietary” by the Disclosing Party at the time of written disclosure or that was deemed to be “Confidential Information” under the [Non-Disclosure Agreement between JEA, Contractor and PIE Supplier, dated [●], 2026], and (b) all information about the Facility, its development and financing, or about the Disclosing Party and its business, that is developed or ascertained by the Receiving Party during the performance of the Work or in connection with this Agreement, (c) any information that is orally designated as “confidential” or “proprietary” by the Disclosing Party at the time of oral disclosure and is confirmed to be “confidential” or “proprietary” in writing within ten (10) Days after oral disclosure, (d) in the context of the Contractor as the Receiving Party, all information about the Project or JEA that is disclosed to or ascertained to Contractor during the performance of the Work or in connection with this Agreement, and (e) this Agreement and all draft copies hereof. Notwithstanding the foregoing, the Parties acknowledge that JEA is a local government agency that is subject to the requirements of Florida’s Public Records Law (Chapter 119, Florida Statutes) and that nothing in this Section shall prevent JEA from disclosing public records in compliance with the requirements of the Public Records Law. It is acknowledged and agreed that portions of this Agreement contain Confidential Information that is protected from compelled disclosure under Florida law. Following execution of this Agreement by both Parties, Contractor shall provide JEA a redacted copy of this Agreement that JEA may provide in the event of a public records request in accordance with the provisions of Section 17.3.

Restrictions.

Extent and Duration of Restrictions. Each Receiving Party acknowledges that the improper use or disclosure of any Confidential Information may cause irreparable harm to the Disclosing Party. Except as otherwise expressly permitted by this Article 17 or as approved in writing in advance by the Disclosing Party, each Receiving Party hereby covenants and agrees to keep all Confidential Information strictly confidential and not disclose, communicate, publish, transfer, copy or otherwise use any Confidential Information throughout the Term and for a period of five (5) years following the expiration of the Term.

Certain Exceptions.  The restrictions set forth in the foregoing Section 17.2.1 shall not apply to: (a) information which is in the public domain through no action on the part of the Receiving Party; or (b) information which the Receiving Party can demonstrate was in its possession at the time of disclosure; (c) information which is hereafter received by the Receiving Party from a Third Party who the Receiving Party reasonably and in good faith believes is not subject to any confidentiality or non-disclosure obligations to the Disclosing Party or others, and which, in each of the foregoing cases, was not acquired by the Receiving Party directly or indirectly from a Third Party that the Receiving Party knew, or through reasonable diligence should have known, was bound to keep such information confidential; or (d) information which is required to be disclosed in accordance with Applicable Legal Requirements in accordance with Section 17.2.4.

Restrictions on Use.  Each Receiving Party covenants and agrees that, without the prior written consent of the Disclosing Party in each instance, the Receiving Party will use the Confidential Information solely for the purpose of performing under this Agreement, and not for any other purpose. Each Receiving Party may make limited and controlled disclosures of the Confidential Information to its Affiliates and each of their respective directors, officers, employees, consultants, advisors, attorneys, vendors, suppliers, subcontractors, and insurance brokers (collectively, “Representatives”) who need to know the Confidential Information for the purpose of assisting the Receiving Party in its performance of its obligations or resolution of disputes under this Agreement (and/or, in JEA’s case, in connection with the development of or insurance for the Project); provided, however, that the Receiving Party may not disclose, communicate, publish, transfer, copy or otherwise provide use of any Confidential Information to any Representatives unless the Receiving Party: (a) informs such Representatives, in advance, of the confidential nature of the Confidential Information and the restrictions contained in this Agreement; and (b) such Representative are bound to a written confidentiality agreement consistent with this Article 17 that protects such Confidential Information; provided, that such written agreement will not be required of outside attorneys nor of directors, officers or other employee individuals of the Receiving Party. In any event, the Receiving Party shall remain responsible and liable for the actions, omissions, uses and disclosures of all of its Representatives.

Judicial Disclosure Exception.  Notwithstanding the foregoing provisions of this Section 17.2, each Party acknowledges that the Receiving Party may be legally compelled to disclose Confidential Information (or portions thereof): (a) pursuant to a valid subpoena or other court process; or (b) at the express direction of any properly authorized Government Authority. If the Receiving Party becomes legally compelled to disclose any Confidential Information, it will provide the Disclosing Party with immediate written notice thereof so that the Disclosing Party may seek a protective order or other appropriate remedy. Subject to Section 17.3, the Receiving Party will also furnish only that portion of the Confidential Information which it is legally compelled to disclose and will cooperate with the Disclosing Party and its counsel in the Disclosing Party’s efforts to obtain a protective order or other reliable assurance that confidential treatment will be accorded to any such Confidential Information.

Return of Items.  The Receiving Party shall promptly return to the Disclosing Party or destroy and delete (with a certification of such destruction and deletion), all items containing or constituting Confidential Information, together with all copies, extracts or summaries thereof, upon the earlier to occur of: (a) any request by the Disclosing Party; or (b) the termination of this Agreement; provided however, that nothing in this Section 17.2.5 shall require either Party or any of their respective Affiliates to return, destroy, or delete copies of any computer records and/or files containing the Confidential Information that have been created pursuant to automated processes such as document retention/archiving and/or back up policies/procedures, provided that each and any such copies: (i) are kept confidential in accordance with this Agreement and cannot be accessed in the regular course of business; (ii) are maintained and archived in compliance with reasonable information security standards; and (iii) are properly deleted as required by the Receiving Party’s document retention/archiving and/or back up policies/procedures.

Public Announcements.  Subject to Section 17.2.4, Contractor will not make or issue any public announcement, press release or statement with respect to this Agreement, the Work or the Facility unless such public announcement, press release or statement is approved in advance by JEA or is issued jointly by the Parties. Contractor shall not publish any drawing, photograph, video, or film or directly or indirectly disclose any information relating to the Parties’ performance obligations or the Project to the press, radio, television, or other news or social media without the prior written consent of JEA.

Public Records.

Access to Public Records. Notwithstanding anything in this Article 17 to the contrary, Contractor acknowledges that all documents, data and other records received by JEA in connection with the Agreement are public records and available for public inspection unless specifically exempt by law. Contractor shall allow public access to all documents, data and other records made or received by Contractor in connection with the Agreement unless the records contain business confidential information or are subject to another type of exemption from production under Section 24(a) of Article I of the Florida Constitution or Chapter 119, Florida Statutes (“Florida’s Public Records Law”).

Redacted Confidential Information.

Redacted Copies of Confidential Information. If Contractor believes that any portion of any documents, data or other records submitted to JEA contain business confidential information or are subject to another type of exemption from disclosure under Florida’s Public Records Law, Contractor must (1) clearly segregate and mark the specific sections of the document, data and records as “Confidential”, (2) cite the specific Florida Statute or other legal authority for the asserted exemption, and (3) provide JEA with a separate redacted copy of the documents, data, or records (the “Redacted Copy”). The Redacted Copy shall contain JEA’s contract name and number, and shall be clearly titled “Redacted Copy”. Contractor should only redact those portions of records that Contractor claims are specifically exempt from disclosure under Florida’s Public Records Laws. If Contractor fails to submit a redacted copy of documents, data, or other records it claims is confidential, JEA is authorized to produce all documents, data, and other records submitted to JEA in answer to a public records request for these records.

Request for Redacted Information. In the event of a public records or other disclosure request under Florida’s Public Records Law or other authority to which Contractor’s documents, data or records are responsive, JEA will provide the Redacted Copy to the requestor of such information (the “Requestor”). If a Requestor asserts a right to any redacted information, JEA will notify Contractor that such an assertion has been made. If JEA becomes subject to a demand for discovery or disclosure of the redacted information under legal process, JEA shall give Contractor prompt notice of such demand for discovery or disclosure of the redacted information in advance of such disclosure, (unless otherwise prohibited by applicable law) and reasonably cooperate in attempts to maintain the confidentiality of the redacted information so that Contractor may seek an appropriate protective order. Contractor shall notify JEA whether it intends to seek a protective order within ten (10) Business Days after its receipt of notice of a demand for discovery or disclosure. If Contractor fails to notify JEA of its intent to seek a protective order within ten (10) Business Days, JEA may presume that Contractor does not object to the disclosure of the redacted information. Contractor shall be responsible for defending its determination that the redacted portions of the information are not subject to disclosure. Contractor shall protect, defend, and indemnify JEA from and against all Claims, demands, actions, suits, damages, liabilities, losses, settlements, judgments, costs, and expenses (including but not limited to reasonable attorneys’ fees and costs) arising from or relating to Contractor’s assertion that all or any portion of its information is not subject to disclosure. If litigation is filed in relation to such request and Contractor is not initially named as a party, Contractor may promptly seek to intervene as a defendant in such litigation.

Public Records Clause for Service Contracts. If, under the Agreement, Contractor is providing Services acting on behalf of JEA in providing such Services in accordance with subsection 119.011(2), Florida Statutes, Contractor shall:

Keep and maintain public records that ordinarily and necessarily would be required by JEA in order to perform service;

Provide the public with access to public records on the same terms and conditions that JEA would provide the records and at a cost that does not exceed the cost provided in Chapter 119, Florida Statutes, or otherwise prohibited by law;

Ensure that public records that are exempt or confidential and exempt from public records disclosure requirements are not disclosed except as authorized by law; and

Meet all requirements for retaining public records and transfer, at no cost, to JEA all public records in possession of Contractor upon termination of the agreement and destroy any duplicate public records that are exempt or confidential and exempt from public records disclosure requirements. All records stored electronically shall be provided to JEA in a format that is compatible with the information technology systems of JEA.

- IF CONTRACTOR HAS QUESTIONS REGARDING THE APPLICATION OF CHAPTER 119, FLORIDA STATUTES, TO THE CONTRACTOR’S DUTY TO PROVIDE PUBLIC RECORDS RELATING TO THIS AGREEMENT, CONTACT THE CUSTODIAN OF PUBLIC RECORDS AT:

- JEA

- Attn: Public Records

- 225 North Pearl Street

- Jacksonville, Florida 32202

- Ph: 904-665-8606

- publicrecords@jea.com

Remedies and Interpretation.

Equitable Remedies.  Each Receiving Party hereby acknowledges that any violation of this Article 17 will cause the Disclosing Party immediate and irreparable harm that monetary damages cannot adequately remedy, and agrees that, upon any actual, impending, or threatened breach or violation of any provision of this Agreement, the Disclosing Party shall be entitled to seek and receive equitable relief, including injunctive relief and specific performance (without bond or proof of damages), and the Receiving Party shall not plead in defense thereto that there would be an adequate remedy at law. Any such equitable relief shall be in addition to, and not in lieu of, any other remedies that the Disclosing Party may have at law, in equity or otherwise under this Agreement.

Severability. All of the provisions of this Article 17 are severable, and the unenforceability or invalidity of any one provision of this Article 17 shall not affect the enforceability or validity of any remaining provisions of this Article 17, which shall be interpreted and construed to carry out fully the intention of the Parties. The Parties hereby authorize and instruct any judicial body interpreting this Article 17 to rewrite any provision of this Article 17 which such body determines is unenforceable as written in such a fashion so that the provision may be enforced to the greatest extent legally possible. Each Party acknowledges and agrees that the covenants and agreements contained in this Article 17 shall be construed as covenants and agreements independent of each other or any other contract or agreement between the Parties, and that the existence of any claim or cause of action by one Party against the other Party, whether predicated upon this Agreement or any other contract or agreement between the Parties, shall not constitute a defense to the enforcement of the covenants and agreements contained in this Article 17.

Miscellaneous

Governing Documents.

The following documents and provisions, listed in descending order of priority, and any amendments thereto, comprise the “Contract Documents”:

(a)	Change Orders and amendments entered into pursuant to Section 18.11,

(b)	Construction Documents

(c)	Design Development Documents

(d)	the Terms and Conditions;

(e)	Exhibit A-1;

(f)	Exhibit A-2;

(g)	Exhibit [●] [Exhibits to be listed in priority order once finalized]

In the event of a conflict or inconsistency among the various items listed above, such conflict or inconsistency shall be resolved by reference to that item having the higher priority as determined by the order in which the item is listed above.  Subject to the foregoing, if any provisions within any given listed item are in conflict with any other provisions in the same, the provision setting forth the higher standard of conduct for or more onerous obligations upon Contractor will prevail.

Project Managers.

In order to secure effective cooperation and to deal on a prompt and orderly basis with the various scheduling and administrative issues which may arise in connection with the rights and obligations of the Parties hereunder, each Party hereby appoints the following people as their respective “Project Managers”:

JEA Project Manager: [●]

Contractor Project Manager: [●]

Either Party may, at any time, change the designation of its Project Manager, provided such Party shall promptly notify the other Party in writing of such change.  Each Party’s Project Manager shall be authorized to administer, but not modify or amend, this Agreement on behalf of such Party and agree upon procedures and provide such information as is necessary for coordinating the efforts of the Parties.

Assignment/Delegation.

Assignment/Delegation by Contractor.  It is expressly understood and agreed that this Agreement is personal to JEA, and that Contractor will have no right, power or authority to assign or delegate its rights or obligations under this Agreement or any portion thereof, either voluntarily or involuntarily, or by operation of law.

Assignment/Delegation by JEA.  JEA may assign any or all of its rights and/or delegate any or all of its obligations under this Agreement to any third party; provided, that JEA must first seek and receive Contractor’s consent to such delegation; and provided, further, that such consent will not be unreasonably withheld, unreasonably conditioned or unreasonably delayed.  If, upon JEA’s request for such consent, Contractor has concerns that may lead to Contractor’s (reasonably) withholding such consent, then Contractor will promptly meet and in good faith discuss with JEA such reasonable and appropriate means as may be taken to address and resolve such concerns so as to allow for such consent to be granted. If Contractor has consented to the delegation of JEA’s obligations as provided above, then, if JEA so requests, Contractor will execute such reasonable documentation evidencing such consent and releasing JEA from such delegated obligations.

Successors and Assigns.  Subject to Sections 18.3.1 and 18.3.2, the provisions of this Agreement will extend to the benefit of and will be binding upon the successors and permitted assigns of the Parties.

Unauthorized Assignments.  Any attempted assignment, delegation or transfer of a Party’s rights and/or obligations under this Agreement that is not in accordance with this Section 18.3 shall be null and void.

Reviews, Inspections, Approvals by JEA.

Any and all reviews, inspections or approvals by JEA or JEA’s Engineer or any of their respective representatives that are required by, allowed or otherwise referenced in this Agreement or that are otherwise undertaken by JEA or JEA’s Engineer or any of their respective representatives in connection with the Work, before or after the Effective Date, are for the sole purpose of concept review only.  Any such reviews, inspections, approvals or related actions of JEA shall not in any way be, or be deemed to be, either: (a) an indication of any knowledge or expertise by any such parties in any area of the Work; (b) an approval of any architectural, civil, structural, electrical, mechanical, plumbing, engineering, fire protection, safety or design aspects, requirements or specifications, all of which are, and shall remain, the responsibility of Contractor; or (c) a waiver of Contractor’s obligations to perform the Work in accordance with this Agreement. Notwithstanding any provision in this Agreement to the contrary, JEA shall not be deemed to have assumed the responsibilities of Contractor nor shall Contractor presume that JEA or its representatives have any knowledge or expertise in any area of the Work as a result of any such review, inspection approval or related actions. No action or inaction by JEA or its representatives with respect to the design or construction of the Work shall relieve Contractor of its duties and responsibilities under this Agreement or under this Agreement.

Governing Law.

To the greatest extent permitted by law, this Agreement shall in all respects be governed by and construed in accordance with the laws of the State of Florida, excluding any choice of law provisions that would result in the application of the laws of another jurisdiction.

Severability.

If any provision of this Agreement shall be held void, voidable, invalid or inoperative, no other provision of this Agreement shall be affected as a result thereof, and, accordingly, the remaining provisions of this Agreement shall remain in full force and effect as though such void, voidable, invalid or inoperative provision had not been contained herein.

Notices.

All notices permitted or required to be given under this Agreement shall be in writing and shall be deemed duly given: (a) on the same Day when transmitted by electronic mail to the recipient’s e-mail address as set forth below; provided, that such notice is initially printed onto the sending Party’s company letterhead and signed in ink by an authorized representative of the Party, with such letter then scanned into .pdf, .gif, .jpeg or similar electronic scan format, and attached to the e-mail so transmitted, and provided further, that the recipient has confirmed its receipt of the email either by response email or by verbal confirmation in person or by telephone, (b) on the date when delivered, when sent by overnight courier (e.g., FedEx or UPS) or by personal delivery.  All notices shall be delivered or sent to the Parties at their respective address(es) or number(s) shown below or to such other address(es) or number(s) as a Party may designate by prior written notice given in accordance with this provision to the other Party:

If to JEA:

JEA

Attn: Jim Stancin

15701 Beaver Street West

Jacksonville, Florida 32234

Email Address: stanjm@jea.com

With a copy to:

JEA

Attn: General Counsel

225 N. Pearl St.

Jacksonville, Florida 32202

If to Contractor:

__________________

__________________

__________________

Attention:

Email Address:

and a copy to:

__________________

__________________

Attention:

Email Address:

Article and Section Headings.

The Article and Section headings herein have been inserted for convenience of reference only and shall not in any manner affect the construction, meaning or effect of anything herein contained nor govern the rights and liabilities of the Parties.  References to “Articles” and “Sections” in these Terms and Conditions shall mean the Articles and Sections of these Terms and Conditions unless otherwise expressly noted.

No Waiver of Rights.

Except as may be specifically agreed in writing, the failure of JEA or Contractor to insist in any one or more instances upon the strict performance of any one or more of the provisions of this Agreement or to exercise any right herein contained or provided by law or equity shall not be construed as, or constitute in any way, a waiver, modification or relinquishment of the performance of such provision or right(s), or of the right to subsequently demand strict performance or exercise of such right(s), and all such rights shall continue unchanged and remain in full force and effect. “Electronic mail” shall not be considered a “writing” for purposes hereof.

Entire Agreement.

This Agreement contains the entire agreement between the Parties with respect to the subject matter hereof, and supersedes any and all prior and contemporaneous written and oral agreements, proposals, negotiations, understandings and representations pertaining to the subject matter hereof, including [Non-Disclosure Agreement between JEA, Contractor and PIE Supplier, dated [●], 2026].

Amendments.

No amendments or modifications of this Agreement shall be valid unless evidenced in writing and signed by a duly authorized representative of the Party against which enforcement is sought. “Electronic mail” shall not be considered a “writing” for purposes hereof.

No Third-Party Rights.

This Agreement and all rights hereunder are intended for the sole benefit of the Parties, JEA Indemnitees, and shall not imply or create any rights on the part of, or obligations to, any other Person.

JEA’s Obligations Non-recourse.

The Parties acknowledge that JEA has entered into this Agreement entirely on its own behalf, and that Contractor will not have any recourse against any of JEA’s members, board of directors, managers, partners, joint venturers, officers, directors, employees, successors or assigns for any reason.

Relationship of the Parties.

Nothing in this Agreement shall be deemed to constitute either Party a partner, agent or legal representative of the other Party, or to create any fiduciary relationship between the Parties.  Contractor is and shall remain an independent contractor in the performance of this Agreement, maintaining complete control of its Personnel, workers, Subcontractors and operations required for performance of the Work.

Further Assurances.

Each of Contractor and JEA agrees to provide such information, execute and deliver any instruments and documents and to take such other actions as may be reasonably necessary, or reasonably requested by the other Party in order to give full effect to this Agreement and to carry out the intent of this Agreement.

Counterparts; Facsimile Signatures.

This Agreement may be executed in counterparts, each of which shall be deemed an original, but all of which together shall constitute one and the same instrument. Any signature page of any such counterpart, or any electronic or facsimile thereof, may be attached or appended to any other counterpart to complete a fully executed counterpart of this Agreement, and any electronic, .pdf-format or other facsimile transmission of any signature of a Party shall be deemed an original and shall bind such Party.

IN WITNESS WHEREOF, the Parties, intending to be legally bound, have caused this Agreement to be executed by their duly authorized officers as of the date indicated below and to be effective as of the Effective Date.

“JEA” 							“Contractor”

By:							By:

Name:	  						Name:

Title:				 			Title:

Exhibit A-1

Essential Form

[Attached]

Exhibit A-2

Technical Specifications

[Attached]

Exhibit B

Baseline Project Schedule

[NTD: To be inserted]

Exhibit C

Scheduling Specification

[NTD: To be inserted]

Exhibit D

Milestone Payment Schedule

[NTD: To be inserted]

Exhibit E

Monthly Progress Report

[Attached]

St. Johns River Power Park (SJRPP)

Unit 3 Combined Cycle Project

Equipment, Procurement and Construction Agreement

Monthly Progress Report No. ##: Issue Date:

TABLE OF CONTENTS

1.0 	EXECUTIVE SUMMARY

2.0 	SUMMARY OF PROGRESS AND STATUS OF ENGINEERING, PROCUREMENT AND CONSTRUCTION

2.1 	Current Month

2.2 	Next Month

3.0 	MEETING STATUS

4.0 	PRIORITIES / ISSUES / COORDINATION

5.0 	SAFETY

6.0 	QUALITY

7.0 	SCHEDULE UPDATE (with electronic files)

8.0	CHANGE IN WORK

9.0 	PERMIT AND COMPLIANCE STATUS

10.0 	PROJECT FINANCIAL STATUS

11.0 	PROGRESS PHOTOGRAPHS

ATTACHMENT 2:	Contractor Purchasing Status Summary

ATTACHMENT 3:	RFI Log

ATTACHMENT 4:	Level I Updated Schedule

ATTACHMENT 5:	Project Percent Complete Curves

ATTACHMENT 6:	Change Order Log

ATTACHMENT 7:	Project Financial Status

ATTACHMENT 8:	Surveillance Reports

EXECUTIVE SUMMARY

1.0	SUMMARY OF PROGRESS AND STATUS OF ENGINEERING, PROCUREMENT, AND CONSTRUCTION

  - Current Month – Date

    - Engineering:

      - Progress through Date is XX%.

      - Activities conducted during Date:

    - Procurement:

      - Progress through Date is about XX%. The Purchase Status

Summary is attached to this report, Attachment 2.

      - Activities conducted during Date:

1.1.3 	Construction:

1.1.3.1 Progress through Date is about XX%.

      - Activities conducted during Date:

    - Commissioning:

1.1.4.1	Progress through Date is about XX%.

      - Activities conducted during Date:

  - Next Month – Date

1.2.1 	Engineering:

1.2.2 	Procurement:

1.2.3 	Construction:

1.2.4 	Commissioning:

2.0 	MEETING STATUS

2.1 	Meetings held during Date

2.2 	Upcoming meetings in Date:

2.3 	Monthly Progress Meeting Proposed Schedule:

2.3.1

3.0 	PRIORITIES / ISSUES / COORDINATION

4.0 	SAFETY

4.1 	Contractor Monthly Site Safety Report for Date:

Contractor Hours

Subcontractor Hours

Man-Hours (Total)

Injuries 					(Contractor) 	(Subcontractor)

First Aid

Recordable Injuries

Restricted Duty

Total Restricted Duty

Lost Time Cases

Total Lost Time Days

Site Safety

Non-Compliance Notices Issued

Safety Violation Notices Issued

Employee Violation Notices Issued

PPE Compliance (Percent Worn)

Hard Hats

Eye Protection

Hearing Protection

Foot Protection

Hand Protection

Fall Protection

5.0 	QUALITY

5.1 	Activities

5.1.1 	TRAINING / AUDITING:

5.1.2 	RECEIVING / STORAGE/PM:

5.1.3	SOILS / CONCRETE:

5.1.4 	STRUCTURAL & BUILDING STEEL:

5.1.5	 EQUIPMENT SETTING / ALIGNMENT:

5.1.6 	PIPING / WELDING / NDE / PWHT:

5.1.7 	ELECTRICAL / I&C:

5.1.8 	SURVEILLANCE UNSATS / NCRS (See Attachment #8)

5.1.9 	SYSTEM FLUSHES, CLEANING AND ACCEPTANCE TESTING

5.1.9.1 Cleanliness air blows were conducted on the following systems:

5.1.9.2 Flushes were completed on the following systems:

5.1.9.3 Cleanliness inspections were performed on the following:

5.1.9.4 Acceptance tests were performed on the following:

6.0 	SCHEDULE UPDATE

6.1 	This update is based on the overall Level 3 schedule for the project. The target

schedule is shown below the actual progress reported for each activity. The

overall project progress is about XX%.

6.2	 Project Percent Complete Curves, Attachment 5.

6.2.1 	Construction, Project Percent Complete, and Commissioning Percent

Complete

6.2.2 	Engineering & Procurement Percent Complete

7.0 	CHANGES IN WORK

8.0 	PERMIT AND COMPLIANCE STATUS

9.0 	PROJECT FINANCIAL STATUS

10.0 	PROGRESS PHOTOGRAPHS

Exhibit F

Insurance Requirements

[NTD: To be inserted]

Exhibit G

Permits

[NTD: To be inserted]

Exhibit H

Key Personnel

[NTD: To be inserted]

Exhibit I

JEA Contractor Travel Policy

[Attached]

JEA Contractor Travel Policy

    - To the extent Contractor's fees include reimbursement for travel and travel related expenses, only the authorized expenses described here in will be reimbursed.  Contractor must request approval in writing from the Project Manager for all travel for a specific person on official JEA business prior to commencement of travel.  JEA will only reimburse Contractor for actual cost of travel expenses that are documented with receipts submitted with the expense statement (the "Traveler"). The Traveler shall choose the most economical means of transportation, considering the nature of the business, the Traveler's time, cost of transportation, meals, lodging and incidental expenses required.  Reimbursement shall be made only for travel performed over usually regularly traveled routes to the destination. When travel is by indirect route for the Traveler’s own convenience, reimbursement for expenses shall be based only on such charges as would have been incurred over the usually traveled route.

    - Authorized Expenses:

    - Airplane

    - Travel by common carrier will only be reimbursed at the coach/economy fare rate purchased.

    - A copy of the Traveler's air itinerary showing the cost of the coach/economy fare must be submitted along with the expense statements. The Traveler is encouraged to select the most economical published fare. A round-trip coach/economy fare greater than $1,500 must be pre-approved by the Traveler's Chief.

    - Private Automobiles

    - If the total miles from point of origin to destination exceeds 400 miles one way, the mileage reimbursement for use of a private motor vehicle shall be limited to the lesser of:

    - I.     IRS rate per mile (current mileage rate can be found on the IRS website) or

    - II.    the lowest airline common carrier coach/economy fare to the nearest airport plus the cost of other means of transportation from the airport to the destination.

    - If travel is by private automobile, reimbursement shall be based on the IRS authorized mileage rate in existence at the time of travel.  All mileage shall be completed from the constructive point of origin to the point of destination. Vicinity mileage incurred while driving on official business may also be reimbursed. No other reimbursement for expenses related to the operation, maintenance and ownership of a vehicle shall be allowed when a private motor vehicle is used on public business.

    - Car Rental

    - Rental cars may be used only if taxis or other means of transportation are less economical or otherwise impractical.

    - JEA has contracts with AVIS, Budget and Enterprise/National for car rentals and must be used where available.  For reservations:

      - AVIS

        - https://www.carrental.com/abgPartners/sof/

        - 800-652-7900

        - Discount Code: B113410

      - Budget

        - https://www.carrental.com/abgPartners/sof/

        - 800-214-6094

        - Discount Code: B113410

      - Enterprise/National

        - https://elink.enterprise.com/en/23/08/jea.html

        - Account Number: XZ78612

    - Every effort shall be made to coordinate travel so that Travelers share a rental car and thereby eliminate multiple cars at the same location. Travelers must use the intermediate or standard class (or subordinate) of vehicles unless the number of passengers or the volume of equipment makes the intermediate/standard class impractical or if health or physical need requires a larger vehicle. A business justification for upgrades noting such must be included in the travel pre-approval. Personal accident insurance purchased by the traveler will not be reimbursed by JEA.

    - A receipt of itemized rental car charges must be obtained and submitted with the travel reimbursement claim.

    - Lodging

    - Reimbursement will be made for the cost of reasonably required overnight lodging when a Traveler is required to be away from his/her place of residence on behalf of JEA business. Travelers shall select lodging that is the most economical available, consistent with the duties being performed. Travelers will be reimbursed for a single room rate; double occupancy rates may be obtained if two Travelers share a room.

    - Travelers must document all lodging expenses with itemized statement and paid receipt from lodging facility. A receipt of itemized lodging expenses must be obtained and submitted with your travel reimbursement claim. Personal expenses such as entertainment, in-room movies, in-room concessions (i.e., mini-bar charges) and other personal charges will not be reimbursed.

    - Meals

    - Reimbursement is authorized for meals for all travelers while in a business travel status at the following fixed subsistence / per diem rates, or, at the traveler's option, at the amount submitted, not to exceed the following fixed maximum subsistence rates, but in any case, only when travel begins before and extends beyond the times specified:

    - I.      Breakfast - when Travel Time begins before 6:00 a.m. and extends beyond 8:00 a.m. The JEA breakfast per diem maximum is $20.

    - II.     Lunch - when Travel Time begins before 12:00 noon and extends beyond 2:00 p.m. The JEA lunch per diem maximum is $25.

    - III.    Dinner - when Travel Time begins before 6:00 p.m. and extends beyond 8:00 p.m. The JEA dinner per diem maximum is $35.

    - IV.     International Travel - for travel outside of the United States, the per diem rate is doubled to $100 per day.

    - Incidental Transportation Expenses

    - The following expenses incidental to transportation of the Traveler may be reimbursed:

    - I.      Taxi fare

    - II.     Ferry fares, bridge, road and tunnel tolls

    - III.    Storage and parking fees

    - a).  Valet parking may be selected when there is not a more economical means of parking or where less economical options present a safety concern. A business justification for the use of valet parking must be provided in the reimbursement claim.

    - b).  One of the long-term (non-valet) airport parking options (vs. hourly parking) must be utilized for approved travel greater than 24 hours.

    - IV.     Communication expenses such as business telephone expenses and daily internet/wireless access to conduct JEA business or to inform family members or caretakers of travel delays.

    - V.      Reasonable gratuities for services incurred at a cost (not to exceed 20% of the cost of the service or to exceed the total subsistence allowance in the case of meals).

    - VI.    Reasonable gratuities for services incurred without a cost (limited to $10 per day) (receipt not required, but service justification must be indicated).

Exhibit J

Acceptable Subcontractors

[NTD: To be inserted]

Exhibit K

Forms of Certificates

[Attached]

Exhibit K-1

Form of Certificate of Ready for First Fire

CERTIFICATE OF READY FOR FIRST FIRE

Re:	Equipment, Procurement and Construction Agreement between JEA (“JEA”) and [●] (“Contractor”), dated [●], 2026 (the “Agreement”).

Date: 	[●]    (“Ready for First Fire Date”)

1.	Unless otherwise defined herein, the capitalized terms used throughout this certificate shall have the meanings ascribed to same in the Agreement.

2.	Contractor certifies and represents that the following statements are true as of the Ready for First Fire Date:

- The Ready for First Fire criteria have been met as required in accordance with Section 1.1 (Definitions; Ready for First Fire) of the Agreement.

- As required by Section 6.1.2 of the Agreement, Contractor hereby delivers this Certificate of Ready for First Fire, completed except for signature by JEA, to JEA’s duly authorized representative.

3.	The person signing below is authorized to submit this Certificate of Ready for First Fire to JEA and on behalf of Contractor.

| Contractor’s Representative: ________________________________ By: Date: Name: ## Title: | JEA’s Representative: ________________________________ By: Date: Name: Title: |
| --- | --- |

Exhibit K-2

Form of Certificate of Ready for Full Steam Admission

CERTIFICATE OF READY FOR FULL STEAM ADMISSION

Re:	Equipment, Procurement and Construction Agreement between JEA (“JEA”) and [●] (“Contractor”), dated [●], 2026 (the “Agreement”).

Date: 	[●]    (“Ready for Full Steam Admission Date”)

1.	Unless otherwise defined herein, the capitalized terms used throughout this certificate shall have the meanings ascribed to same in the Agreement.

2.	Contractor certifies and represents that the following statements are true as of the Ready for Full Steam Admission Date:

- The Ready for Full Steam Admission criteria have been met as required in accordance with Section 1.1 (Definitions; Ready for Full Steam Admission) of the Contract.

- As required by Section 6.1.7 of the Agreement, Contractor hereby delivers this Certificate of Ready for Full Steam Admission, completed except for signature by JEA, to JEA’s duly authorized representative.

3.	The person signing below is authorized to submit this Certificate of Ready for Full Steam Admission to JEA and on behalf of Contractor.

| Contractor’s Representative: ________________________________ By: Date: Name: ## Title: | JEA’s Representative: ________________________________ By: Date: Name: Title: |
| --- | --- |

Exhibit K-3

Form of Certificate of Mechanical Completion

CERTIFICATE OF MECHANICAL COMPLETION

Re:	Equipment, Procurement and Construction Agreement between JEA (“JEA”) and [●] (“Contractor”), dated [●], 2026 (the “Agreement”).

Date: 	[●]    (“Mechanical Completion Date”)

1.	Unless otherwise defined herein, the capitalized terms used throughout this certificate shall have the meanings ascribed to same in the Agreement.

2.	Contractor certifies and represents that the following statements are true as of the Mechanical Completion Date:

- Contractor has satisfied all of the requirements for the achievement of Mechanical Completion as required in accordance with Section 6.2.1 (Criteria; Mechanical Completion) of the Agreement.

- As required by Section 6.2.2 of the Agreement, Contractor hereby delivers this Certificate of Mechanical Completion, completed except for signature by JEA, to JEA’s duly authorized representative.

3.	The person signing below is authorized to submit this Certificate of Mechanical Completion to JEA and on behalf of Contractor.

| Contractor’s Representative: ________________________________ By: Date: Name: ## Title: | JEA’s Representative: ________________________________ By: Date: Name: Title: |
| --- | --- |

CERTIFICATE OF MECHANICAL COMPLETION

(Page 2 of 2)

Re:	Equipment, Procurement and Construction Agreement between JEA (“JEA”) and [●] (“Contractor”), dated [●], 2026 (the “Agreement”).

JEA to cross through one (1) of the following statements:

- JEA agrees that Mechanical Completion has been achieved in accordance with Section 6.2.1 (Criteria for Mechanical Completion) of the Agreement. This Certificate of Mechanical Completion was received by JEA on the date first written above and is effective as of such date.

- JEA does not agree that Mechanical Completion has been achieved by the Contractor for the reasons listed below and/or the incomplete nature of the specified portions of the Work listed below or on the attached sheet:

________________________________________________________________

________________________________________________________________

________________________________________________________________

3.	The person signing below is authorized to sign this Certificate of Mechanical Completion for and on behalf of JEA.

JEA’s Representative:

________________________________

By:

Date:

Name:

## Title:

Exhibit K-4

Form of Certificate of Substantial Completion

CERTIFICATE OF SUBSTANTIAL COMPLETION

(Page 1 of 2)

Re:	Equipment, Procurement and Construction Agreement between JEA (“JEA”) and [●] (“Contractor”), dated [●], 2026 (the “Agreement”).

Date: 	[●]  (“Substantial Completion Date”)

1. 	Unless otherwise defined herein, the capitalized terms used throughout this certificate shall have the meanings ascribed to same in the Agreement.

2.	Contractor certifies and represents that the following statements are true as of the Substantial Completion Date:

- Contractor has satisfied all of the requirements for the achievement of Substantial Completion as required in accordance with Section 6.3.1 (Criteria for Substantial Completion) of the Agreement.

- As required by Section 6.3.2 of the Agreement, Contractor hereby delivers this Certificate of Substantial Completion, completed except for signature by JEA, to JEA’s duly authorized representative.

- Punch List items not completed to date are listed below or on the attached sheet.

________________________________________________________________

________________________________________________________________

________________________________________________________________

3. 	The person signing below is authorized to submit this Certificate of Substantial Completion to JEA and on behalf of Contractor.

Contractor’s Representative:

________________________________

By:

Date:

Name:

## Title:

CERTIFICATE OF SUBSTANTIAL COMPLETION

(Page 2 of 2)

Re:	Equipment, Procurement and Construction Agreement between JEA (“JEA”) and [●] (“Contractor”), dated [●], 2026 (the “Agreement”).

JEA to cross through one (1) of the following statements:

- JEA agrees that Substantial Completion has been achieved in accordance with Section 6.3.1 (Criteria for Substantial Completion) of the Agreement. This Certificate of Substantial Completion was received by JEA on the date first written above and is effective as of such date.

- JEA does not agree that Substantial Completion has been achieved by the Contractor for the reasons listed below and/or the incomplete nature of the specified portions of the Work listed below or on the attached sheet:

________________________________________________________________

________________________________________________________________

________________________________________________________________

3.	The person signing below is authorized to sign this Certificate of Substantial Completion for and on behalf of JEA.

JEA’s Representative:

________________________________

By:

Date:

Name:

## Title:

## Exhibit K-5

Form of Certificate of Final Completion

CERTIFICATE OF FINAL COMPLETION

(Page 1 of 2)

Re:	Equipment, Procurement and Construction Agreement between JEA (“JEA”) and [●] (“Contractor”), dated [●], 2026 (the “Agreement”).

Date: 	[●]     (“Final Completion Date”)

1. 	Unless otherwise defined herein, the capitalized terms used throughout this certificate shall have the meanings ascribed to same in the Agreement.

2.	Contractor certifies and represents that the following statements are true as of the Final Completion Date:

- Contractor has satisfied all of the requirements for the achievement of Final Completion as required in accordance with Section 6.6.1 (Criteria for Final Completion) of the Agreement.

- As required by Section 6.6.2 of the Agreement, Contractor hereby delivers this Certificate of Final Completion, completed except for signature by JEA, to JEA’s duly authorized representative.

3. 	The person signing below is authorized to submit this Certificate of Final Completion to JEA for and on behalf of Contractor.

Contractor’s Representative:

________________________________

By:

Date:

Name:

## Title:

CERTIFICATE OF FINAL COMPLETION

(Page 2 of 2)

Re:	Equipment, Procurement and Construction Agreement between JEA (“JEA”) and [●] (“Contractor”), dated [●], 2026 (the “Agreement”).

JEA to cross through one (1) of the following statements:

- JEA agrees that Final Completion has been achieved in accordance with Section 6.6.1 (Criteria for Final Completion) of the Agreement. This Certificate of Final Completion was received by JEA on the date first written above and is effective as of such date.

- JEA does not agree that Final Completion has been achieved by the Contractor for the reasons listed below and/or the incomplete nature of the specified portions of the Work listed below or on the attached sheet:

________________________________________________________________

________________________________________________________________

________________________________________________________________

3.	The person signing below is authorized to sign this Certificate of Final Completion for and on behalf of JEA.

JEA’s Representative:

________________________________

By:

Date:

Name:

Title:

Exhibit L-1

Facility Site (ALTA Survey)

[NTD: To be inserted]

Exhibit L-2

Existing Conditions

[NTD: To be inserted]

Exhibit M

Form of Change Order

| JEA: | [_______] Attn: | Change Order No.: | [ ] |
| --- | --- | --- | --- |
|  |  | Date of Change Order: | [Date] |
| Contractor: | [______ ] [Address] [Address] Attn: [Contact Name] Email: [Contact Email] | Agreement Date: | [Date] |

Change Description:

[Contractor to provide description of changes requested, including whether there may be any impact on health and safety and/or the quality requirements.]

Change Reason:

[Contractor to provide the reason & justification for the changes requested, e.g. design change, scope increase, schedule compression, estimate omission, etc.]

Change Order Contract Type (‘Lump Sum’ or ‘Cost + Mark-up’): Original Contract Price: $__________________

Net change by previously authorized Change Orders: $__________________

Contract Price including previously authorized Change Orders: $__________________

Amount of increase/(decrease) requested in this Change Order: $__________________

New Contract Price following approval of this Change Order: $__________________

The Project Schedule will be extended by (number of days): __________________ Revised Guaranteed Mechanical Completion date: _________________ Revised Guaranteed Substantial Completion date: _________________

Contractor hereby acknowledges and agrees that this Change Order shall comprise and settle all of Contractor’s known and alleged impacts, claims, issues, disputes, concerns, requests for relief, Time Changes, Price Changes, or potential Change Orders related to or arising out of the subject matter of this Change Order.  Except to the extent expressly provided herein, Contractor hereby acknowledges that it shall not be entitled to any additional Change Order, change to the Project Schedule, or any other recovery of any kind arising out of or related to any the subject matter of this Change Order, including (without limitation) any potential impact, singly or in combination with other Work or changes, the changes provided in this Change Order may have on other Work, both changed and unchanged, to the extent such changes were known or should have reasonably known by Contractor upon the execution of this Change Order.  This Change Order shall become effective upon the latter of the dates of execution set forth below or the  date of the JEA’s signature where this Change Order is a Change Directive.

| Contractor | JEA |
| --- | --- |
| [ ] | [____] |
| By: | By: |
| Name: | Name: |
| Title: | Title: |
| Date: | Date: |

Exhibit N

Lien Waivers

[Attached]

EXHIBIT N-1

FORM OF CONDITIONAL LIEN RELEASE UPON PROGRESS PAYMENT

KNOW ALL MEN BY THESE PRESENTS:

WHEREAS, the undersigned [●] (“Contractor”), pursuant to that certain Equipment, Procurement and Construction Agreement dated [●], 2026 (the “Agreement”) with JEA (“Owner”), did furnish labor, equipment and/or materials utilized in connection with improvements to real property owned by Owner, which property and/or improvements are described or more commonly known as the St. Johns River Power Park project (the “Project”), located in Jacksonville, Duval County, Florida.

NOW THEREFORE, this __ day of _____, 20__, for and in consideration of all sums paid heretofore under the Agreement and the sum of 	 Dollars ($	) pursuant to Contractor’s Invoice No. __, the legal sufficiency of which is hereby acknowledged, the undersigned, on behalf of itself and anyone acting or claiming through or under it, and intending to be legally bound:

- acknowledges that, except for the claims expressly set forth in Attachment 1 (the “Reserved Claims”), it has been, or upon full payment of the aforementioned amount will be, paid in full for all labor, services, materials, fixtures, equipment, apparatus or machinery furnished or work performed for the Project to date (collectively the “Work”), and

- does hereby, conditioned upon payment of the aforementioned amount, but otherwise unconditionally and without reservation waive, release, remise and relinquish, except for the Reserved Claims, any and all payment claims arising out of or related, directly or indirectly, to the Work, the Agreement or the Project which it ever had or may now have against the Owner, the Owner’s lender (if any), the Owner’s surety (if any), their officers, agents, attorneys, employees, successors and assigns (collectively, the “Released Parties”), or against any labor or material payment bond furnished to date in connection with the Project, and

- on behalf of itself and anyone acting or claiming through or under it, hereby waives and releases, except for the Reserved Claims, any mechanic’s, materialman’s or similar liens or stop notices and all rights to file any such liens or notices in the future against the Project and on the monies or other consideration due or to become due from any of the Released Parties for the Work performed to date, and agrees to defend, indemnify and hold harmless the Released Parties from and against any and all costs and expenses (including reasonable attorneys’ fees and costs) resulting from any such claim or lien, and

- represents that: (i) there are no outstanding amounts owed to any lower-tier subcontractors, suppliers or materialmen for any labor, services, materials, fixtures, equipment, apparatus or machinery furnished or work furnished for the Project under any prior lien release which are not subject to this lien release; and (ii) upon receipt of the above amount, Contractor will fully pay for all said labor, services, materials, fixtures, equipment, apparatus or machinery furnished or work furnished by it, or by its lower-tier subcontractors, suppliers or materialmen on the Project to date, subject only to retainage withheld (if any), such payment to be made within thirty (30) days after receipt of the above amount, or such different time period as has been agreed to with such lower-tier subcontractors, suppliers or materialmen.

(Date)	(Signature)

Attachment 1

Reserved Claims

[Insert]

EXHIBIT N-2

FORM OF UNCONDITIONAL LIEN RELEASE UPON FINAL PAYMENT

KNOW ALL MEN BY THESE PRESENTS:

WHEREAS, the undersigned [●] (“Contractor”), pursuant to that certain Equipment, Procurement and Construction Agreement dated [●], 2026 (the “Agreement”) with JEA (“Owner”), did furnish labor, equipment and/or materials utilized in connection with improvements to real property owned by Owner, which property and/or improvements are described or more commonly known as the St. Johns River Power Park project (the “Project”), located in Jacksonville, Duval County, Florida

NOW THEREFORE, this __ day of__________, for and in consideration of all sums paid heretofore under the Contract, the legal sufficiency of which is hereby acknowledged, the undersigned, on behalf of itself and anyone acting or claiming through or under it, and intending to be legally bound:

- acknowledges that, except for the claims expressly set forth in Attachment 1 (the “Reserved Claims”), it has been paid in full for all labor, services, materials, fixtures, equipment, apparatus or machinery furnished or work performed for the Project (collectively the “Work”), and

- does hereby unconditionally and without reservation waive, release, remise and relinquish, except for the Reserved Claims, any and all payment claims arising out of or related, directly or indirectly, to the Work, the Contract or the Project which it ever had or may now have against the Owner, the Owner's lender (if any), the Owner’s surety (if any), their officers, agents, attorneys, employees, successors or assigns (collectively, the “Released Parties”), or against any labor or material payment bond furnished in connection with the Project, and

- on behalf of itself and anyone acting or claiming through or under it, hereby waives and releases, except for the Reserved Claims, any mechanic's, materialman's or similar liens or stop notices and all rights to file any such liens or notices in the future against the Project for the Work, and agrees to defend, indemnify and hold harmless the Released Parties from and against any and all costs and expenses (including reasonable attorneys’ fees and costs) resulting from any such claim or lien, and

- represents that Contractor has fully paid for all said labor, services, materials, fixtures, equipment, apparatus or machinery furnished or work furnished by it, or by its lower-tier subcontractors, suppliers or materialmen on the Project.

___________________________		___________________________

(Date)						(Signature)

Attachment 1

Reserved Claims

[Insert]

Exhibit O

Contractor Rate Sheet

[NTD: To be inserted]

Exhibit P

HUMAN TRAFFICKING AFFIDAVIT - S.787.06, FLORIDA STATUTES

Before me, the undersigned authority, personally appeared

, whom after being duly sworn, deposes and states: (Affiant)

- My name is 	and I am over eighteen years of age. The following information is given from my own personal knowledge.

- I am an officer or representative with 	, a non-governmental entity. I am authorized to provide this affidavit on behalf of _ 		.

- The non-governmental entity, _ 	_ 	, does not use coercion for labor or services as defined in s.787.06, Florida Statutes.

FURTHER AFFIANT SAYETH NOT.

__, 20__

STATE OF FLORIDA COUNTY

OF

_ (Affiant)

Sworn to (or affirmed) and subscribed before me by means of _	physical presence or	online notarization, this	day of 	, by

. (Affiant)

_	 (Signature of Notary Public--State of Florida)

_

(Print, Type, or Stamp Commissioned Name of Notary Public) Personally Known _ 	_ OR Produced Identification

Type of Identification Produced 	_

Exhibit Q-1

Form of Payment Bond

JEA CONTRACT NUMBER [__________]

SURETY BOND NUMBER [________]

PAYMENT BOND

REQUIRED

BY SECTION 255.05, FLORIDA STATUTES

As to the Contractor/Principal:

Name: Contracting Party Name

Telephone: (    )

As to the Surety:

Name:

Principal Business Address:

Telephone: (    )

As to the Owner of the Property/Contracting Public Entity:

Name: JEA, 225 N. Pearl St., Jacksonville, FL  32202

Telephone: (904) 665-6000

Description of project including address and description of improvements:

“Contract Title”

Project Number

JEA

PAYMENT BOND REQUIRED BY

SECTION 255.05, FLORIDA STATUTES

KNOW ALL MEN BY THESE PRESENTS, that  Contracting Party Name, hereinafter called "Principal", and [__________________], a [corporation] organized and existing under the laws of the State of [___________________], and duly authorized to conduct and carry on a general surety business in the State of Florida, hereinafter called "Surety," are each held and firmly bound unto JEA of Jacksonville, a municipal corporation, of Jacksonville, Duval County, Florida, hereinafter called "JEA" or "Owner," in the penal sum of [________________________] and [__]/100 Dollars ($[___________.__])  in lawful money of the United States of America, for the payment whereof Principal and Surety bind themselves, their respective heirs, executors, administrators, legal representatives, successors and assigns, jointly and severally, firmly by these presents.

WHEREAS the Principal entered into a certain contract with JEA, dated the [____] day of [__________], 20[__] (JEA Contract# Contract Number) (the “Contract”) which is, by this reference, made a part hereof, as if fully set out herein, for “Contract Title”, pursuant to Solicitation # [_______________],  entitled “Contract Title" for JEA, in accordance with plans and specifications prepared by JEA.

NOW, THEREFORE, THE CONDITION OF THIS BOND is such that if the said Principal:

(1) Provides to JEA a certified copy of the recorded bond prior to commencing the work (or before recommencing the work after a default or abandonment) in accordance with Section 255.05(1)(b), Florida Statutes; and

(2) Promptly makes payments to all claimants, as defined in Sections 255.05(1) and 713.01, Florida Statutes, supplying Principal with labor, materials or supplies that are consumed or used directly or indirectly, by Principal in connection with the prosecution of the work provided for in such Contract and including all insurance premiums on the work, and including any authorized extensions or modifications of such Contract; and

(3) Defends, indemnifies and saves JEA harmless from claims, demands, liens, or suits by any person or entity whose claim, demand, lien or suit is for the payment of labor, materials or equipment furnished for use in the performance of the Contract, provided JEA has promptly notified the Principal and Surety of any claims, demands, liens, or suits and provided there is no failure by JEA to pay the Principal as required by the Contract; and

(4) Pays JEA all losses, damages, expenses, costs and attorney’s fees, including appellate proceedings, that JEA sustains because of the Principal’s failure to promptly make payments to all claimants as provided above, then this Bond is void; otherwise, it remains in full force and effect, both in equity and in law, in accordance with the statutes and the laws of the State of Florida and, specifically Section 255.05, Florida Statutes.

PROVIDED, no suit or action for labor, materials or supplies shall be instituted hereunder against the Principal or the Surety unless a claimant provides, to each of them, both of the proper notices, in accordance with the requirements of Section 255.05(2), Florida Statutes. Both notices must be given in order to institute such suit or action.

PROVIDED further, an action, except for an action exclusively for recovery of retainage, must be instituted against the Principal or Surety on this Payment Bond within one (1) year after the performance of the labor or completion of delivery of the materials or supplies, in accordance with the requirements of Section 255.05(10), Florida Statutes.

PROVIDED further, an action exclusively for the recovery of retainage must be instituted against the Principal or Surety within one (1) year after the performance of the labor or completion of delivery of the materials or supplies, unless an extension beyond the one (1) year period is specifically provided pursuant to Section 255.05(10), Florida Statutes.

PROVIDED further, that the said Surety, hereby stipulates and agrees that no change, extension of time, alteration or addition of the terms of the Contract or to the work to be performed thereunder or the specifications accompanying the same shall in any wise effect its obligation on this Bond, and it does hereby waive notice of any such change, extension of time, alteration or addition to the terms of the Contract or to the work or to the specifications.

SIGNED AND SEALED this           day of                             , 20__.

ATTEST:			Contracting Party Name, a [________________] [Corporation]

Signature				Signature

Type/Print Name		Type/Print Name

Title				Title

AS PRINCIPAL

Signed, Sealed and Delivered

in the Presence of:

________________________________	________________________________

________________________________	By: _____________________________

Its: _____________________________

AS SURETY

Name of Agent: __________________

Address: ________________________

_______________________________

Note:  Date of Bond Must Not Be Prior to Date of Contract

Exhibit Q-2

Form of Performance Bond

JEA CONTRACT NUMBER [__________]

SURETY BOND NUMBER [________]

PERFORMANCE BOND

As to the Contractor/Principal:

Name: Contracting Party Name

Telephone: (    )

As to the Surety:

Name:

Principal Business Address:

Telephone: (    )

As to the Owner of the Property/Contracting Public Entity:

Name: JEA, 225 N. Pearl St., Jacksonville, FL  32202

Telephone: (904) 665-6000

Description of project including address and description of improvements:

“Contract Title”

Project Number

JEA

PERFORMANCE BOND

KNOW ALL MEN BY THESE PRESENTS, that Contracting Party Name, as Principal,  (hereinafter called “Contractor”), and [_____________________________], a [corporation] organized and existing under the laws of the State of [________________] and duly authorized to conduct and carry on a general surety business in the State of Florida, as Surety (hereinafter called “Surety”), are each held and firmly bonded unto JEA, a body  politic and corporate, in Duval County, Florida, as Obligee (hereinafter called “JEA”), in the sum of [_______________________] and  00/100 Dollars ($[_________.__]), lawful money of the United States of America, for the payment whereof Contractor and Surety bind themselves, their respective heirs, executors, administrators, legal representatives, successors and assigns, jointly and severally, firmly by these presents.

WHEREAS, Contractor has by written agreement dated the [__] day of [                ___________], 20[__], entered into a contract with JEA (Contract # Contract Number) for “Contract Title” pursuant to Solicitation #[______]; all of said work to be done in the time and manner and in strict accordance with any advertisement for bids for said work and done in strict compliance with the drawings, plans and specifications for said work and requirements of JEA proposal and award therefor and of the contract and all documents included as a part of the contract (hereinafter referred to collectively as the “Contract”), all of which are, by this reference, made a part hereof to the same extent as if fully set out herein.

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that, if Contractor shall: (1) provide JEA with a certified copy of the recorded bond before commencing the work (or before recommencing the work after a default or abandonment; and (2) promptly and faithfully perform the construction work and other work in the time and manner prescribed in said Contract, which is made a part of this Bond, by reference, in strict compliance with the Contract requirements; and (3) perform the guarantee and maintenance of all work and materials furnished under the Contract for the time specified in the Contract; and (4) pay JEA all losses, delay and disruption damages and all other damages, expenses, costs, statutory attorney’s fees, including appellate proceedings, that JEA sustains because of a default by Contractor under the Contract; then this Bond shall be void; otherwise it shall remain in full force and effect, both in equity and in law, in accordance with the laws and statutes of the State of Florida.

PROVIDED, that the Surety hereby waives notice of any alteration or extension of time made by JEA, and any changes in or under the Contract and compliance or noncompliance with any formalities connected with the Contract or the changes, does not affect Surety’s obligation under this bond.

PROVIDED further, that whenever Contractor shall be declared by JEA to be in default under the Contract, JEA having performed JEA’s obligations thereunder, the Surety shall, at JEA’s sole option, take one (1) of the following actions upon JEA’s written notice:

(1)	Within a reasonable time, but in no event later than thirty (30) days from JEA's written notice of termination for default, the Surety shall arrange for the Company, with JEA’s consent, to complete the Contract.  Subject to the provisions below, JEA shall promptly pay the balance of the Contract price to the Surety upon completion of the Contract; or

(2)	(A) Within a reasonable time, but in no event longer than sixty (60) days from JEA’s written notice of termination for default, the Surety shall obtain a bid or bids for completing the Contract in accordance with its terms and conditions and, upon determination by Surety of the lowest responsible qualified bidder, award a contract to complete the Work required by the Contract, issue and notice to proceed, and timely pay the costs to complete the Contract, less the balance of the Contract price; or (B) JEA may elect to have the Surety determine jointly with JEA the lowest responsible qualified bidder, to have the Surety arrange for a contract between such bidder and JEA to complete the Work required by the Contract, and for the Surety to make available as Work progresses sufficient funds to pay the cost of completion, less the balance of the Contract price (even though there should be a default or a succession of defaults under the contract or contracts of completion arranged under this paragraph); or

(3)	Within a reasonable time, but in no event later than thirty (30) days from JEA's notice of termination for default, JEA may begin work to complete the Work required by the Contract or arrange for completion of the Contract and, within twenty-one (21) days thereafter, JEA shall determine the amount necessary to complete the Work required by the Contract.  Upon notice to the Surety, the Surety shall promptly tender payment to JEA of the amount so determined to complete the Work required by the Contract, less the balance of the Contract price.

The term “balance of the Contract price,” as used in this Bond, shall mean the total amount payable by JEA to Contractor under the Contract and any approved change orders thereto, less the amount properly paid by JEA to or on behalf of Contractor.  However, the term “balance of the Contract price” shall not include any liquidated damages or other damages due from Contractor to JEA (or which JEA may retain or use as an offset of amounts owed to Contractor) pursuant to the Contract.

In addition to the costs to complete the Contract under the options above, the Surety shall indemnify and hold JEA harmless on account of all claims and damages arising from Contractor’s default under the Contract, and pay JEA for all losses, delay and disruption damages, and all other damages, expenses, costs and statutory attorney’s fees, including appellate proceedings, that JEA sustains as the result of a default by the Contractor under the Contract.

PROVIDED further, the Surety shall indemnify and save JEA harmless from any and all claims and damages, arising from the Contractor’s default under the Contract including, but not limited to, contractual damages, expenses, costs, injury, negligent default, or intentional default, patent infringement and actual damages (including delay and disruption damages) in accordance with the Contract, and including all other damages and assessments which may arise by virtue of failure of the product to perform or any defects in work or materials  within a period of one (1) year from the date on which the Contractor receives from JEA a certificate of final completion under the Contract.

PROVIDED further, that during any interim period after JEA has declared Contractor to be in default but Surety has not yet remedied the default in the manner acceptable to JEA, Surety shall be responsible for securing and protecting the work site including, but not limited to, the physical premises, structures, fixtures, materials, and equipment, and shall be responsible for securing and protecting materials and equipment stored off-site in accordance with the Contract.

PROVIDED further, no right of action shall accrue on this Bond to or for the use of any person or corporation other than JEA named herein or the heirs, executors, administrators or successors of JEA.

REMAINDER OF PAGE LEFT BLANK INTENTIONALLY

NEXT PAGE IS THE SIGNATURE PAGE

SIGNED AND SEALED this           day of                             , 20__.

ATTEST:			Contracting Party Name, a _________________________ Corporation

Signature				Signature

Type/Print Name		Type/Print Name

Title				Title

AS PRINCIPAL

Signed, Sealed and Delivered

in the Presence of:

________________________________	________________________________

________________________________	By: _____________________________

Its: _____________________________

AS SURETY

Name of Agent: __________________

Address: ________________________

_______________________________

Note:  Date of Bond Must Not Be Prior to Date of Contract

Exhibit R

Care of JEA customers

[Attached]

Care of JEA Customers

Contractor agrees to provide excellent customer service throughout the execution of the Work during both scheduled Work hours and Overtime in the manner, as a minimum, as set forth below:

Customer Service Plan:

Contractor shall submit a Customer Service Plan prior to mobilization and designate an individual to assume the duties of Contractor's Customer Service Representative (CSR) as described herein.

Contractor shall provide an after-hours emergency phone number to JEA.

Contractor shall provide contact numbers for those individuals assigned to concerns arising during non-business hours and in the event of emergencies.  The designated person(s) shall provide a cellular phone number as the main contact number, and one alternate number.  The designated person(s) shall respond to JEA with proposed resolution within two hours of receiving a call from a JEA representative or customer.  If Contractor fails to respond within the designated time and it is thereby necessary for JEA to provide assistance, Contractor shall be responsible for all costs incurred by JEA as a result of resolving the concern.

Upon JEA approval, Contractor shall deliver fliers and/or door hangers provided by Project Outreach to all customers in an affected work area at least three days prior to each construction activity including, but not limited to, locates, TV/cleaning, soil borings, mobilization, etc. Upon JEA's request, the contractor will install JEA provided signage at a location chosen by the JEA project team. These signs will be removed by the contractor at the end of the project.

Contractor shall notify affected customers prior to any planned water/electric outages, line flushing, valve simulations and driveway/curb construction, paving and road closures.  The notification will be produced by Contractor (unless notifications are provided by JEA) and approved by JEA Project Outreach.

Customer Concerns:

The CSR shall contact the JEA customer who has a concern by the end of the business day of when the concern was received from JEA Project Outreach.  Contractor shall contact Project Outreach within two business days to confirm that they have contacted the customer and assessed the concern.

The CSR shall provide JEA Project Outreach with concern evaluations, resolutions, and actions taken all within five business days of when the concern was received.

The CSR shall notify Project Outreach immediately after a concern has been resolved with specific resolution actions or an update of the resolution.  Project Outreach will contact the customer following notification of resolution to confirm the resolution before Project Outreach closes the concern and prior to notifying Contractor, the CSR, JEA Representatives and inspectors of resolution of the concern.

Within one business day of receiving a concern from a JEA customer, Contractor shall notify JEA Project Outreach in writing of each customer concern reported directly to Contractor's personnel by any JEA customer.  Such notification shall include, as a minimum: Contractor's name, date and time the concern was communicated to Contractor, the name, address and phone numbers for the customer, the nature of their concern and any action that was taken or any action currently underway to resolve the concern.  The CSR shall follow the customer concern procedures stated above.

If Contractor fails to meet the problem resolution deadlines stated in this document in a manner that meets acceptable quality standards, JEA may make repairs or take other necessary actions to resolve the issue, which shall be at Contractor's sole expense.

Duties of the Customer Service Representative (CSR)

Contractor shall provide a Customer Service Representative for the Term of the Contract.  The CSR's primary responsibilities shall include, but are not limited to the following:

Communication: Serve as the primary point of contact for customer concerns and information requests; report customer concerns to the JEA Project Manager and Project Outreach or other internal JEA resources and assist in resolution of issues; and meet with customers on site as needed to assess their concerns.

Planning: Conduct biweekly progress meetings with JEA Project Manager; conduct progress meetings with Project Outreach regularly and as needed to review any outstanding complaints and provide a timeframe/action plan for resolving them; review customer satisfaction targets and goals, measurements, documentation and project definition and assist with making improvements; conduct periodic customer service reviews during the course of the Work to assess and identify any items considered to be at risk or vulnerable in relationship to meeting JEA goals and objectives; and notify Project Outreach, in a timely manner, of change in scope or schedule.

Process Improvement: Work with JEA to identify process improvement opportunities that increase customer service and satisfaction; make recommendations to JEA to enhance and assist with JEA goals and objectives for customer service; and conduct a customer service review at the completion of the construction phase of a project, but prior to the restoration, or "punch list" phase, to assess customers' satisfaction with the handling of concerns and customers' overall response to the project.

Disruption of Utility Services: If Contractor  disrupts any utility services (water, sewer or electric, etc.) during performance of the Work, Contractor shall return them to operation as soon as possible.  No disruption to any utility service disruption shall exceed the end of Contractor's normal work shift.  No disruption to the customer's utility services shall exceed any 12-hour period.  Should any of the customer's utility services be disrupted, for a period longer than 12 hours, Contractor shall provide alternative arrangements for the customer, as determined by JEA, with no additional cost to JEA for these arrangements unless otherwise specified in the documents.  The CSR shall immediately notify JEA Project Outreach (telephone 665-7500) of any service disruptions.

Restoration:

Contractor shall restore, for no additional compensation, the landscaping of any properties affected by Contractor's actions, directly or indirectly, (in the right-of-way not related to ongoing Work, or isolated Work in the right-of-way that would leave unrestored areas for undue periods of time subject to criticism) to its original state, within five calendar days from the time the area was disrupted.  All other restoration required within the right-of-way shall be scheduled in the customary method for such construction and in accordance with any permit conditions.

Contractor shall, at its own expense (unless otherwise specified in the documents), repair any irrigation systems damaged by Contractor's Work within one day from the time the irrigation system was damaged.  If this is not possible, Contractor shall inform the customer of the damage and provide an estimated time for repair.  In addition, Contractor shall make adequate provisions for the customer to water and maintain his or her lawn.

Contractor shall repair, at its own expense, any asphalt and concrete damaged by Company (in the right-of-way not related to ongoing Work, or isolated Work within the right-of-way that would leave unrestored areas for undue periods of time subject to residents/customer criticism) within five calendar days from the time the damage occurred.  All other restoration required within the right-of-way shall be scheduled in the customary method for such construction and in accordance with any permit conditions.

Customer Concern Ratios:

Project Outreach's goal for customer concerns is to completely resolve all complaints within 10 business days of receiving a complaint.  A formal customer concern shall be defined as a documented concern to JEA Project Outreach.  The concern may be of a real or perceived problem that the customer has against Contractor.

The JEA Project Manager or designee will notify Contractor on a monthly basis of how many concerns were received by JEA's Project Outreach and the number of concerns yet to be resolved.  JEA will immediately notify Contractor when a concern has been opened and has not been a response to it within five business days.  Contractor shall contact Project Outreach and provide a written correction plan within five calendar days of receipt of the notice. If at any time Contractor allows unresolved concerns to exceed the five business days without prior notification to Project Outreach and the customer concern ratio reaches 3.0 percent, Contractor shall be required to appear in front of Contractor Performance Review Board to explain the circumstances leading to the unresolved concern.  Contractor Performance Review Board will notify the Chief Procurement Officer of the board's decision and any recommended actions, which may include, but are not limited to, additional remedial action, termination of the Contract and/or suspension from JEA's Responsible Bidder's List in all categories for a period not to exceed one year.

If Contractor fails to adhere to the customer service requirements stated herein, Contractor's performance will be documented in accordance with JEA's Vendor Performance Evaluation process stated herein.

Exhibit S

Required Federal Contract Clauses

[Attached]

REQUIRED FEDERAL CONTRACT CLAUSES

In the event any portion of the Work is funded through a federal funding source, the following Required Federal Contract Clauses shall apply to Contractor’s performance under this Agreement.

  - Equal Employment Opportunity (FEMA & Grants)

    - During the performance of this contract, Contractor agrees as follows:

    - (1) Contractor will not discriminate against any employee or applicant for employment because of race, color, religion, sex, sexual orientation, gender identity, or national origin. Contractor will take affirmative action to ensure that applicants are employed, and that employees are treated during employment without regard to their race, color, religion, sex, sexual orientation, gender identity, or national origin. Such action shall include, but not be limited to the following:

    - Employment, upgrading, demotion, or transfer; recruitment or recruitment advertising; layoff or termination; rates of pay or other forms of compensation; and selection for training, including apprenticeship. Contractor agrees to post in conspicuous places, available to employees and applicants for employment, notices to be provided setting forth the provisions of this nondiscrimination clause.

    - (2) Contractor will, in all solicitations or advertisements for employees placed by or on behalf of Contractor, state that all qualified applicants will receive consideration for employment without regard to race, color, religion, sex, sexual orientation, gender identity, or national origin.

    - (3) Contractor will not discharge or in any other manner discriminate against any employee or applicant for employment because such employee or applicant has inquired about, discussed, or disclosed the compensation of the employee or applicant or another employee or applicant. This provision shall not apply to instances in which an employee who has access to the compensation information of other employees or applicants as a part of such employee's essential job functions discloses the compensation of such other employees or applicants to individuals who do not otherwise have access to such information, unless such disclosure is in response to a formal complaint or charge, in furtherance of an investigation, proceeding, hearing, or action, including an investigation conducted by the employer, or is consistent with Contractor's legal duty to furnish information.

    - (4)  Contractor will send to each labor union or representative of workers with which he has a collective bargaining agreement or other contract or understanding, a notice to be provided advising the said labor union or workers' representatives of Contractor's commitments under this section, and shall post copies of the notice in conspicuous places available to employees and applicants for employment.

    - (5)  Contractor will comply with all provisions of Executive Order 11246 of September 24, 1965, and of the rules, regulations, and relevant orders of the Secretary of Labor.

    - (6)  Contractor will furnish all information and reports required by Executive Order 11246 of September 24, 1965, and by rules, regulations, and orders of the Secretary of Labor, or pursuant thereto, and will permit access to his books, records, and accounts by the administering agency and the Secretary of Labor for purposes of investigation to ascertain compliance with such rules, regulations, and orders.

    - (7)  In the event of Contractor's noncompliance with the nondiscrimination clauses of this contract or with any of the said rules, regulations, or orders, this contract may be canceled, terminated, or suspended in whole or in part and Contractor may be declared ineligible for further Government contracts or federally assisted construction contracts in accordance with procedures authorized in Executive Order 11246 of September 24, 1965, and such other sanctions may be imposed and remedies invoked as provided in Executive Order 11246 of September 24, 1965, or by rule, regulation, or order of the Secretary of Labor, or as otherwise provided by law.

    - (8)  Contractor will include the portion of the sentence immediately preceding paragraph (1) and the provisions of paragraphs (1) through (8) in every subcontract or purchase order unless exempted by rules, regulations, or orders of the Secretary of Labor issued pursuant to section 204 of Executive Order 11246 of September 24, 1965, so that such provisions will be binding upon each subcontractor or vendor. Contractor will take such action with respect to any subcontract or purchase order as the administering agency may direct as a means of enforcing such provisions, including sanctions for noncompliance:

    - Provided, however, that in the event a Contractor becomes involved in, or is threatened with, litigation with a subcontractor or vendor as a result of such direction by the administering agency, Contractor may request the United States to enter into such litigation to protect the interests of the United States.

  - Compliance with the Davis-Bacon Act

    - (1)  To the extent required under applicable Federal program legislation, all transactions regarding this contract shall be done in compliance with the Davis-Bacon Act (40 U.S.C. 3141- 3144, and 3146-3148) and the requirements of 29 C.F.R. pt. 5 as may be applicable. Contractor shall comply with 40 U.S.C. 3141-3144, and 3146-3148 and the requirements of 29 C.F.R. pt. 5 as applicable.

    - (2)  Contractor shall be required to pay wages to laborers and mechanics at a rate not less than the prevailing wages specified in a wage determination made by the Secretary of Labor.

    - (3)  Contractor shall be  required to pay wages not less than once a week.

  - Compliance with the Copeland "Anti-Kickback" Act

    - (1)  Contractor.  Contractor shall comply with 18 U.S.C. § 874, 40 U.S.C. § 3145, and the requirements of 29 C.F.R. pt. 3 as may be applicable, which are incorporated by reference into this Contract.

    - (2)  Subcontracts. Contractor or subcontractor shall insert in any subcontracts the clause above and such other clauses as FEMA may by appropriate instructions require, and also a clause requiring the subcontractors to include these clauses in any lower tier subcontracts. The prime Contractor shall be responsible for the compliance by any subcontractor or lower tier subcontractor with all of these contract clauses.

    - (3)  Breach. A breach of the contract clauses above may be grounds for termination of the Agreement, and for debarment as a Contractor and subcontractor as provided in 29 C.F.R. § 5.12.

  - Compliance with the Contract Work Hours and Safety Standards Act

    - (1)  Overtime requirements. No Contractor or subcontractor contracting for any part of the Work which may require or involve the employment of laborers or mechanics shall require or permit any such laborer or mechanic in any workweek in which he or she is employed on such work to work in excess of forty hours in such workweek unless such laborer or mechanic receives compensation at a rate not less than one and one-half times the basic rate of pay for all hours worked in excess of forty hours in such workweek.

    - (2)  Violation; liability for unpaid wages; liquidated damages. In the event of any violation of the clause set forth in paragraph (b)(1) of this section Contractor and any subcontractor responsible therefor shall be liable for the unpaid wages. In addition, such Contractor and subcontractor shall be liable to the United States (in the case of work done under contract for the District of Columbia or a territory, to such District or to such territory), for liquidated damages. Such liquidated damages shall be computed with respect to each individual laborer or mechanic, including watchmen and guards, employed in violation of the clause set forth in paragraph (b)(1) of this section, in the sum of $27 for each calendar day on which such individual was required or permitted to work in excess of the standard workweek of forty hours without payment of the overtime wages required by the clause set forth in paragraph (b)(1) of this section.

    - (3)  Withholding for unpaid wages and liquidated damages. JEA or the federal agency providing funds under this Agreement shall upon its own action or upon written request of an authorized representative of the Department of Labor withhold or cause to be withheld, from any moneys payable on account of work performed by Contractor or subcontractor under any such contract or any other Federal contract with the same prime Contractor, or any other federally-assisted contract subject to the Contract Work Hours and Safety Standards Act, which is held by the same prime Contractor, such sums as may be determined to be necessary to satisfy any liabilities of such Contractor or subcontractor for unpaid wages and liquidated damages as provided in the clause set forth in paragraph (b)(2) of this section.

    - (4)  Subcontracts. Contractor or subcontractor shall insert in any subcontracts the clauses set forth in paragraph (b)(1) through (4) of this section and also a clause requiring the subcontractors to include these clauses in any lower tier subcontracts. The prime Contractor shall be responsible for compliance by any subcontractor or lower tier subcontractor with the clauses set forth in paragraphs (b)(1) through (4) of this section.

  - Clean Air Act

    - (1)  Contractor agrees to comply with all applicable standards, orders or regulations issued pursuant to the Clean Air Act, as amended, 42 U.S.C. § 7401 et seq.

    - (2)  Contractor agrees to report each violation to the JEA and understands and agrees that the JEA will, in turn, report each violation as required to assure notification to the Federal Emergency Management Agency, and the appropriate Environmental Protection Agency Regional Office.

    - (3)  Contractor agrees to include these requirements in each subcontract exceeding $150,000 financed in whole or in part with Federal assistance provided by FEMA.

  - Federal Water Pollution Control Act

    - (1)  Contractor agrees to comply with all applicable standards, orders, or regulations issued pursuant to the Federal Water Pollution Control Act, as amended, 33 U.S.C. 1251 et seq.

    - (2)  Contractor agrees to report each violation to JEA and understands and agrees that JEA will, in turn, report each violation as required to assure notification to the Federal Emergency Management Agency, and the appropriate Environmental Protection Agency Regional Office.

    - (3)  Contractor agrees to include these requirements in each subcontract exceeding $150,000 financed in whole or in part with Federal assistance provided by FEMA.

  - Suspension and Debarment

    - (1)  This Agreement is a covered transaction for purposes of 2 C.F.R. pt. 180 and 2 C.F.R. pt. 3000. As such, Contractor is required to verify that none of Contractor’s principals (defined at 2 C.F.R. § 180.995) or its affiliates (defined at 2 C.F.R. § 180.905) are excluded (defined at 2 C.F.R. § 180.940) or disqualified (defined at 2 C.F.R. § 180.935).

    - (2)  Contractor must comply with 2 C.F.R. pt. 180, subpart C and2 C.F.R. pt. 3000, subpart C, and must include a requirement to comply with these regulations in any lower tier covered transaction it enters into.

    - (3)  This certification is a material representation of fact relied upon by JEA. If it is later determined that Contractor did not comply with 2 C.F.R. pt. 180, subpart C and 2 C.F.R. pt. 3000, subpart C, in addition to remedies available to JEA, the Federal Government may pursue available remedies, including but not limited to suspension and/or debarment.

    - (4)  Contractor agrees to comply with the requirements of2 C.F.R. pt. 180, subpart C and 2 C.F.R. pt. 3000, subpart C while this offer is valid and throughout the period of any contract that may arise from this offer. Contractor further agrees to include a provision requiring such compliance in its lower tier covered transactions.

  - Domestic Preferences

    - To the extent consistent with applicable law, and to the greatest extent practicable, the purchase, acquisition, or use by Contractor of goods, products, or materials produced in the United States (including but not limited to iron, aluminum, steel, cement, and other manufactured products) is preferred for materials being used in the performance of Work under this Contract.

    - (b) For purposes of this section:

    - (1) “Produced in the United States” means, for iron and steel products, that all manufacturing processes, from the initial melting stage through the application of coatings, occurred in the United States.

    - (2) “Manufactured products” means items and construction materials composed in whole or in part of non-ferrous metals such as aluminum; plastics and polymer-based products such as polyvinyl chloride pipe; aggregates such as concrete; glass, including optical fiber; and lumber.

  - Prohibition on Certain Telecom and Video Surveillance Services or Equipment

    - No funds may be expended under this Agreement to:

    - (1) Procure or obtain;

    - (2) Extend or renew a contract to procure or obtain; or

    - (3) Enter into a contract (or extend or renew a contract) to procure or obtain equipment, services, or systems that uses covered telecommunications equipment or services as a substantial or essential component of any system, or as critical technology as part of any system. For the purposes of this section, “covered telecommunications equipment” is defined as:

    - (i)   Telecommunications equipment produced by Huawei Technologies Contractor or ZTE Corporation (or any subsidiary or affiliate of such entities);

    - (ii)  For the purpose of public safety, security of government facilities, physical security surveillance of critical infrastructure, and other national security purposes, video surveillance and telecommunications equipment produced by Hytera Communications Corporation, Hangzhou Hikvision Digital Technology Contractor, or Dahua Technology Contractor (or any subsidiary or affiliate of such entities);

    - (iii) Telecommunications or video surveillance services provided by such entities or using such equipment; or

    - (iv) Telecommunications or video surveillance equipment or services produced or provided by an entity that the Secretary of Defense, in consultation with the Director of the National Intelligence or the Director of the Federal Bureau of Investigation, reasonably believes to be an entity owned or controlled by, or otherwise connected to, the government of a covered foreign country.

  - License and Delivery of Works Subject to Copyright and Data Rights

    - Contractor grants to JEA, a paid-up, royalty-free, nonexclusive, irrevocable, worldwide license in data first produced in the performance of this contract to reproduce, publish, or otherwise use, including prepare derivative works, distribute copies to the public, and perform publicly and display publicly such data. For data required by the Agreement but not first produced in the performance of this Agreement, Contractor will identify  such data and grant to JEA or acquires on its behalf a license of the same scope as for data first produced in the performance of this contract. Data, as used herein, shall include any work subject to copyright under 17 U.S.C. § 102, for example, any written reports or literary works, software and/or source code, music, choreography, pictures or images, graphics, sculptures, videos, motion pictures or other audiovisual works, sound and/or video recordings, and architectural works. Upon or before the completion of this contract, Contractor will deliver to JEA data first produced in the performance of this contract and data required by the Agreement but not first produced in the performance of this contract in formats acceptable by JEA.

  - Byrd Anti-Lobbying Amendment, 31 U.S.C. § 1352 (as amended)

    - By the execution of this agreement Contractor certifies that for Contracts in the amount of one hundred thousand dollars ($100,000.00) or more, as required under 31 U.S.C. § 1352 that it will not and has not used Federal appropriated funds to pay any person or organization for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, officer or employee of Congress, or an employee of a Member of Congress in connection with obtaining any Federal contract, grant, or any other award covered by 31 U.S.C. § 1352. Contractor shall also disclose any lobbying with non-Federal funds that takes place in connection with obtaining any Federal award. Such disclosures shall be forwarded to JEA, who in turn will forward the certification(s) to the Federal awarding agency.  By execution of this Agreement, Contractor certifies the following:

    - CERTIFICATION REGARDING LOBBYING

    - Certification for Contracts, Grants, Loans, and Cooperative Agreements

    - The undersigned certifies, to the best of his or her knowledge and belief, that:

    - 1.  No Federal appropriated funds have been paid or will be paid, by or on behalf of the undersigned, to any person for influencing or attempting to influence an officer or employee of an agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with the awarding of any Federal contract, the making of any Federal grant, the making of any Federal loan, the entering into of any cooperative agreement, and the extension, continuation, renewal, amendment, or modification of any Federal contract, grant, loan, or cooperative agreement.

    - 2.  If any funds other than Federal appropriated funds have been paid or will be paid to any person for influencing or attempting to influence an officer or employee of any agency, a Member of Congress, an officer or employee of Congress, or an employee of a Member of Congress in connection with this Federal contract, grant, loan, or cooperative agreement, the undersigned shall complete and submit Standard Form-LLL, “Disclosure Form to Report Lobbying,” in accordance with its instructions.

    - 3.  The undersigned shall require that the language of this certification be included in the award documents for all subawards at all tiers (including subcontracts, subgrants, and contracts under grants, loans, and cooperative agreements) and that all subrecipients shall certify and disclose accordingly.

    - This certification is a material representation of fact upon which reliance was placed when this transaction was made or entered into. Submission of this certification is a prerequisite for making or entering into this transaction imposed by Section 1352, Title 31, U.S. Code. Any person who fails to file the required certification shall be subject to a civil penalty of not less than $10,000 and not more than $100,000 for each such failure.

    - Contractor, certifies or affirms the truthfulness and accuracy of each statement of its certification and disclosure, if any. In addition, Contractor understands and agrees that the provisions of 31 U.S.C. Chap.38, Administrative Remedies for False Claims and Statements, apply to this certification and disclosure, if any.

  - Procurement of Recovered Materials

    - (1)  In the performance of this contract, Contractor shall make maximum use of products containing recovered materials that are EPA-designated items unless the product cannot be acquired—

    - (a)  Competitively within a timeframe providing for compliance with the contract performance schedule;

    - (b)  Meeting contract performance requirements; or

    - (c)  At a reasonable price.

    - (2)  Information about this requirement, along with the list of EPA- designated items, is available at EPA’s Comprehensive Procurement Guidelines web site, https://www.epa.gov/smm/comprehensive-procurement-guideline-cpg-program.

    - (3)  Contractor also agrees to comply with all other applicable requirements of Section 6002 of the Solid Waste Disposal Act.

  - Access to Records

    - The following access to records requirements apply to this contract:

    - (1)  Contractor agrees to provide JEA the FEMA Administrator, the Comptroller General of the United States, or any of their authorized representatives access to any books, documents, papers, and records of Contractor which are directly pertinent to this Agreement for the purposes of making audits, examinations, excerpts, and transcriptions.

    - (2)  Contractor agrees to permit any of the foregoing parties to reproduce by any means whatsoever or to copy excerpts and transcriptions as reasonably needed.

    - (3)  For FEMA-funded contracts, Contractor agrees to provide the FEMA Administrator or his authorized representatives access to construction or other work sites pertaining to the work being completed under the Agreement.

    - (4) For FEMA-funded contracts, in compliance with the Disaster Recovery Act of 2018, JEA and Contractor acknowledge and agree that no language in this contract is intended to prohibit audits or internal reviews by the FEMA Administrator or the Comptroller General of the United States.

  - DHS SEAL, LOGO, AND FLAGS

    - Contractor shall not use the Department of Homeland Security (DHS) seal(s), logos, crests, or reproductions of flags or likenesses of DHS agency officials without specific FEMA pre-approval.

  - No Obligation By Federal Government

    - The Federal Government is not a party to this contract and is not subject to any obligations or liabilities to the non-Federal entity, Contractor, or any other party pertaining to any matter resulting from the Agreement.

  - Program Fraud and False Or Fraudulent Statements or Related Acts

    - Contractor acknowledges that 31 U.S.C. Chap. 38 (Administrative Remedies for False Claims and Statements) applies to Contractor’s actions pertaining to this contract.

  - Compliance with Federal Law, Regulations, and Executive Orders

    - This is an acknowledgement that FEMA financial assistance or federal grant money will be used to fund the Agreement only.  Contractor will comply will all applicable federal law, regulations, executive orders, and FEMA policies, procedures, and directives.

Exhibit T

PIE Purchase Agreement

[Attached]

Exhibit U

GSU Transformers

[NTD: To be inserted]

Exhibit V

UAT Transformers

[NTD: To be inserted]

Note to Contractor: JEA will provide this at a later date.

NTD: This is to be a Level 3 project schedule.

Baseline Project Schedule to include delivery dates for the Power Island Equipment.

NTD: To be included if the Project utilizes any federal funding.