## Sheet1 (2) (hidden)
Appendix B Bid Workbook - 085-17 Construction of 16” Water Main Crossing of Silver Smith Creek (Enter Data in yellow cells only) | [7 empty] | Odor control | Perm Facilities | Temporary Solids Capture Facility | Cleaning | Ops Contingency | Perm facilities Contingency
M&P/Spec No. * | ITEM No. | ITEM DESCRIPTION | Total Est Quantity | Units | Unit Cost | Total Cost | IN Cost estimate | 219000 | 979730 | 532700 | 504000 | 103595 | 80828
| 1 | Construction of Intermediate Pigging Station 1A | 1 | LS | 42000 | 42000 |  |  | 42000
| 2 | Construction of Intermediate Pigging Station 1B | 1 | LS | 42000 | 42000 |  |  | 42000
| 3 | Construction of Intermediate Pigging Station 3 | 1 | LS | 42000 | 42000 |  |  | 42000
| 4 | Construction of Pigging Launching/Receiving Station at CR 210 BPS and RCW extension | 1 | LS | 500000 | 500000 |  |  | 500000
| 5 | TSCF Setup, Maintenance, etc for duration of project & restoration post | 1 | LS | 500000 | 500000 |  |  |  | 500000
| 6 | Cleaning Runs of Segment A1 | 10 | EA | 4000 | 40000 |  |  |  |  | 40000
| 7 | Cleaning Runs of Segment A2 & A1 | 10 | EA | 8000 | 80000 |  |  |  |  | 80000
| 8 | Cleaning Runs of Segment B, A2 & A1 | 10 | EA | 12000 | 120000 |  |  |  |  | 120000
| 9 | Solids hauled to JEA Facilities | 200 | Wet Ton | 50 | 10000 |  |  |  |  | 10000
| 10 | Solids hauled offsiete | 1800 | Wet Ton | 127 | 228600 |  |  |  |  | 228600
| 11 | Chemical Counteractnt and Odor Control Setup and Operation | 1 | LS | 150000 | 150000 |  | 150000
Allowances
|  | TSCF and odor control Maintenance past 5/31/18 (If not fault of contractor) | 4 | Week | 20000 | 80000 | [6 empty] | 80000
|  | Downtime post drainage < 2 days | 30 | Days | 1250 | 37500 |  |  |  |  | 37500
|  | Work pause 2 days-1 week | 20 | Days | 1250 | 25000 | [5 empty] | 25000
|  | Work pause >-1 week | 10 | Days | 500 | 5000 | [5 empty] | 5000
|  | H2O2 | 2000 | Gallons | 2 | 4000 |  | 4000
|  | FeCl2 | 5000 | Gallons | 3 | 15000 |  | 15000
|  | Offsite Disposal of Sewage during downtime | 300000 | Gallons | 0.25 | 75000 | [5 empty] | 75000
| SUBTOTAL |  |  |  |  | 1996100
| ***902. GENERAL CONDITIONS LUMP SUM (MAX 10% OF SUBTOTAL) |  |  |  |  | 199610
| TOTAL BID PRICE (transfer this number to TOTAL BID PRICE line in Appendix B Bid Form |  |  |  |  | 2195710
Additive Alternative
2.16.3*** | 12 | Construction of Intermediate Pigging Station 2A | 1 | LS | 42000 | 42000 |  |  | 42000
2.17.10*** | 13 | Construction of Intermediate Pigging Station 2B | 1 | LS | 42000 | 42000 |  |  | 42000
|  | Construction of Pigging Launching Station at Twin Creeks MPS | 1 | LS | 250000 | 250000 |  |  | 250000
|  | Construction of Temporary RCW Jumper Connection | 1 | LS | 20000 | 20000 |  |  |  | 20000
| SUBTOTAL |  |  |  |  | 354000 |  | 169000 | 960000 | 520000 | 516100 | 105000 | 80000
[7 empty] | Unallocated | 50000 | 19730 | 12700 | -12100 | -1405 | 828
| TOTAL BID PRICE (transfer this number to TOTAL BID PRICE line in Appendix B Bid Form |  |  |  |  | 2549710

## Sheet1
Appendix B - Bid Workbook 97661 DES Insulation Replacement (Enter data in yellow cells only)
ITEM No. | ITEM DESCRIPTION | Total Est Quantity | Units | Unit Cost | Total Cost
1 | Chiller: Remove insulation from evaporator barrel and both chiller legs. Re-insulate with 1.5" closed-cell foam insulation. | 5 | EA | 0 | 0
2 | Chiller: Remove insulation from chiller head, 18" flanges at head, 16" elbow, 16" piping and 18" valve above elbow. Re-insulate head, flanges and valve with 1.5" closed-cell foam insulation. Re-insulate 16" piping and elbow with 2" thick foam glass, finished with White PVC Jacket. | 3 | EA | 0 | 0
3 | Chiller: Remove deteriorated insulation from suction elbow. Re-insulate elbow with 1.5" closed-cell foam insulation. | 11 | EA | 0 | 0
4 | Chiller: Remove deteriorated insulation from economizer barrel and all economizer piping. Re-insulate economizer barrel and piping with 1.5" closed-cell foam insulation. | 5 | EA | 0 | 0
5 | Chilled Water Pump: Remove existing insulation from chilled water pump. Re-insulate pump with 1.5" closed-cell foam insulation. Includes entire pump, suction diffuser, all 18” flanges | 1 | EA | 0 | 0
6 | Chill Water Piping & Valves: 16” valve and stem to actuator | 1 | EA | 0 | 0
7 | Chill Water Piping & Valves: 18” valve and stem to actuator | 1 | EA | 0 | 0
8 | Chill Water Piping & Valves: 30” chill water piping @10’ section. 2” thick foam glass with PVC Jacket | 1 | EA | 0 | 0
TOTAL BID PRICE (transfer this number to TOTAL BID PRICE line in Appendix B - Bid Form) |  |  |  |  | 0